## Correlated risk portfolio
Impact
Risk | Min | Most likely | Max | Probability | Risk simulation
A | 7 | 10 | 15 | 30% | 0
B | 9.8 | 12 | 18 | 20% | 14.6924
C | 10.4 | 13 | 19.5 | 10% | 0
D | 11.2 | 14 | 21 | 15% | 0
E | 6.4 | 8 | 12 | 22% | 0
F | 4.8 | 6 | 9 | 12% | 0 | Technique: model the total impact of a cascading set of risk events that threaten a project. The probability and impact of risks depend on each other in the following way: if Risk A occurs it increases the probability of Risks D and E occurring; and if Risks B, C and F all occur then both the probability of occurrence and the size of impact of Risk H increase.
G | 6.4 | 8 | 12 | 7% | 0
H | 9.6 | 12 | 18 | 5% | 0
I | 8.8 | 11 | 16.5 | 19% | 0
J | 11.2 | 14 | 21 | 23% | 14.6242
Sum |  |  |  | Total risk impact with correlation | 29.3166
Formulae table
C3:C12 | =D3*0.8
E3:E12 | =D3*1.5
F3:F12 | =VosePERT(C3,D3,E3)
F6 | =IF(OR(G3,G5),50%,15%)
F7 | =IF(OR(G3,G6),45%,22%)
F10 | =IF(AND(G4,G5,G7,G8),13%,5%)
G3:G9, G11:G12 | =VoseInput(B3)+VoseRiskEvent(F3,VosePERTObject(C3,D3,E3))
G10 | =VoseInput(B10)+IF(AND(G4,G5,G7,G8),3.2,1)*VoseRiskEvent(F10,VosePERTObject(C10,D10,E10))
G13 | =VoseOutput(F13)+SUM(G3:G12)