## Correlated risk portfolio
Correlated risk portfolio
Problem: We have a portfolio of risks (A to J), each of which is described by a PERT distribution. The risks are correlated in the following way: a) If A or C occurs, D increases in size by 50%; b) If A or D occurs, E increases to 45% probability and c) If all of B, C, E, F occur, H increases in size to 320% and to 13% probability. Our task is to calculate the total risk of the portfolio.
Risk | Min (80%) | Most likely | Max (150%) | Probability | Risk distribution
A | 8 | 10 | 15 | 30% | 0
B | 9.6 | 12 | 18 | 20% | 0
C | 10.4 | 13 | 19.5 | 10% | 0
D | 11.2 | 14 | 21 | 15% | 0
E | 6.4 | 8 | 12 | 22% | 0
F | 4.8 | 6 | 9 | 12% | 0
G | 6.4 | 8 | 12 | 7% | 0
H | 9.6 | 12 | 18 | 5% | 0
I | 8.8 | 11 | 16.5 | 19% | 13.8776
J | 11.2 | 14 | 21 | 23% | 0
Sum | 86.4 | 108 | 162 |  | 13.8776