## Sheet1
Project start date |  | 2012-08-10
| Start | Duration d (weeks) |  |  |  | Finish | Start | Start lag (weeks) |  |  |  | Finish | Finish lag (weeks)
| Date St | Dist | Min | ML | Max | Date Fin | logic | Dist | Min | ML | Max | logic | Dist | Min | ML | Max
Task1 | 2012-08-10 | 9.8567 | 7 | 9 | 12 | 2012-10-17 23:56 | =start date |  |  |  |  | St+d
Task2 | 2012-10-17 23:56 | 8.7105 | 6 | 7 | 9 | 2012-12-17 23:18 | =Fin1 |  |  |  |  | St+d
Task3 | 2012-10-17 23:56 | 8.8901 | 8 | 9 | 13 | 2012-12-19 05:28 | =St2 |  |  |  |  | St+d
Task4 | 2012-11-14 23:56 | 20.7246 | 15 | 18 | 21 | 2013-04-09 01:40 | =St3+lag | 4 | 2 | 3 | 7 | =Fin3
Task5 | 2012-10-17 23:56 | 13.7987 | 12 | 13 | 17 | 2013-02-12 01:40 | =St2 |  |  |  |  | =Fin4-lag | 8 | 7 | 8 | 9
Task1
Formulae table
Dist | =VoseTriangle(Min,ML,Max)
C6 | =D2 | [6 empty] | Task2
C7 | =H6
C8 | =C7
C9 | =C8+7*J9 | [6 empty] | Task3
C10 | =C7
H6 | =C6+7*D6
H7 | =C7+7*D7 | [7 empty] | Task4
H8 | =C8+7*C8
H9 | =MAX(C9+7*D9,H8)
H10 | =MAX(C10+D10*7,H9-O10*7) | [6 empty] | Task5
Formulas:
Start = [Finish, row above]
Start = [Start, row above]
Finish = [Start]+7*[Duration d (weeks)]
Finish = MAX([Start]+7*[Duration d (weeks)],[Finish, row above])
Project schedule model Technique: a simple project schedule model: we have 5 tasks of uncertain duration to do, with dependencies as indicated in the diagram. When will the project be finished?