## Sheet1
Project start date | 2012-08-10
| Start | Duration d (weeks) |  |  |  | Finish | Probability | Start | Start lag (weeks) |  |  |  | Finish | Finish lag (weeks)
| Date St | Dist | Min | ML | Max | Date Fin |  | logic | Dist | Min | ML | Max | logic | Dist | Min | ML | Max
Task1 | 2012-08-10 | 9.4418 | 8 | 9 | 12 | 2012-10-15 02:13 |  | =Start date |  |  |  |  | =St+d
Task2 normal | 2012-10-15 02:13 | 7.5714 | 6 | 7 | 9 | 2012-12-07 02:13 | 70% | =Fin1 |  |  |  |  | =St+d
=Task2 risk | 2012-10-15 02:13 | 14.3811 | 10 | 12 | 15 | 2013-01-23 18:14 | 20% | =Fin1 |  |  |  |  | =St+d
=Task2 opportunity | 2012-10-15 02:13 | 7.2757 | 5 | 6 | 8 | 2012-12-05 00:33 | 10% | =Fin1 |  |  |  |  | =St+d
Task2 total | [5 empty] | 2012-12-07 02:13 | [6 empty] | Discrete
Task3 | 2012-12-07 02:13 | 8.0929 | 7 | 8 | 12 | 2013-02-01 17:49 |  | =Fin2total |  |  |  |  | =St+d
| Formulae table | [6 empty] | Task1
| Dist | =VoseTriangle(Min,ML,Max)
| C6 | =C2
| C7:C9 | =$H$6 | [6 empty] | Task2 Normal
| C11 | =H10
| H6:H9,H11 | =C6+7*D6
| H10 | =VoseDiscrete(H7:H9,I7:I9) | [6 empty] | Task2 risk
Task2 opportunity
Task3
Formulas:
Start = [Finish, row above]
Finish = [Start]+7*[Duration d (weeks)]
Finish = _XLL.VOSEDISCRETE(H7:[Finish, row above],I7:[Probability, row above])
Project schedule model Technique: a project schedule model with schedule risk modeled as alternative duration.