## Pylons
Pylons
Problem: Your company has been invited to bid for a project to design and construct a line of 16 electricity pylons. Estimates are based on PERT distributions (using absolute minimum, most likely and absolute maximum) unless indicated. Produce distributions of the total project cost and duration. Use a scatter plot to illustrate the relationship between the project’s cost and duration. Plot iterations above and below 35 weeks separately on the same graph and fit regression lines through the two data sets.
Number of pylons | 16
Design: | Min | Most likely | Max | Actual | Summary costs: | USD
Summary costs:
In-house design | 150000 | 165000 | 190000 | 161465.7294 | Design: | 214329.6151
Sub-contracted | 180000 | 200000 | 235000 | 214329.6151 | Construction foundation: | 533638.6473
Prob in house |  |  |  | 60% | Construction pylon: | 920339.5825
Prob. of French job |  | 40% |  | 40% | Penalty: | 0
|  | Total costs |  | 214329.6151 | Sum: | 1668307.8448
[5 empty] | Project duration: | 33.5208
Construction foundation: | Min | Most likely | Max | Actual
Material/pylon | 6200 | 7000 | 7900 | 6491.9512
Man hours for all pylons |  | 9600 |  | 9172.5981
Cost/man hour |  | 7.5 |  | 7.5 | Total time | 33.5208
Total plant cost | 250000 | 300000 | 380000 | 360972.9429 | Over time | 0
[5 empty] | Weeks | 0
|  | Total costs |  | 533638.6473 | Penalty/wk | 25000
[5 empty] | Penalty | 0
Construction pylon: | Min | Most likely | Max | Actual
Steel cost/pylon | 52000 | 54000 | 58500 | 54600.0422
Man hours/pylon | 200 | 240 | 270 | 224.7063
Cost/man hour |  | 13 |  | 13
|  | Total costs |  | 920339.5825
Time constraints: | Min | Most likely | Max | Actual
Design | 10 | 12 | 15 | 12.1206
Foundations | 14 | 16 | 21 | 16.8334
Time foundation-last pylon | 4 | 4.5 | 5.5 | 4.5668

## Scatter plot
Total time | Grand Total
Output | Output
C35 | C40
29.1735 | 1588830
29.2081 | 1575811
29.2191 | 1575335
29.2299 | 1600728
29.2771 | 1654731
29.3524 | 1685559
29.4509 | 1585270
29.5135 | 1538724
29.5586 | 1592153
29.5606 | 1658018
29.6199 | 1571394
29.6529 | 1574689
29.6899 | 1578306
29.6998 | 1548175
29.7069 | 1620791
29.7439 | 1526042
29.7483 | 1618874
29.7921 | 1541882
29.8051 | 1557140
29.813 | 1629656
29.8329 | 1624459
29.835 | 1602043
29.8429 | 1555199
29.8587 | 1579727
29.8646 | 1559254
29.8805 | 1594812
29.8848 | 1547583
29.8865 | 1582572
29.8945 | 1606123
29.914 | 1589196
29.9251 | 1583056
29.9348 | 1601117
29.9511 | 1573736
29.9716 | 1636233
29.9843 | 1534815
30.0174 | 1533950
30.0259 | 1640341
30.0733 | 1619720
30.0754 | 1592032
30.082 | 1539225
30.0846 | 1546895
30.0946 | 1552821
30.1098 | 1614966
30.1415 | 1607306
30.1431 | 1601594
30.1621 | 1621437
30.1684 | 1579981
30.1742 | 1528499
30.1745 | 1582505
30.1745 | 1622639
30.1767 | 1592665
30.2063 | 1645565
30.2246 | 1605414
30.2417 | 1654932
30.2461 | 1610207
30.2464 | 1556210
30.2581 | 1577026
30.2753 | 1575220
30.2781 | 1598741
30.2913 | 1581719
30.3011 | 1560883
30.3048 | 1567787
30.3145 | 1587439
30.3172 | 1585438
30.3277 | 1640480
30.3344 | 1631736
30.339 | 1613157
30.344 | 1609097
30.3506 | 1552693
30.352 | 1559456
30.3606 | 1554484
30.3782 | 1652322
30.3846 | 1597619
30.3893 | 1562100
30.3932 | 1617388
30.3944 | 1573917
30.3976 | 1587469
30.4033 | 1528119
30.4064 | 1616432
30.4077 | 1535051
30.4124 | 1623479
30.4244 | 1565818
30.4254 | 1638399
30.427 | 1605984
30.4343 | 1616542
30.4386 | 1566748
30.4459 | 1558355
30.4526 | 1623279
30.4555 | 1624160
30.4564 | 1618422
30.4625 | 1583443
30.463 | 1585144
30.4687 | 1658872
30.4829 | 1606314
30.4836 | 1539967
30.4847 | 1522198
30.4931 | 1574711
30.5028 | 1620651
30.5072 | 1571981
30.5149 | 1573900
30.518 | 1605122
30.5204 | 1632872
30.5225 | 1585604
30.5354 | 1602537
30.5395 | 1628440
30.5403 | 1657387
30.5456 | 1598188
30.5459 | 1542606
30.5502 | 1611746
30.5504 | 1564333
30.5508 | 1600555
30.5588 | 1598446
30.5743 | 1653538
30.5748 | 1650862
30.5874 | 1603368
30.5911 | 1550221
30.604 | 1630230
30.6089 | 1593546
30.6119 | 1631828
30.6162 | 1634057
30.6184 | 1574321
30.6192 | 1567804
30.6195 | 1606549
30.6223 | 1660568
30.6235 | 1545434
30.6278 | 1633146
30.6294 | 1536520
30.6316 | 1675664
30.6372 | 1562285
30.6429 | 1616635
30.6502 | 1559110
30.6508 | 1555237
30.6579 | 1561197
30.66 | 1618055
30.6603 | 1606765
30.6608 | 1553949
30.6648 | 1583666
30.6653 | 1579237
30.6662 | 1542402
30.668 | 1596767
30.6737 | 1604682
30.6771 | 1620576
30.6777 | 1612065
30.681 | 1556438
30.6818 | 1559495
30.682 | 1649831
30.6828 | 1608614
30.6941 | 1524379
30.6949 | 1571651
30.6958 | 1594021
30.6961 | 1570827
30.6967 | 1526545
30.7067 | 1534854
30.7116 | 1658632
30.7117 | 1629700
30.7167 | 1562312
30.721 | 1550330
30.7255 | 1599218
30.7276 | 1619673
30.7298 | 1614752
30.7301 | 1593877
30.7352 | 1558141
30.7364 | 1620351
30.7426 | 1517238
30.7434 | 1579301
30.7573 | 1632696
30.7601 | 1577606
30.7657 | 1567437
30.7946 | 1548617
30.7964 | 1587180
30.8037 | 1599374
30.8062 | 1631570
30.8076 | 1630691
30.81 | 1595651
30.8154 | 1644751
30.8213 | 1614917
30.8229 | 1600029
30.828 | 1547924
30.8281 | 1640816
30.8285 | 1622113
30.8314 | 1567613
30.8438 | 1533264
30.8457 | 1598342
30.8564 | 1620147
30.8596 | 1576806
30.8618 | 1557834
30.8666 | 1545677
30.8703 | 1541479
30.8707 | 1605727
30.8736 | 1598881
30.8753 | 1671550
30.877 | 1604764
30.8833 | 1595677
30.8916 | 1596248
30.8934 | 1563170
30.8975 | 1606135
30.9093 | 1649241
30.9111 | 1515623
30.9171 | 1540978
30.9187 | 1647336
30.9188 | 1539117
30.9299 | 1580300
30.9325 | 1584595
30.9353 | 1629422
30.9436 | 1585063
30.9454 | 1559275
30.9455 | 1604750
30.9498 | 1522393
30.951 | 1549922
30.9511 | 1522333
30.9572 | 1567386
30.9584 | 1619059
30.9585 | 1564039
30.9591 | 1503306
30.9665 | 1570561
30.9682 | 1560822
30.9706 | 1557500
30.9737 | 1565480
30.9737 | 1566172
30.9783 | 1576172
30.9844 | 1637986
30.9912 | 1540495
30.9937 | 1564128
30.9975 | 1655738
30.9998 | 1694700
31.0024 | 1550031
31.0065 | 1532914
31.0075 | 1568278
31.0089 | 1569623
31.0091 | 1640026
31.0106 | 1603060
31.0118 | 1614776
31.0157 | 1610253
31.0204 | 1660085
31.0239 | 1571236
31.0258 | 1557122
31.0269 | 1551079
31.0307 | 1592434
31.0336 | 1554613
31.0355 | 1561062
31.0396 | 1643148
31.0399 | 1614897
31.042 | 1692355
31.0441 | 1610900
31.0468 | 1702296
31.0479 | 1609044
31.05 | 1584844
31.0521 | 1594398
31.0561 | 1622424
31.0595 | 1576432
31.0604 | 1582260
31.0636 | 1587792
31.0707 | 1639824
31.0787 | 1597704
31.0801 | 1683240
31.0811 | 1598964
31.0861 | 1600977
31.0862 | 1581720
31.0874 | 1588726
31.0879 | 1650408
31.0881 | 1532759
31.0889 | 1560608
31.0916 | 1618191
31.0924 | 1632455
31.0927 | 1521877
31.0993 | 1580452
31.1005 | 1623025
31.1008 | 1554235
31.1033 | 1609771
31.1075 | 1622338
31.1088 | 1587160
31.1094 | 1615590
31.1124 | 1603109
31.1198 | 1617476
31.1203 | 1546398
31.1234 | 1597891
31.1246 | 1585781
31.1291 | 1591174
31.133 | 1665860
31.1376 | 1589871
31.1441 | 1526470
31.1441 | 1555452
31.1444 | 1661977
31.1475 | 1567197
31.1503 | 1676016
31.1507 | 1601065
31.1557 | 1577149
31.159 | 1640006
31.1607 | 1654016
31.1609 | 1651865
31.1656 | 1610317
31.1666 | 1562051
31.168 | 1599498
31.1717 | 1562145
31.1727 | 1623996
31.1729 | 1652765
31.1742 | 1544550
31.1787 | 1590478
31.186 | 1589797
31.1877 | 1536563
31.1885 | 1634619
31.1915 | 1540952
31.1949 | 1541208
31.1971 | 1600496
31.1978 | 1595116
31.1992 | 1587724
31.1994 | 1645232
31.1999 | 1594714
31.2015 | 1596071
31.2059 | 1632723
31.2091 | 1556473
31.211 | 1541957
31.215 | 1578533
31.2179 | 1578614
31.2279 | 1596142
31.229 | 1631002
31.2315 | 1586965
31.2349 | 1571533
31.2356 | 1607893
31.2368 | 1568410
31.2377 | 1562548
31.2433 | 1589992
31.244 | 1658041
31.244 | 1611965
31.2469 | 1598241
31.2494 | 1648693
31.2523 | 1547930
31.2555 | 1585908
31.2613 | 1560043
31.2613 | 1675707
31.2619 | 1602743
31.263 | 1638657
31.2654 | 1570954
31.2682 | 1579943
31.2693 | 1635736
31.2704 | 1681330
31.2732 | 1553941
31.2783 | 1567528
31.2799 | 1560695
31.2807 | 1584249
31.2811 | 1618210
31.285 | 1551433
31.2856 | 1599721
31.2894 | 1596710
31.2947 | 1604664
31.2974 | 1546098
31.299 | 1541801
31.2994 | 1574465
31.2997 | 1589761
31.3005 | 1584446
31.3026 | 1637401
31.3067 | 1596555
31.3103 | 1563260
31.311 | 1597816
31.3143 | 1593674
31.324 | 1580628
31.3257 | 1632127
31.3287 | 1592515
31.3382 | 1612399
31.3403 | 1583623
31.342 | 1609900
31.3426 | 1548771
31.3441 | 1541033
31.346 | 1542042
31.3469 | 1639020
31.3479 | 1554977
31.3483 | 1636702
31.3525 | 1552176
31.3529 | 1609494
31.354 | 1551462
31.3658 | 1626499
31.3694 | 1522516
31.3703 | 1591523
31.3714 | 1543277
31.3748 | 1646271
31.3795 | 1610491
31.3812 | 1555151
31.3819 | 1603272
31.3823 | 1634953
31.3875 | 1584257
31.3877 | 1559174
31.3964 | 1607503
31.3969 | 1553475
31.3985 | 1562274
31.4021 | 1645142
31.4025 | 1623029
31.4035 | 1547423
31.4044 | 1580485
31.4053 | 1533708
31.4054 | 1593690
31.4075 | 1596135
31.408 | 1589558
31.4089 | 1613932
31.4141 | 1672684
31.4159 | 1654084
31.4169 | 1560591
31.4176 | 1585245
31.4215 | 1579489
31.4237 | 1585253
31.426 | 1640908
31.4296 | 1539887
31.4299 | 1613445
31.4321 | 1579815
31.4361 | 1621033
31.4402 | 1597007
31.4585 | 1639203
31.4601 | 1574055
31.4617 | 1610801
31.462 | 1559653
31.4642 | 1598800
31.4664 | 1582606
31.4669 | 1570352
31.4675 | 1553151
31.4686 | 1603736
31.4696 | 1580109
31.4727 | 1587810
31.4731 | 1573628
31.4778 | 1616555
31.4842 | 1640497
31.4855 | 1566874
31.4871 | 1616628
31.4913 | 1535428
31.4913 | 1646200
31.4954 | 1663846
31.4954 | 1545087
31.4965 | 1612885
31.4981 | 1628897
31.5012 | 1659632
31.503 | 1624949
31.5052 | 1622840
31.5104 | 1596115
31.5178 | 1523513
31.5183 | 1606823
31.5186 | 1565166
31.528 | 1631691
31.5295 | 1657007
31.5314 | 1572275
31.5328 | 1577725
31.533 | 1664509
31.5357 | 1550880
31.5397 | 1622496
31.5409 | 1544082
31.5432 | 1612356
31.5432 | 1654137
31.5453 | 1579596
31.5459 | 1539384
31.5464 | 1625922
31.5467 | 1535345
31.5507 | 1609231
31.5513 | 1556387
31.5548 | 1558635
31.5556 | 1526407
31.5607 | 1540444
31.5647 | 1574164
31.5655 | 1558241
31.5671 | 1557155
31.5712 | 1621658
31.5713 | 1564948
31.5714 | 1610965
31.5726 | 1596167
31.5784 | 1576154
31.5795 | 1603031
31.5828 | 1571396
31.5842 | 1569743
31.5845 | 1580253
31.5858 | 1602459
31.5873 | 1623083
31.5933 | 1566300
31.5942 | 1600399
31.5949 | 1585146
31.5968 | 1558518
31.5991 | 1618995
31.5993 | 1558535
31.5996 | 1568817
31.5997 | 1562193
31.6015 | 1583377
31.6043 | 1633965
31.6057 | 1542896
31.6079 | 1556517
31.6102 | 1565297
31.6105 | 1604846
31.6115 | 1667205
31.6118 | 1571489
31.6129 | 1601267
31.6139 | 1635712
31.614 | 1594849
31.6169 | 1587603
31.6189 | 1548357
31.6236 | 1612131
31.6239 | 1567755
31.6246 | 1643871
31.6279 | 1566277
31.6283 | 1643962
31.6293 | 1628052
31.6295 | 1541296
31.6324 | 1584041
31.6329 | 1647674
31.6343 | 1619041
31.6343 | 1612329
31.6352 | 1596587
31.6374 | 1604058
31.6408 | 1551424
31.6489 | 1606312
31.6495 | 1627585
31.6512 | 1640090
31.6547 | 1652951
31.6563 | 1620048
31.6575 | 1629543
31.6576 | 1602553
31.6596 | 1555674
31.66 | 1563184
31.6607 | 1622385
31.6607 | 1570985
31.6616 | 1591429
31.6632 | 1531642
31.6638 | 1578002
31.6688 | 1603437
31.6695 | 1633682
31.6746 | 1618759
31.6782 | 1564570
31.679 | 1583247
31.682 | 1605879
31.6829 | 1568394
31.6833 | 1595731
31.6836 | 1651882
31.6857 | 1583636
31.6866 | 1575878
31.6881 | 1593661
31.6934 | 1634695
31.7017 | 1559369
31.7072 | 1642799
31.7086 | 1597491
31.7089 | 1647413
31.7089 | 1620463
31.7091 | 1637969
31.7101 | 1611009
31.7103 | 1629933
31.7125 | 1562825
31.7144 | 1547143
31.7153 | 1586188
31.7154 | 1605619
31.716 | 1603844
31.7167 | 1639683
31.7185 | 1597697
31.7188 | 1583187
31.7235 | 1673196
31.7248 | 1571873
31.7271 | 1587217
31.7273 | 1573144
31.7289 | 1598422
31.7295 | 1595352
31.7296 | 1594658
31.7306 | 1645965
31.7327 | 1572408
31.734 | 1546119
31.7342 | 1603115
31.7344 | 1643139
31.7353 | 1597107
31.7398 | 1591429
31.7405 | 1581092
31.741 | 1637785
31.7423 | 1584538
31.7428 | 1684750
31.7494 | 1584308
31.7502 | 1609671
31.7525 | 1580754
31.7535 | 1569481
31.7545 | 1573262
31.7568 | 1591120
31.7619 | 1599580
31.7622 | 1637801
31.7628 | 1571838
31.7655 | 1609109
31.7674 | 1664322
31.7679 | 1539983
31.7694 | 1618724
31.7707 | 1578776
31.7749 | 1655807
31.7764 | 1638866
31.7774 | 1587172
31.7777 | 1525815
31.7792 | 1615923
31.7862 | 1622487
31.7867 | 1576176
31.7895 | 1571955
31.7899 | 1647179
31.79 | 1508528
31.7913 | 1557756
31.7916 | 1606283
31.792 | 1632106
31.7927 | 1649849
31.793 | 1616320
31.7961 | 1561687
31.7962 | 1628466
31.7968 | 1573538
31.8018 | 1595421
31.8019 | 1580061
31.8032 | 1592716
31.8054 | 1618601
31.806 | 1536619
31.8091 | 1549275
31.8092 | 1635129
31.8108 | 1580450
31.8124 | 1613171
31.8156 | 1574790
31.8169 | 1595965
31.8169 | 1557435
31.8171 | 1582853
31.8184 | 1573824
31.8212 | 1662123
31.8226 | 1525059
31.8234 | 1655450
31.8244 | 1572036
31.8256 | 1591223
31.8275 | 1623956
31.8277 | 1625056
31.8287 | 1581966
31.8315 | 1669183
31.8347 | 1588479
31.8352 | 1565613
31.8355 | 1535959
31.8363 | 1606789
31.8368 | 1602518
31.8382 | 1570300
31.8413 | 1539549
31.8419 | 1688860
31.8422 | 1578630
31.8446 | 1584964
31.846 | 1576779
31.8487 | 1504758
31.8487 | 1521252
31.8588 | 1602008
31.8588 | 1548918
31.8609 | 1647704
31.8618 | 1610625
31.8631 | 1569780
31.8633 | 1511454
31.8634 | 1598489
31.8636 | 1585471
31.8698 | 1630838
31.8705 | 1584407
31.8724 | 1583338
31.8733 | 1610417
31.8735 | 1565945
31.874 | 1557225
31.8749 | 1579021
31.8749 | 1633684
31.8778 | 1585267
31.8805 | 1613808
31.8807 | 1581727
31.887 | 1616443
31.8879 | 1663096
31.8889 | 1642399
31.8892 | 1624956
31.8894 | 1601603
31.8905 | 1601769
31.8911 | 1678804
31.8958 | 1596223
31.8965 | 1607254
31.8965 | 1574533
31.899 | 1569701
31.9007 | 1630411
31.9014 | 1638015
31.9017 | 1548793
31.9066 | 1572328
31.9068 | 1631826
31.9074 | 1628864
31.908 | 1625908
31.9151 | 1631866
31.9158 | 1543984
31.9195 | 1616077
31.9211 | 1612315
31.9227 | 1588878
31.9228 | 1711368
31.9239 | 1601031
31.9239 | 1593518
31.9286 | 1582586
31.9294 | 1652919
31.9327 | 1539842
31.934 | 1570581
31.9345 | 1645290
31.9363 | 1652103
31.9372 | 1582867
31.941 | 1550516
31.9422 | 1614321
31.9433 | 1607805
31.9453 | 1581847
31.946 | 1590011
31.9504 | 1553765
31.9514 | 1573379
31.9516 | 1594453
31.9548 | 1563223
31.9572 | 1584923
31.9616 | 1588775
31.9618 | 1591484
31.9622 | 1565533
31.9634 | 1591850
31.9727 | 1640153
31.9766 | 1588659
31.9819 | 1641224
31.9843 | 1686739
31.9873 | 1639656
31.9884 | 1535449
31.9886 | 1665901
31.9903 | 1573352
31.9912 | 1635527
31.9914 | 1566888
31.993 | 1565935
31.995 | 1611985
31.9968 | 1575181
31.9975 | 1621833
32.0002 | 1587698
32.0043 | 1582101
32.0133 | 1562002
32.0147 | 1641857
32.0182 | 1576458
32.0199 | 1547972
32.02 | 1606416
32.0236 | 1559724
32.0246 | 1575451
32.026 | 1603854
32.0283 | 1580732
32.0306 | 1569089
32.0307 | 1550856
32.0309 | 1610017
32.0333 | 1606892
32.0365 | 1647283
32.0412 | 1585453
32.043 | 1580022
32.0435 | 1550752
32.0437 | 1621259
32.0472 | 1604539
32.051 | 1605716
32.055 | 1568443
32.0571 | 1618143
32.0577 | 1603029
32.058 | 1571689
32.0612 | 1621901
32.0654 | 1566734
32.0665 | 1574419
32.0666 | 1621212
32.0677 | 1515257
32.069 | 1639861
32.0691 | 1547728
32.0705 | 1618828
32.0712 | 1580540
32.0725 | 1527256
32.0748 | 1587658
32.0754 | 1610905
32.0762 | 1578133
32.0785 | 1545373
32.0807 | 1551867
32.0842 | 1593153
32.0845 | 1606105
32.0859 | 1634536
32.0869 | 1614384
32.093 | 1583578
32.0963 | 1599439
32.0978 | 1549951
32.0992 | 1601026
32.1022 | 1547962
32.1028 | 1580263
32.1073 | 1540337
32.1082 | 1585307
32.1116 | 1602801
32.1129 | 1542776
32.1161 | 1548521
32.1183 | 1607652
32.1246 | 1629445
32.1268 | 1577481
32.1272 | 1641876
32.1279 | 1552183
32.1285 | 1570486
32.1294 | 1615367
32.1298 | 1613851
32.1299 | 1603607
32.1302 | 1582702
32.132 | 1580281
32.1358 | 1587067
32.1373 | 1592800
32.1379 | 1592657
32.1395 | 1590388
32.1396 | 1583162
32.1402 | 1569247
32.1418 | 1550982
32.142 | 1532219
32.1421 | 1603344
32.1424 | 1511836
32.1424 | 1527243
32.1438 | 1554518
32.1494 | 1636557
32.1499 | 1612782
32.1506 | 1608630
32.1525 | 1596315
32.1553 | 1660166
32.1602 | 1591511
32.162 | 1614357
32.1624 | 1574178
32.163 | 1583412
32.1648 | 1567643
32.1673 | 1612211
32.1744 | 1617003
32.1761 | 1606167
32.1788 | 1604485
32.1802 | 1558101
32.1812 | 1595941
32.1829 | 1609294
32.1833 | 1607861
32.1839 | 1625058
32.1841 | 1583897
32.1861 | 1588986
32.1873 | 1592441
32.1883 | 1547486
32.1894 | 1551759
32.1904 | 1563241
32.1912 | 1571884
32.1919 | 1592364
32.192 | 1562248
32.1927 | 1602782
32.1943 | 1549830
32.1949 | 1575187
32.1972 | 1596834
32.1977 | 1648633
32.1977 | 1583137
32.1992 | 1626025
32.2 | 1596101
32.2004 | 1586092
32.2011 | 1573578
32.2022 | 1630221
32.203 | 1598242
32.2059 | 1574121
32.206 | 1602902
32.2062 | 1627598
32.2078 | 1655832
32.2083 | 1584097
32.2083 | 1615459
32.2093 | 1598666
32.2097 | 1639307
32.2099 | 1582078
32.2101 | 1651248
32.2103 | 1581733
32.2119 | 1507460
32.2128 | 1533941
32.2161 | 1541999
32.2168 | 1600010
32.2171 | 1611716
32.2179 | 1542039
32.218 | 1624250
32.2204 | 1667376
32.221 | 1574833
32.2218 | 1595429
32.222 | 1553991
32.2244 | 1666977
32.2264 | 1603030
32.2266 | 1624590
32.2281 | 1649768
32.2304 | 1623020
32.2383 | 1559143
32.2396 | 1620752
32.2402 | 1506779
32.2429 | 1531000
32.2432 | 1500973
32.2456 | 1570182
32.2468 | 1607366
32.2507 | 1594088
32.2512 | 1636837
32.2512 | 1626520
32.2514 | 1541379
32.2526 | 1609445
32.253 | 1605832
32.2563 | 1518766
32.2578 | 1585964
32.2584 | 1680661
32.2658 | 1551336
32.268 | 1625220
32.2704 | 1596892
32.2723 | 1549573
32.273 | 1626718
32.2768 | 1610187
32.2773 | 1616956
32.278 | 1598641
32.279 | 1586420
32.2837 | 1585246
32.284 | 1564574
32.2841 | 1603640
32.2844 | 1662215
32.286 | 1551551
32.2865 | 1533438
32.2888 | 1641567
32.2897 | 1565913
32.2898 | 1529108
32.2944 | 1630379
32.2947 | 1576311
32.295 | 1616020
32.2975 | 1546845
32.2999 | 1607640
32.3002 | 1619277
32.3002 | 1660558
32.3016 | 1625811
32.3067 | 1654239
32.307 | 1636467
32.3078 | 1598772
32.3083 | 1578950
32.3089 | 1560738
32.3102 | 1570989
32.3116 | 1614017
32.3118 | 1615046
32.3125 | 1556978
32.3131 | 1608165
32.3135 | 1588407
32.314 | 1533916
32.3142 | 1562565
32.3154 | 1598000
32.3162 | 1601240
32.3169 | 1609621
32.3219 | 1620512
32.3231 | 1637609
32.3257 | 1604046
32.3276 | 1553233
32.328 | 1644598
32.3295 | 1620608
32.3392 | 1578544
32.3452 | 1617742
32.3479 | 1511774
32.348 | 1539365
32.3486 | 1589048
32.3502 | 1618302
32.3538 | 1600538
32.3539 | 1595160
32.3541 | 1594196
32.355 | 1581314
32.3607 | 1577173
32.3623 | 1606597
32.3639 | 1603937
32.3656 | 1545814
32.3666 | 1588448
32.3706 | 1581682
32.3711 | 1531279
32.3723 | 1628041
32.3725 | 1593381
32.3732 | 1596856
32.378 | 1634320
32.3783 | 1621232
32.3799 | 1552951
32.3801 | 1619705
32.3842 | 1613464
32.3849 | 1588740
32.3851 | 1631597
32.3854 | 1596002
32.3863 | 1564931
32.3868 | 1614717
32.3872 | 1687702
32.3886 | 1629405
32.3892 | 1610771
32.391 | 1490701
32.3911 | 1577151
32.3917 | 1614057
32.3929 | 1622471
32.3933 | 1589764
32.394 | 1629938
32.3954 | 1668398
32.3957 | 1597500
32.3984 | 1569883
32.3989 | 1677402
32.3993 | 1634198
32.3995 | 1602575
32.3997 | 1566788
32.4011 | 1622227
32.4014 | 1581083
32.404 | 1606441
32.4044 | 1589873
32.4047 | 1632652
32.4091 | 1555622
32.4109 | 1561610
32.4126 | 1594386
32.4138 | 1599353
32.4145 | 1642712
32.4148 | 1609242
32.4153 | 1568199
32.4164 | 1561004
32.4181 | 1546415
32.4187 | 1571512
32.4198 | 1587594
32.4214 | 1576406
32.4215 | 1636736
32.4226 | 1628554
32.4237 | 1570327
32.4245 | 1591821
32.4265 | 1582703
32.4267 | 1608761
32.428 | 1601470
32.4288 | 1639639
32.43 | 1584942
32.4303 | 1581137
32.4304 | 1554348
32.431 | 1579921
32.4319 | 1616823
32.4334 | 1577686
32.4351 | 1588500
32.4356 | 1559970
32.4365 | 1544792
32.438 | 1585644
32.4382 | 1608529
32.4389 | 1581593
32.4405 | 1577071
32.4412 | 1519358
32.4421 | 1582478
32.4423 | 1597652
32.4432 | 1713450
32.4444 | 1590812
32.4457 | 1599843
32.446 | 1588499
32.4472 | 1616041
32.4493 | 1603968
32.4515 | 1604152
32.4516 | 1626320
32.4518 | 1556056
32.4542 | 1579189
32.4572 | 1574694
32.4573 | 1554375
32.4579 | 1575832
32.459 | 1548104
32.461 | 1557559
32.4626 | 1596272
32.463 | 1645844
32.4637 | 1605788
32.4639 | 1582484
32.4647 | 1622618
32.465 | 1636364
32.4656 | 1610741
32.4658 | 1646156
32.466 | 1620044
32.4661 | 1584065
32.4674 | 1604683
32.4706 | 1624938
32.4716 | 1573428
32.472 | 1602977
32.4724 | 1642815
32.4734 | 1547630
32.4737 | 1564067
32.4765 | 1516443
32.4781 | 1571829
32.4812 | 1492148
32.4814 | 1598334
32.4833 | 1532241
32.4835 | 1572507
32.4882 | 1592811
32.4887 | 1584437
32.4895 | 1576009
32.4909 | 1602659
32.4911 | 1617648
32.4913 | 1622673
32.4923 | 1602519
32.4934 | 1618344
32.4952 | 1556586
32.4959 | 1606504
32.496 | 1584950
32.4962 | 1596812
32.4964 | 1580184
32.4968 | 1524951
32.4985 | 1650239
32.4999 | 1580283
32.501 | 1667512
32.5017 | 1593942
32.5062 | 1615987
32.5074 | 1636599
32.5098 | 1617548
32.5108 | 1616424
32.5132 | 1624804
32.5136 | 1595162
32.5154 | 1604424
32.5164 | 1657678
32.5168 | 1570478
32.5187 | 1622938
32.5207 | 1615315
32.5209 | 1568313
32.5211 | 1555269
32.5219 | 1538638
32.5235 | 1617603
32.524 | 1561617
32.5253 | 1595846
32.5253 | 1571507
32.5278 | 1590834
32.5292 | 1630639
32.5312 | 1609474
32.5354 | 1655667
32.5371 | 1602764
32.5378 | 1607947
32.5379 | 1638989
32.5447 | 1571026
32.5464 | 1583501
32.5467 | 1598480
32.5489 | 1619257
32.5499 | 1650225
32.5523 | 1590722
32.5545 | 1588545
32.5573 | 1628101
32.5579 | 1539991
32.5622 | 1605669
32.5635 | 1589456
32.5648 | 1562245
32.5649 | 1662524
32.567 | 1627123
32.5693 | 1584449
32.5713 | 1608916
32.5719 | 1586136
32.5722 | 1620789
32.5776 | 1603649
32.58 | 1584700
32.583 | 1598186
32.583 | 1640481
32.5843 | 1583148
32.5851 | 1630011
32.5853 | 1565842
32.5862 | 1589271
32.5961 | 1581939
32.5972 | 1521029
32.5986 | 1555876
32.6018 | 1534879
32.6048 | 1576334
32.6068 | 1610183
32.6093 | 1562635
32.6094 | 1559681
32.6127 | 1606045
32.6131 | 1598453
32.6144 | 1586974
32.6145 | 1574701
32.6166 | 1572304
32.6174 | 1581844
32.6207 | 1632574
32.6212 | 1554133
32.6214 | 1637803
32.6217 | 1610846
32.6221 | 1541462
32.6228 | 1644371
32.6242 | 1578346
32.6281 | 1609055
32.6284 | 1515217
32.6323 | 1600686
32.6326 | 1592547
32.6335 | 1563693
32.6348 | 1602931
32.6375 | 1650349
32.64 | 1598696
32.6436 | 1634002
32.6522 | 1557451
32.6524 | 1601771
32.6542 | 1645040
32.656 | 1600916
32.6561 | 1597958
32.6567 | 1652628
32.6579 | 1570830
32.6587 | 1600778
32.6592 | 1603955
32.6598 | 1645532
32.6603 | 1638299
32.6613 | 1632313
32.6617 | 1579653
32.6633 | 1537069
32.6652 | 1606553
32.6682 | 1523579
32.669 | 1603753
32.67 | 1551588
32.6721 | 1557852
32.6724 | 1591646
32.6729 | 1645565
32.6729 | 1575478
32.6731 | 1576988
32.6736 | 1589070
32.6747 | 1599225
32.6749 | 1550198
32.6763 | 1606137
32.678 | 1577955
32.6795 | 1581776
32.6797 | 1592239
32.68 | 1615967
32.6812 | 1600598
32.6816 | 1647859
32.6825 | 1517832
32.6842 | 1599958
32.6864 | 1651331
32.6889 | 1580807
32.689 | 1616120
32.6945 | 1592024
32.6954 | 1648647
32.6965 | 1591059
32.6995 | 1607038
32.7006 | 1608672
32.7008 | 1644091
32.7009 | 1629082
32.7024 | 1603795
32.7025 | 1620391
32.7034 | 1623868
32.7038 | 1643236
32.7057 | 1616079
32.7062 | 1571548
32.7076 | 1601743
32.7079 | 1609446
32.7095 | 1633482
32.7149 | 1532403
32.7158 | 1567497
32.7194 | 1639951
32.7197 | 1593559
32.7226 | 1575998
32.7226 | 1545323
32.7248 | 1618022
32.7254 | 1617030
32.7255 | 1603660
32.7298 | 1554780
32.7311 | 1640861
32.7317 | 1606674
32.7341 | 1570170
32.7352 | 1701372
32.7358 | 1597383
32.7364 | 1547629
32.7429 | 1518938
32.7433 | 1604006
32.7448 | 1631122
32.7473 | 1598463
32.7524 | 1627761
32.7533 | 1604970
32.7534 | 1634329
32.7555 | 1591152
32.7562 | 1638324
32.7577 | 1611646
32.7582 | 1588998
32.7583 | 1619495
32.759 | 1603566
32.7609 | 1653144
32.7609 | 1633166
32.7624 | 1598485
32.7638 | 1596627
32.7668 | 1565783
32.7674 | 1616195
32.7688 | 1577169
32.7689 | 1619810
32.7696 | 1620977
32.7698 | 1654809
32.7737 | 1567614
32.7796 | 1619865
32.7821 | 1569939
32.7827 | 1557951
32.7874 | 1632957
32.7876 | 1567181
32.7916 | 1559646
32.794 | 1572895
32.7943 | 1547878
32.7944 | 1597304
32.7948 | 1560569
32.7952 | 1610363
32.7977 | 1580130
32.798 | 1547120
32.798 | 1620490
32.7988 | 1644225
32.8003 | 1656782
32.8037 | 1584084
32.8058 | 1697788
32.8063 | 1601247
32.8082 | 1624257
32.81 | 1606051
32.8111 | 1668014
32.8153 | 1589436
32.8166 | 1573619
32.819 | 1586703
32.8226 | 1636684
32.8231 | 1646368
32.824 | 1564324
32.8243 | 1577334
32.825 | 1600319
32.8308 | 1594838
32.8308 | 1587180
32.8316 | 1662047
32.8345 | 1576052
32.8357 | 1617106
32.8362 | 1572533
32.8375 | 1652240
32.8378 | 1570753
32.8391 | 1557885
32.8392 | 1559725
32.8427 | 1677506
32.8437 | 1620658
32.8465 | 1647355
32.8486 | 1613258
32.8492 | 1570502
32.8492 | 1559257
32.8494 | 1562701
32.8494 | 1569344
32.8496 | 1571408
32.8507 | 1603351
32.8525 | 1631644
32.8543 | 1650594
32.8549 | 1593427
32.8583 | 1567967
32.8612 | 1548382
32.8639 | 1634654
32.8639 | 1643128
32.8658 | 1551701
32.8659 | 1574133
32.8659 | 1561065
32.8665 | 1623667
32.8693 | 1637777
32.873 | 1601427
32.8781 | 1586647
32.8787 | 1577710
32.8809 | 1589560
32.8813 | 1557945
32.8822 | 1611914
32.8824 | 1566465
32.8836 | 1639869
32.8843 | 1595678
32.8891 | 1589049
32.8903 | 1613762
32.8926 | 1568192
32.893 | 1624834
32.894 | 1571939
32.8948 | 1590446
32.8978 | 1598447
32.8986 | 1571817
32.9007 | 1585990
32.9009 | 1591520
32.9019 | 1671065
32.903 | 1600355
32.9056 | 1594562
32.9087 | 1622317
32.91 | 1552508
32.9111 | 1586761
32.9127 | 1618566
32.9132 | 1669809
32.9168 | 1640356
32.9177 | 1626108
32.9181 | 1532477
32.9214 | 1647599
32.9217 | 1610696
32.9219 | 1653702
32.9231 | 1586108
32.9234 | 1645200
32.924 | 1628671
32.9244 | 1654972
32.9264 | 1625584
32.9272 | 1605081
32.9277 | 1583900
32.9284 | 1615839
32.9314 | 1563977
32.9329 | 1513298
32.9329 | 1605627
32.9343 | 1572141
32.9356 | 1567991
32.9357 | 1632082
32.9383 | 1632267
32.9394 | 1566686
32.9407 | 1606913
32.9438 | 1646016
32.9458 | 1543970
32.947 | 1602277
32.9475 | 1606082
32.9483 | 1549304
32.9483 | 1571368
32.9503 | 1558907
32.9516 | 1568584
32.952 | 1615308
32.9537 | 1605891
32.9546 | 1559848
32.9547 | 1595986
32.9551 | 1614720
32.9601 | 1632283
32.9605 | 1577093
32.9611 | 1621346
32.9629 | 1649080
32.9637 | 1632011
32.9641 | 1574837
32.9642 | 1519379
32.9658 | 1543768
32.966 | 1649301
32.966 | 1579568
32.9683 | 1546281
32.9744 | 1567409
32.9755 | 1586146
32.9755 | 1614040
32.9762 | 1561545
32.9768 | 1571990
32.9793 | 1576492
32.9808 | 1591979
32.9829 | 1576931
32.9831 | 1631756
32.9833 | 1574716
32.9834 | 1549417
32.9858 | 1495939
32.9881 | 1553122
32.9887 | 1622070
32.9889 | 1607158
32.9899 | 1556927
32.9932 | 1587593
32.9932 | 1563129
32.9938 | 1522649
32.9949 | 1512680
32.9952 | 1595284
32.9994 | 1597271
32.9999 | 1631051
33.0019 | 1597488
33.0022 | 1592028
33.0056 | 1666326
33.0072 | 1629570
33.0075 | 1523960
33.0085 | 1598755
33.0086 | 1650655
33.0087 | 1624379
33.0129 | 1636529
33.0142 | 1672969
33.016 | 1562752
33.0189 | 1568381
33.0194 | 1618215
33.0198 | 1576860
33.0205 | 1561554
33.0207 | 1640096
33.0239 | 1625683
33.0269 | 1577108
33.0274 | 1645725
33.0317 | 1594360
33.0357 | 1561751
33.0388 | 1637586
33.0403 | 1574100
33.0425 | 1587393
33.0442 | 1611941
33.0465 | 1579512
33.0472 | 1659191
33.0486 | 1638683
33.0487 | 1559686
33.0499 | 1616600
33.0504 | 1638599
33.0512 | 1599942
33.0515 | 1601203
33.0515 | 1615278
33.0519 | 1601864
33.0523 | 1576594
33.0545 | 1671046
33.0562 | 1618573
33.0568 | 1587026
33.0568 | 1580986
33.0575 | 1619775
33.0585 | 1599081
33.061 | 1654616
33.0616 | 1584536
33.0637 | 1558819
33.0638 | 1595759
33.0645 | 1576363
33.0669 | 1521052
33.0673 | 1557334
33.0701 | 1579099
33.0704 | 1588582
33.0707 | 1544240
33.0707 | 1591651
33.073 | 1579612
33.0731 | 1604439
33.0756 | 1540312
33.0758 | 1573555
33.0777 | 1594464
33.0818 | 1610623
33.0832 | 1640622
33.0835 | 1615712
33.0869 | 1597222
33.0879 | 1664675
33.0908 | 1619158
33.0927 | 1651594
33.0983 | 1599832
33.0991 | 1590891
33.105 | 1583741
33.1065 | 1607332
33.107 | 1626738
33.1093 | 1540569
33.1097 | 1558844
33.1104 | 1578210
33.1107 | 1607621
33.1116 | 1634279
33.1134 | 1612464
33.1135 | 1654004
33.1137 | 1635222
33.114 | 1638830
33.1177 | 1594692
33.133 | 1632520
33.1331 | 1594417
33.1351 | 1569003
33.1396 | 1540466
33.1421 | 1583326
33.1445 | 1619114
33.1448 | 1643242
33.1454 | 1605707
33.146 | 1597416
33.1479 | 1610285
33.15 | 1597922
33.1514 | 1608522
33.1523 | 1655522
33.153 | 1534844
33.1583 | 1564193
33.1594 | 1575485
33.1595 | 1595066
33.1635 | 1551208
33.1704 | 1578109
33.1753 | 1629265
33.1757 | 1608541
33.1763 | 1618044
33.1778 | 1567715
33.1805 | 1595367
33.1829 | 1566380
33.1831 | 1623139
33.184 | 1630081
33.1861 | 1629644
33.1863 | 1575753
33.187 | 1592325
33.1884 | 1569948
33.189 | 1548679
33.1901 | 1608906
33.1901 | 1582225
33.192 | 1548957
33.1928 | 1637858
33.1967 | 1568696
33.1972 | 1558083
33.1976 | 1580094
33.1984 | 1573808
33.1985 | 1626682
33.2001 | 1538559
33.2009 | 1569268
33.202 | 1689556
33.2029 | 1569566
33.2033 | 1575506
33.2037 | 1568140
33.2037 | 1525224
33.2048 | 1654885
33.2069 | 1527328
33.2083 | 1565491
33.2094 | 1629188
33.2116 | 1602083
33.212 | 1601721
33.2125 | 1616953
33.2171 | 1587239
33.2175 | 1579822
33.2211 | 1655948
33.223 | 1657033
33.225 | 1615407
33.227 | 1585080
33.2274 | 1563506
33.2284 | 1618170
33.2304 | 1617304
33.2306 | 1559033
33.2316 | 1606219
33.2329 | 1587269
33.2339 | 1641938
33.236 | 1598165
33.2387 | 1576813
33.239 | 1612147
33.2394 | 1623292
33.2421 | 1674236
33.2435 | 1596105
33.2445 | 1624291
33.2448 | 1566586
33.2475 | 1586035
33.2476 | 1560586
33.2492 | 1585582
33.2499 | 1566132
33.2517 | 1590051
33.2539 | 1606914
33.2555 | 1611607
33.2575 | 1558657
33.259 | 1627196
33.2595 | 1605854
33.2618 | 1619956
33.2633 | 1587914
33.2634 | 1597544
33.2653 | 1551346
33.266 | 1649432
33.2669 | 1590834
33.2684 | 1564957
33.2689 | 1605083
33.2692 | 1588811
33.2722 | 1646426
33.2731 | 1635315
33.2757 | 1641082
33.2769 | 1587771
33.2785 | 1596734
33.2793 | 1659138
33.2793 | 1635834
33.2809 | 1623104
33.2816 | 1631901
33.2824 | 1614735
33.2825 | 1591044
33.2878 | 1595890
33.2884 | 1561930
33.2884 | 1691903
33.2905 | 1550895
33.2951 | 1603521
33.296 | 1546822
33.2964 | 1521181
33.2971 | 1603013
33.2989 | 1606897
33.3007 | 1543618
33.3019 | 1603065
33.3022 | 1564949
33.3025 | 1546513
33.3026 | 1611151
33.304 | 1605360
33.3049 | 1642967
33.305 | 1632573
33.3051 | 1583782
33.3098 | 1623601
33.31 | 1582653
33.3116 | 1622905
33.3141 | 1531310
33.315 | 1605501
33.3167 | 1643082
33.3169 | 1632911
33.3174 | 1627934
33.3208 | 1612792
33.3244 | 1554687
33.3257 | 1545366
33.3277 | 1576615
33.3278 | 1621365
33.3278 | 1683601
33.3288 | 1549017
33.329 | 1548915
33.33 | 1612967
33.3316 | 1620193
33.3359 | 1673140
33.3374 | 1569727
33.3379 | 1563700
33.338 | 1638446
33.3397 | 1635285
33.34 | 1618121
33.3412 | 1578818
33.3478 | 1641325
33.3478 | 1581520
33.348 | 1547691
33.3491 | 1623592
33.3514 | 1541037
33.3516 | 1585801
33.3517 | 1628315
33.352 | 1582505
33.3524 | 1540398
33.353 | 1584461
33.353 | 1583779
33.3535 | 1588615
33.3553 | 1573516
33.3572 | 1591870
33.3578 | 1586818
33.3609 | 1534074
33.3624 | 1586580
33.3649 | 1599900
33.3662 | 1605123
33.3675 | 1574182
33.368 | 1583025
33.3688 | 1605551
33.3706 | 1590293
33.372 | 1593618
33.3722 | 1592707
33.3767 | 1572634
33.3769 | 1617590
33.377 | 1557339
33.3784 | 1571923
33.3796 | 1566516
33.3798 | 1569409
33.3823 | 1576599
33.3838 | 1697184
33.3839 | 1637897
33.386 | 1649328
33.3862 | 1594670
33.3898 | 1599689
33.3913 | 1647587
33.3953 | 1576403
33.3963 | 1591181
33.3987 | 1646256
33.4002 | 1566399
33.403 | 1553109
33.4055 | 1607701
33.4059 | 1567778
33.4076 | 1582635
33.409 | 1639021
33.4096 | 1615270
33.4097 | 1640484
33.4103 | 1639709
33.4117 | 1567740
33.413 | 1584741
33.4132 | 1585420
33.4144 | 1661523
33.4151 | 1566802
33.4165 | 1550663
33.4182 | 1583525
33.4183 | 1588684
33.4209 | 1592346
33.4238 | 1596269
33.4254 | 1570089
33.4257 | 1560070
33.4278 | 1627589
33.4301 | 1589248
33.4331 | 1594394
33.4342 | 1602773
33.4364 | 1687044
33.4401 | 1591023
33.443 | 1634764
33.4433 | 1605986
33.4456 | 1586319
33.4471 | 1588811
33.4481 | 1598871
33.4515 | 1563188
33.4524 | 1566082
33.4543 | 1605566
33.4553 | 1596824
33.4592 | 1597382
33.46 | 1547251
33.4631 | 1601757
33.4631 | 1609227
33.4769 | 1594313
33.4787 | 1565135
33.4799 | 1513172
33.48 | 1573146
33.4811 | 1586952
33.4831 | 1582127
33.4847 | 1653302
33.4849 | 1595355
33.485 | 1623009
33.4856 | 1651416
33.4862 | 1619007
33.487 | 1614315
33.4878 | 1614193
33.4889 | 1554431
33.4889 | 1594573
33.4899 | 1582653
33.4907 | 1541362
33.4921 | 1645317
33.5 | 1584206
33.501 | 1599768
33.5012 | 1537746
33.502 | 1563459
33.5044 | 1565658
33.5087 | 1580093
33.5094 | 1592963
33.5105 | 1662416
33.5106 | 1589647
33.5125 | 1603286
33.5197 | 1596193
33.5214 | 1614206
33.5215 | 1610181
33.5239 | 1555412
33.5269 | 1614956
33.5311 | 1655917
33.534 | 1616394
33.535 | 1532259
33.5358 | 1571993
33.5365 | 1605237
33.537 | 1602903
33.5405 | 1588369
33.5411 | 1608538
33.5411 | 1542056
33.5446 | 1580232
33.5493 | 1624611
33.5506 | 1577060
33.5508 | 1646450
33.5525 | 1554083
33.5538 | 1599768
33.5539 | 1619783
33.5555 | 1625447
33.5559 | 1633355
33.5572 | 1555140
33.5603 | 1609610
33.5624 | 1571425
33.563 | 1515874
33.5647 | 1549896
33.5683 | 1582476
33.5699 | 1556232
33.57 | 1586232
33.5712 | 1627792
33.5749 | 1646387
33.5756 | 1570982
33.5779 | 1575954
33.5799 | 1626940
33.5811 | 1559514
33.5825 | 1539852
33.5828 | 1642938
33.5831 | 1510306
33.5852 | 1670031
33.5866 | 1636008
33.5871 | 1620415
33.5881 | 1594865
33.5891 | 1555367
33.5892 | 1527684
33.5895 | 1512550
33.5896 | 1571551
33.5903 | 1622918
33.5913 | 1585966
33.5921 | 1601722
33.5938 | 1676190
33.5942 | 1635615
33.5953 | 1572370
33.5979 | 1540293
33.5982 | 1607384
33.6014 | 1528220
33.6017 | 1547383
33.6021 | 1605807
33.6021 | 1657357
33.6034 | 1566933
33.6036 | 1670815
33.6056 | 1603343
33.6066 | 1650550
33.6068 | 1567112
33.6089 | 1608805
33.609 | 1561000
33.611 | 1650428
33.6121 | 1617360
33.6125 | 1560557
33.6155 | 1680523
33.6173 | 1562188
33.6185 | 1547063
33.6187 | 1542949
33.6207 | 1595000
33.6216 | 1642209
33.6227 | 1561707
33.6239 | 1591084
33.624 | 1567228
33.6254 | 1639393
33.628 | 1569920
33.6304 | 1655657
33.6321 | 1636615
33.6342 | 1532155
33.6355 | 1548839
33.6356 | 1620572
33.6452 | 1590331
33.6461 | 1606988
33.6482 | 1658747
33.6488 | 1613075
33.6492 | 1537148
33.6505 | 1573517
33.6515 | 1593426
33.6532 | 1579276
33.6535 | 1544451
33.6553 | 1550692
33.6554 | 1616597
33.6575 | 1583667
33.6589 | 1555419
33.6609 | 1582971
33.661 | 1546194
33.6618 | 1562562
33.6641 | 1612654
33.6672 | 1517330
33.6701 | 1579847
33.671 | 1603999
33.6733 | 1557478
33.6755 | 1587986
33.6783 | 1622576
33.6792 | 1527541
33.6808 | 1583288
33.681 | 1649298
33.6816 | 1545002
33.6831 | 1590769
33.6864 | 1559429
33.6865 | 1542202
33.6878 | 1688054
33.6881 | 1575617
33.6896 | 1633225
33.6896 | 1601019
33.695 | 1558601
33.6974 | 1594184
33.6988 | 1578113
33.6995 | 1621248
33.7029 | 1636499
33.7034 | 1576321
33.7059 | 1595864
33.7063 | 1585311
33.7068 | 1592429
33.7068 | 1614903
33.707 | 1583343
33.7099 | 1548293
33.7113 | 1616427
33.7118 | 1650069
33.7143 | 1595814
33.7154 | 1541897
33.7165 | 1625211
33.7197 | 1625681
33.7201 | 1572735
33.7206 | 1582809
33.7209 | 1614652
33.721 | 1595094
33.7213 | 1586238
33.7221 | 1576601
33.7223 | 1641915
33.7235 | 1555078
33.7287 | 1606037
33.7288 | 1596523
33.7294 | 1589867
33.7295 | 1627635
33.7306 | 1559279
33.7312 | 1591702
33.7314 | 1597280
33.7317 | 1614188
33.7362 | 1623638
33.7371 | 1510192
33.7381 | 1556495
33.7388 | 1595394
33.7407 | 1587932
33.7437 | 1601011
33.7456 | 1640954
33.7461 | 1603068
33.7472 | 1590546
33.7495 | 1644835
33.75 | 1547175
33.753 | 1592289
33.759 | 1646257
33.7595 | 1538583
33.7603 | 1562924
33.7623 | 1565424
33.7624 | 1641288
33.7625 | 1627059
33.763 | 1596098
33.7636 | 1554662
33.7638 | 1554531
33.7644 | 1610616
33.7695 | 1646208
33.7696 | 1584396
33.7702 | 1576018
33.7706 | 1629660
33.7743 | 1577281
33.7747 | 1608232
33.7757 | 1672507
33.776 | 1623211
33.7775 | 1641755
33.7783 | 1609553
33.7788 | 1563388
33.7813 | 1632644
33.7814 | 1578688
33.782 | 1550604
33.7856 | 1636020
33.7879 | 1635071
33.7887 | 1537386
33.789 | 1576548
33.7911 | 1519797
33.7913 | 1600436
33.7914 | 1535446
33.7919 | 1603726
33.794 | 1615253
33.7999 | 1569740
33.8004 | 1646417
33.8013 | 1637117
33.8023 | 1670837
33.8046 | 1611807
33.8049 | 1579202
33.8052 | 1546890
33.8058 | 1617262
33.8064 | 1677942
33.8065 | 1592558
33.8108 | 1588333
33.8125 | 1603742
33.8149 | 1599082
33.816 | 1622507
33.8163 | 1587691
33.8165 | 1655898
33.8178 | 1622490
33.8204 | 1546961
33.8224 | 1634791
33.8282 | 1544654
33.8284 | 1646976
33.8313 | 1610107
33.8355 | 1548753
33.8361 | 1605804
33.8383 | 1598844
33.8391 | 1531125
33.8409 | 1656013
33.8419 | 1558920
33.8435 | 1525185
33.8446 | 1608403
33.8458 | 1585710
33.8471 | 1691046
33.8481 | 1593113
33.8518 | 1545142
33.8535 | 1607824
33.86 | 1635972
33.861 | 1580825
33.8614 | 1599557
33.8643 | 1634112
33.8676 | 1552119
33.8682 | 1647337
33.872 | 1614832
33.8733 | 1631742
33.8744 | 1559181
33.8762 | 1575383
33.8762 | 1570540
33.8773 | 1658989
33.88 | 1609155
33.8801 | 1594522
33.8802 | 1589170
33.8822 | 1686126
33.8836 | 1589313
33.8864 | 1612537
33.8905 | 1596035
33.8956 | 1591408
33.8957 | 1638196
33.8998 | 1571441
33.9 | 1550204
33.9027 | 1568102
33.9035 | 1606518
33.9037 | 1578654
33.9044 | 1618386
33.9055 | 1561362
33.9055 | 1532050
33.9056 | 1562086
33.9073 | 1579926
33.908 | 1597164
33.9159 | 1583745
33.9166 | 1583631
33.9179 | 1644152
33.9198 | 1603759
33.9234 | 1640726
33.9245 | 1625206
33.9267 | 1613375
33.927 | 1668624
33.9271 | 1631123
33.9284 | 1568386
33.9362 | 1590735
33.9369 | 1598140
33.938 | 1599477
33.9416 | 1511648
33.9418 | 1636877
33.943 | 1590573
33.9472 | 1539436
33.9482 | 1597079
33.9486 | 1558900
33.9514 | 1572825
33.9536 | 1598956
33.9547 | 1574775
33.9564 | 1598848
33.957 | 1549248
33.9578 | 1662003
33.958 | 1573110
33.9582 | 1598167
33.9587 | 1618351
33.9591 | 1565285
33.9617 | 1583122
33.9618 | 1590234
33.9645 | 1599809
33.9665 | 1623513
33.9682 | 1574173
33.9719 | 1540289
33.9739 | 1497102
33.9751 | 1601793
33.9752 | 1533368
33.9802 | 1554852
33.9809 | 1584161
33.9843 | 1590578
33.9876 | 1653903
33.9889 | 1601480
33.9914 | 1632064
33.9926 | 1611306
33.9992 | 1558265
33.9994 | 1567071
34.0032 | 1602160
34.0033 | 1602362
34.005 | 1545410
34.0102 | 1636149
34.013 | 1571177
34.013 | 1620312
34.0149 | 1650547
34.0155 | 1551093
34.0177 | 1570601
34.022 | 1572073
34.0265 | 1572135
34.0266 | 1515343
34.0268 | 1635295
34.0274 | 1577339
34.0288 | 1650727
34.0304 | 1633607
34.0305 | 1629796
34.0324 | 1627091
34.0346 | 1595464
34.0417 | 1664569
34.0422 | 1541866
34.0424 | 1587469
34.0433 | 1639583
34.0475 | 1563064
34.0481 | 1588887
34.0488 | 1635918
34.0567 | 1592617
34.0596 | 1600950
34.0616 | 1586576
34.0633 | 1591876
34.0702 | 1578678
34.0703 | 1552886
34.0709 | 1584079
34.0711 | 1569756
34.0713 | 1576702
34.072 | 1635745
34.0734 | 1539323
34.074 | 1643677
34.0755 | 1623610
34.0776 | 1547301
34.0857 | 1594896
34.0945 | 1640837
34.0958 | 1608529
34.0961 | 1553209
34.0964 | 1581109
34.0965 | 1615176
34.099 | 1582657
34.1073 | 1591422
34.1073 | 1644283
34.1117 | 1634206
34.115 | 1569417
34.1158 | 1535229
34.1173 | 1528922
34.1189 | 1563812
34.1189 | 1599621
34.1206 | 1635965
34.121 | 1673477
34.1239 | 1615814
34.1242 | 1602264
34.1242 | 1646009
34.1285 | 1624839
34.1303 | 1593215
34.1363 | 1611589
34.1386 | 1602624
34.1386 | 1594274
34.1391 | 1683145
34.1401 | 1666543
34.1454 | 1628260
34.1459 | 1624507
34.1461 | 1595470
34.1509 | 1616646
34.1514 | 1577364
34.1516 | 1586436
34.1518 | 1519335
34.1525 | 1561454
34.1658 | 1565904
34.1688 | 1574411
34.1693 | 1611703
34.1714 | 1621098
34.1722 | 1654953
34.1738 | 1689608
34.1742 | 1548640
34.1778 | 1679093
34.1799 | 1552722
34.181 | 1593546
34.1855 | 1574698
34.1858 | 1559478
34.1913 | 1573227
34.1947 | 1643811
34.1965 | 1639056
34.198 | 1639264
34.1985 | 1610583
34.2001 | 1623479
34.2004 | 1534106
34.2007 | 1625870
34.2017 | 1618771
34.2035 | 1623405
34.2063 | 1621517
34.2073 | 1640846
34.2081 | 1634709
34.2086 | 1577545
34.2086 | 1580218
34.213 | 1563724
34.2138 | 1603282
34.2139 | 1556595
34.2152 | 1582400
34.2163 | 1627307
34.2182 | 1568406
34.2191 | 1629429
34.2201 | 1643807
34.2203 | 1580349
34.2218 | 1569840
34.2228 | 1585011
34.2256 | 1632228
34.2294 | 1667651
34.2301 | 1597087
34.2338 | 1569101
34.2373 | 1571961
34.2375 | 1667185
34.2379 | 1628541
34.2385 | 1625712
34.2396 | 1576220
34.2403 | 1541800
34.2418 | 1565470
34.2418 | 1642255
34.2426 | 1568952
34.2466 | 1647832
34.2491 | 1576262
34.2491 | 1627945
34.2536 | 1643178
34.2539 | 1599806
34.2565 | 1587694
34.2586 | 1547648
34.2614 | 1568601
34.2614 | 1563708
34.2636 | 1657179
34.2644 | 1658205
34.2649 | 1550884
34.2652 | 1567601
34.2687 | 1640761
34.2692 | 1576078
34.2722 | 1632530
34.2724 | 1659117
34.2736 | 1537009
34.2737 | 1556000
34.2749 | 1603259
34.2765 | 1599721
34.2766 | 1544658
34.2792 | 1608448
34.2795 | 1606470
34.2878 | 1644253
34.2881 | 1537931
34.2881 | 1569833
34.2882 | 1580284
34.2891 | 1581505
34.2899 | 1581195
34.2906 | 1585889
34.2907 | 1629142
34.2919 | 1575692
34.2923 | 1530911
34.2931 | 1619569
34.2934 | 1567419
34.2945 | 1575541
34.2959 | 1642430
34.298 | 1545316
34.3004 | 1637770
34.3024 | 1575344
34.3055 | 1571215
34.3058 | 1558671
34.3067 | 1662423
34.3074 | 1600650
34.3077 | 1602143
34.3103 | 1654309
34.3105 | 1578382
34.3106 | 1573581
34.3114 | 1688378
34.3122 | 1639014
34.3128 | 1556417
34.3174 | 1629357
34.3174 | 1618115
34.3194 | 1610694
34.321 | 1551973
34.3251 | 1557247
34.3271 | 1533049
34.3277 | 1565537
34.3287 | 1602787
34.3297 | 1546055
34.3325 | 1560944
34.3335 | 1595584
34.3346 | 1623310
34.335 | 1577256
34.3353 | 1633776
34.3357 | 1590379
34.3359 | 1657965
34.3422 | 1625880
34.3432 | 1616655
34.3438 | 1519170
34.3457 | 1599784
34.3488 | 1603268
34.3526 | 1593342
34.354 | 1538888
34.3549 | 1592784
34.3551 | 1637450
34.3588 | 1623845
34.3589 | 1641356
34.3593 | 1586126
34.3598 | 1578279
34.3605 | 1572536
34.3614 | 1582718
34.364 | 1651359
34.367 | 1560898
34.3687 | 1632737
34.3696 | 1603230
34.3715 | 1577687
34.372 | 1634077
34.3724 | 1636324
34.3737 | 1592333
34.3743 | 1603800
34.3786 | 1624698
34.3856 | 1632049
34.3867 | 1556126
34.3901 | 1586160
34.3911 | 1626101
34.3916 | 1561818
34.3993 | 1570422
34.4017 | 1549247
34.4061 | 1592257
34.4067 | 1597638
34.4077 | 1630764
34.4079 | 1630665
34.4081 | 1597542
34.4106 | 1604481
34.4137 | 1569653
34.4169 | 1628485
34.4205 | 1613515
34.4254 | 1581727
34.4258 | 1557165
34.4266 | 1606825
34.4268 | 1609996
34.4281 | 1596585
34.433 | 1541891
34.4332 | 1608011
34.4336 | 1601839
34.4367 | 1576071
34.4376 | 1574450
34.44 | 1633911
34.4407 | 1540201
34.4474 | 1613292
34.4477 | 1609745
34.448 | 1682705
34.4545 | 1552156
34.4565 | 1583127
34.4565 | 1614537
34.4598 | 1635161
34.4599 | 1599432
34.4647 | 1601685
34.4682 | 1577315
34.4698 | 1592671
34.4713 | 1599448
34.4734 | 1574705
34.4748 | 1596409
34.4788 | 1596453
34.4792 | 1653658
34.482 | 1610887
34.4832 | 1610728
34.484 | 1664024
34.4893 | 1638683
34.4897 | 1578084
34.4907 | 1643026
34.4928 | 1681572
34.4985 | 1543898
34.5021 | 1615976
34.5025 | 1587519
34.5039 | 1502618
34.5057 | 1558298
34.5058 | 1546002
34.5113 | 1591046
34.5145 | 1564393
34.5164 | 1582142
34.5267 | 1641989
34.5269 | 1560165
34.5272 | 1589034
34.5274 | 1566325
34.5282 | 1540515
34.5317 | 1515102
34.5324 | 1530761
34.5326 | 1566402
34.5327 | 1569139
34.5337 | 1591395
34.5339 | 1611188
34.5343 | 1613302
34.5362 | 1626285
34.5367 | 1608486
34.5382 | 1643234
34.5404 | 1577634
34.5414 | 1597676
34.5441 | 1596377
34.545 | 1595839
34.5461 | 1603334
34.5549 | 1576430
34.5589 | 1517793
34.5629 | 1543476
34.5719 | 1624740
34.5735 | 1624873
34.5764 | 1589597
34.5834 | 1633373
34.5835 | 1615619
34.5876 | 1632641
34.588 | 1581825
34.5886 | 1696108
34.5898 | 1624620
34.5915 | 1494801
34.5926 | 1614840
34.593 | 1608669
34.5962 | 1564953
34.5984 | 1667360
34.5985 | 1547370
34.601 | 1593161
34.6024 | 1588284
34.6035 | 1530375
34.6048 | 1558881
34.6057 | 1578304
34.6067 | 1550505
34.6089 | 1559684
34.6107 | 1628357
34.6135 | 1612775
34.6141 | 1635972
34.6156 | 1557192
34.6176 | 1661387
34.6179 | 1645072
34.6184 | 1622234
34.6187 | 1589802
34.6205 | 1609885
34.6223 | 1560622
34.6255 | 1514394
34.6258 | 1633417
34.6268 | 1631580
34.63 | 1614872
34.63 | 1593951
34.6305 | 1624994
34.6343 | 1587041
34.636 | 1581090
34.6361 | 1575682
34.6437 | 1612395
34.6442 | 1618664
34.6471 | 1600920
34.6472 | 1584996
34.6506 | 1561709
34.651 | 1553439
34.6535 | 1592573
34.654 | 1642787
34.6558 | 1584060
34.6565 | 1546775
34.6589 | 1579069
34.659 | 1652671
34.6597 | 1593782
34.6636 | 1580645
34.6688 | 1597952
34.6705 | 1701377
34.6741 | 1576434
34.6743 | 1616332
34.6766 | 1635726
34.6783 | 1586926
34.6795 | 1649211
34.682 | 1614171
34.6822 | 1588435
34.6827 | 1618826
34.6859 | 1576265
34.687 | 1612207
34.689 | 1594622
34.6901 | 1596472
34.6908 | 1599894
34.6974 | 1641067
34.6979 | 1687758
34.7013 | 1590154
34.7025 | 1585713
34.7043 | 1603533
34.7069 | 1672828
34.7102 | 1587191
34.7131 | 1595794
34.7147 | 1663417
34.7206 | 1565286
34.7214 | 1591616
34.7219 | 1622139
34.7221 | 1528508
34.7231 | 1550238
34.7316 | 1595543
34.7355 | 1623378
34.737 | 1611160
34.7432 | 1662782
34.7448 | 1622117
34.747 | 1647239
34.7502 | 1581172
34.7561 | 1534118
34.7585 | 1629944
34.7591 | 1602984
34.7595 | 1562107
34.7598 | 1548602
34.7604 | 1653205
34.7626 | 1626938
34.7648 | 1616677
34.765 | 1570894
34.7656 | 1603749
34.7689 | 1606370
34.7712 | 1670139
34.7731 | 1600198
34.7735 | 1592404
34.7776 | 1661016
34.779 | 1601898
34.7798 | 1651189
34.782 | 1585235
34.7847 | 1622074
34.7867 | 1568021
34.7878 | 1551906
34.7908 | 1548525
34.8032 | 1651092
34.8093 | 1578961
34.811 | 1620029
34.8162 | 1699347
34.818 | 1579725
34.8237 | 1663046
34.8247 | 1584378
34.8247 | 1673115
34.8263 | 1627386
34.8276 | 1591053
34.8313 | 1637191
34.8324 | 1582039
34.8331 | 1638006
34.8369 | 1592898
34.8371 | 1635196
34.841 | 1574916
34.8426 | 1552391
34.8432 | 1618877
34.8447 | 1608526
34.846 | 1622308
34.8485 | 1624719
34.8518 | 1663043
34.8539 | 1590808
34.8554 | 1586652
34.8557 | 1572198
34.859 | 1659281
34.8632 | 1584013
34.8642 | 1646031
34.8653 | 1598720
34.8658 | 1649810
34.8664 | 1625563
34.8723 | 1548112
34.8746 | 1576104
34.8765 | 1626460
34.8778 | 1603048
34.8809 | 1519392
34.8844 | 1570127
34.8865 | 1601431
34.8907 | 1632545
34.8908 | 1557412
34.892 | 1619848
34.8955 | 1672224
34.8968 | 1579699
34.8988 | 1573132
34.9022 | 1593601
34.9031 | 1610736
34.9062 | 1643863
34.9073 | 1639138
34.9088 | 1649182
34.9139 | 1529758
34.9181 | 1528417
34.9236 | 1661758
34.9246 | 1550705
34.9344 | 1583556
34.937 | 1565808
34.9393 | 1571056
34.94 | 1533843
34.9423 | 1576943
34.9441 | 1698739
34.9453 | 1616264
34.9464 | 1542097
34.9601 | 1629031
34.9678 | 1591437
34.9687 | 1569467
34.9719 | 1571194
34.974 | 1553175
34.9746 | 1640567
34.9762 | 1549399
34.9764 | 1551904
34.9766 | 1566020
34.9772 | 1605195
34.9885 | 1628272
34.9894 | 1588166
34.993 | 1586776
35 | 1621990
35.0013 | 1614313
35.0047 | 1615170
35.0053 | 1626476
35.0069 | 1597294
35.008 | 1624472
35.0082 | 1577669
35.0097 | 1619896
35.0122 | 1637937
35.0125 | 1623893
35.0137 | 1603187
35.0142 | 1613654
35.0192 | 1593629
35.0192 | 1607304
35.0198 | 1607049
35.0223 | 1689447
35.0229 | 1628721
35.0237 | 1620915
35.0255 | 1587758
35.0328 | 1565472
35.0332 | 1649818
35.0342 | 1623638
35.0352 | 1668002
35.0414 | 1696857
35.0418 | 1608720
35.0437 | 1644887
35.0438 | 1618685
35.0454 | 1588698
35.0461 | 1682575
35.0466 | 1608747
35.0483 | 1589789
35.0519 | 1609115
35.0526 | 1616843
35.0528 | 1604603
35.0538 | 1611530
35.0541 | 1644838
35.0545 | 1588165
35.0611 | 1624734
35.0641 | 1611913
35.0643 | 1630298
35.0649 | 1626234
35.0673 | 1632317
35.0741 | 1582402
35.077 | 1590109
35.0774 | 1582728
35.079 | 1655078
35.0819 | 1677470
35.0873 | 1626791
35.0915 | 1557478
35.0951 | 1635351
35.0953 | 1647690
35.0975 | 1656603
35.0997 | 1555074
35.1011 | 1557531
35.108 | 1628963
35.1085 | 1614104
35.121 | 1589773
35.1247 | 1600839
35.127 | 1582730
35.1298 | 1631616
35.1304 | 1581985
35.1309 | 1629892
35.132 | 1695209
35.1346 | 1580688
35.1349 | 1661627
35.1369 | 1677540
35.1382 | 1571958
35.144 | 1625779
35.1454 | 1635258
35.1467 | 1595645
35.1514 | 1572523
35.1526 | 1616111
35.1527 | 1619977
35.1549 | 1589979
35.1602 | 1660287
35.1611 | 1555278
35.1686 | 1538281
35.1716 | 1533620
35.1774 | 1625850
35.1787 | 1600651
35.1805 | 1596983
35.1807 | 1617338
35.1859 | 1619567
35.1927 | 1637228
35.1932 | 1634324
35.1965 | 1607829
35.1978 | 1607582
35.1979 | 1569802
35.2011 | 1666577
35.2055 | 1646743
35.2058 | 1580663
35.2136 | 1627063
35.2166 | 1613078
35.2208 | 1636395
35.2216 | 1573045
35.2295 | 1588342
35.233 | 1634589
35.2355 | 1598254
35.2357 | 1630900
35.2405 | 1650132
35.2493 | 1601954
35.2531 | 1597658
35.2563 | 1611157
35.2593 | 1589584
35.2607 | 1565195
35.2611 | 1620575
35.2655 | 1625948
35.2658 | 1622501
35.2662 | 1628353
35.2664 | 1614408
35.2711 | 1614086
35.2732 | 1718880
35.2739 | 1597418
35.2769 | 1657935
35.2787 | 1589299
35.2818 | 1637948
35.2821 | 1566380
35.2868 | 1654072
35.2925 | 1594887
35.2958 | 1590773
35.2983 | 1580720
35.304 | 1655853
35.3081 | 1617951
35.3094 | 1621228
35.31 | 1596343
35.3106 | 1666374
35.3169 | 1586498
35.3169 | 1614737
35.317 | 1667513
35.3218 | 1706642
35.3274 | 1696067
35.3285 | 1696785
35.3357 | 1642787
35.3398 | 1604176
35.3418 | 1612354
35.343 | 1634145
35.3447 | 1659725
35.3509 | 1669335
35.3525 | 1621852
35.3554 | 1608474
35.3576 | 1665297
35.3616 | 1591732
35.3624 | 1668240
35.3631 | 1614227
35.3645 | 1585470
35.3651 | 1532484
35.3669 | 1632466
35.3675 | 1619538
35.3716 | 1592166
35.3757 | 1665756
35.3796 | 1658073
35.3818 | 1573220
35.3922 | 1578706
35.397 | 1629479
35.3981 | 1648855
35.402 | 1617455
35.4064 | 1699614
35.4083 | 1627362
35.4092 | 1645804
35.4111 | 1600313
35.4123 | 1692309
35.4141 | 1726145
35.4163 | 1601411
35.4227 | 1622791
35.4301 | 1586243
35.4394 | 1597456
35.4407 | 1561160
35.443 | 1626569
35.4455 | 1654980
35.4549 | 1617201
35.4584 | 1668229
35.4608 | 1613911
35.4662 | 1592500
35.4717 | 1596169
35.4732 | 1671786
35.4737 | 1636813
35.4747 | 1619081
35.4807 | 1596141
35.4873 | 1606593
35.4966 | 1686667
35.5008 | 1643922
35.5028 | 1648201
35.5037 | 1557288
35.5083 | 1645251
35.5085 | 1591043
35.5147 | 1618590
35.517 | 1630390
35.521 | 1615956
35.523 | 1673605
35.5238 | 1600492
35.526 | 1693809
35.5331 | 1661409
35.5384 | 1634916
35.5585 | 1584174
35.5615 | 1634489
35.5628 | 1603180
35.5633 | 1604084
35.5702 | 1603386
35.577 | 1577554
35.5782 | 1673816
35.5801 | 1618590
35.583 | 1652835
35.5879 | 1593323
35.5946 | 1600159
35.5962 | 1553312
35.5995 | 1657888
35.5998 | 1633382
35.604 | 1613273
35.6052 | 1646466
35.6144 | 1558866
35.6241 | 1629570
35.6259 | 1647503
35.6264 | 1646533
35.6294 | 1564552
35.6348 | 1662961
35.6382 | 1579021
35.6392 | 1643993
35.6534 | 1666742
35.6548 | 1597788
35.6562 | 1606796
35.6574 | 1617566
35.6585 | 1555782
35.6625 | 1617418
35.6716 | 1627835
35.6728 | 1585494
35.6745 | 1616440
35.6745 | 1644945
35.6759 | 1652007
35.6832 | 1635125
35.6867 | 1632543
35.6878 | 1584613
35.6905 | 1612568
35.6953 | 1676484
35.698 | 1649962
35.6984 | 1664846
35.699 | 1664801
35.7006 | 1567758
35.7011 | 1652169
35.703 | 1616720
35.7042 | 1685733
35.7066 | 1664635
35.708 | 1606904
35.7184 | 1606277
35.7194 | 1625493
35.7205 | 1637364
35.7253 | 1645866
35.7275 | 1629642
35.7321 | 1616212
35.7633 | 1622053
35.764 | 1607653
35.7683 | 1578779
35.7721 | 1557390
35.7722 | 1682586
35.7763 | 1615280
35.7805 | 1621403
35.7876 | 1656930
35.7944 | 1591574
35.7977 | 1683308
35.8003 | 1623473
35.8029 | 1620813
35.8083 | 1580452
35.8159 | 1581002
35.8233 | 1656863
35.8254 | 1587313
35.8325 | 1581362
35.8339 | 1578659
35.8353 | 1594382
35.8411 | 1579486
35.8461 | 1605752
35.8568 | 1639120
35.8722 | 1649283
35.8773 | 1589741
35.8787 | 1608754
35.8789 | 1599069
35.8825 | 1678147
35.8872 | 1617642
35.8973 | 1607467
35.8978 | 1637905
35.8995 | 1635429
35.9008 | 1638726
35.9032 | 1622497
35.9084 | 1592030
35.9094 | 1611762
35.9199 | 1617097
35.9429 | 1554561
35.95 | 1628721
35.9649 | 1598505
35.9706 | 1625257
35.9776 | 1631532
35.9863 | 1591161
35.9948 | 1622857
36.0033 | 1684907
36.0049 | 1661694
36.0122 | 1632248
36.0155 | 1600382
36.0178 | 1681801
36.0209 | 1636119
36.0321 | 1633904
36.0452 | 1671736
36.047 | 1671700
36.0517 | 1631019
36.052 | 1622635
36.0526 | 1659575
36.0536 | 1632217
36.0588 | 1656829
36.0715 | 1661316
36.072 | 1659586
36.0847 | 1664381
36.0875 | 1671929
36.0957 | 1679537
36.1038 | 1652591
36.1127 | 1625794
36.1149 | 1590647
36.116 | 1579704
36.1181 | 1630224
36.1185 | 1703283
36.1203 | 1612654
36.1217 | 1664752
36.1244 | 1642460
36.1253 | 1681956
36.1273 | 1620292
36.1309 | 1607892
36.1337 | 1568421
36.1403 | 1683178
36.1407 | 1584891
36.1502 | 1709013
36.1521 | 1607623
36.1545 | 1631810
36.1571 | 1645649
36.1662 | 1609712
36.1737 | 1597782
36.1747 | 1639750
36.1766 | 1658027
36.1911 | 1686428
36.2091 | 1594066
36.2126 | 1681838
36.2179 | 1638326
36.2221 | 1667421
36.2281 | 1630858
36.2288 | 1620536
36.239 | 1669228
36.2437 | 1707569
36.2438 | 1642181
36.2566 | 1670636
36.2593 | 1675130
36.2623 | 1677811
36.2802 | 1627549
36.2815 | 1624059
36.2902 | 1606191
36.2959 | 1724379
36.2971 | 1657027
36.3072 | 1712671
36.3204 | 1667423
36.3416 | 1615197
36.3429 | 1661948
36.3472 | 1573914
36.3497 | 1703824
36.3526 | 1628003
36.3559 | 1708861
36.37 | 1591507
36.3725 | 1617804
36.3759 | 1561096
36.3783 | 1658452
36.3807 | 1624279
36.3864 | 1626193
36.3875 | 1678649
36.3903 | 1676434
36.3941 | 1681982
36.3965 | 1664518
36.3998 | 1626665
36.4104 | 1723836
36.4121 | 1620863
36.413 | 1589843
36.4247 | 1647327
36.4523 | 1665459
36.4527 | 1684357
36.454 | 1716016
36.4553 | 1657337
36.4604 | 1629853
36.49 | 1662812
36.5041 | 1633550
36.5068 | 1676136
36.5268 | 1701132
36.5324 | 1662407
36.5495 | 1628196
36.5738 | 1628844
36.5846 | 1696691
36.6123 | 1632811
36.6159 | 1657078
36.6385 | 1702329
36.6645 | 1660126
36.6662 | 1630867
36.6703 | 1648727
36.6878 | 1666785
36.6887 | 1703620
36.6931 | 1658328
36.7192 | 1712200
36.7214 | 1652831
36.7348 | 1667508
36.7427 | 1634427
36.7499 | 1580710
36.7506 | 1651274
36.7623 | 1673377
36.7728 | 1683099
36.774 | 1653446
36.79 | 1612368
36.7905 | 1622780
36.7927 | 1618273
36.8096 | 1713801
36.8161 | 1620812
36.8209 | 1630160
36.8295 | 1711525
36.8648 | 1652653
36.8668 | 1610129
36.8722 | 1616161
36.8793 | 1689751
36.893 | 1664105
36.8951 | 1632325
36.8991 | 1692882
36.9005 | 1634292
36.9328 | 1629301
36.9529 | 1650460
36.9601 | 1651132
36.971 | 1585338
36.9727 | 1622755
36.9785 | 1663443
36.9811 | 1690823
36.9918 | 1676654
37.0009 | 1698750
37.0048 | 1601753
37.0279 | 1697220
37.0548 | 1638785
37.0722 | 1634113
37.0819 | 1658549
37.1022 | 1663550
37.1164 | 1647413
37.122 | 1661730
37.1277 | 1698278
37.1442 | 1677079
37.1875 | 1708520
37.2079 | 1710028
37.2211 | 1602880
37.2709 | 1651443
37.3781 | 1729635
37.4131 | 1742632
37.4194 | 1678238
37.4617 | 1692779
37.4695 | 1723502
37.4727 | 1658145
37.5019 | 1648717
37.6224 | 1686101
37.8097 | 1723309
37.9154 | 1682290
37.9523 | 1694434
37.9621 | 1725054
37.9965 | 1670788
38.0543 | 1699019
38.1089 | 1749025
38.2025 | 1682181
38.3599 | 1630412
38.55 | 1726675
38.6533 | 1698814