## About
Cascading Risks |  | ModelRisk example · General use · GU-01
How much do the links between risks add to the contingency? Ten project risks, some of which trigger others.
Next: Inputs ▸
Model card
Industry | General use
Difficulty | ★★☆☆☆ A risk register in which some risks make others more likely or worse: a few IF formulas on top of risk events.
Business question | Ten risks threaten a plant upgrade, and some of them make others more likely or worse: a late design approval or bad ground makes a redesign of the foundations more likely, and a redesign makes an expensive acceleration of the programme more likely. How much contingency do the risks need, and how much of it is due to the links between them?
Who it is for | Risk analysts, project managers and anyone who keeps a risk register and suspects that its risks are not independent.
Main outputs | The total cost of the risks with and without the links, from the same draws · the contingency at the chosen confidence level both ways and the difference · how much more likely the linked risks become · the risks that drive the total.
ModelRisk techniques | Risk events as a chance draw and a how-bad draw (the U arguments of VoseBernoulli and VosePERT) · probabilities and an impact that depend on whether other risks happen (IF with OR or AND) · the same draws with and without the links, so the difference is the effect of the links alone · tornado ranking of the risks (VoseSimSensitivityMean).
File | GU-01 Cascading risks · Version 1.0 · October 2026 · re-issues the examples Cascading Risks and Correlated Risk Portfolio · built with ModelRisk 10
The business question
A plant upgrade has ten risks on its register, each with a probability and a cost range. Registers usually treat their risks as independent, but some of these are linked. If the regulator approves the design late (A) or the ground turns out worse than surveyed (C), the foundations are much more likely to need a redesign (D): 50% instead of 15%. A late approval or a redesign makes it more likely that the programme has to be accelerated with overtime and extra shifts (E): 45% instead of 22%. And if the specialist contractor is unavailable, the ground is bad, the programme is accelerated and prices rise, all in the same project (B, C, E and F), a major claim from the main contractor (H) becomes more likely (13% instead of 5%) and 3.2 times as large. The model simulates the register twice from the same draws, once as if the risks were independent and once with the links, so the difference between the two totals is the effect of the links alone.
How the model works
Three sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | The rules that link the risks: the probability of D, E and H when the risks that trigger them happen, and the factor on H's impact; and the confidence level at which the contingency is read.
2 Risks | The register gives each risk its probability on its own and a three-point cost range. In every iteration each risk gets two draws: a chance draw that decides whether it happens and a how-bad draw that places its cost in the range. With the links, D, E and H first look at whether the risks that trigger them happened, and use the raised probability if they did. Both versions of the register use the same draws: a higher probability only adds iterations in which the risk happens, so the difference between the two totals is the effect of the links.
3 Results | The contingency at the chosen confidence level without and with the links, the S-curves of both totals, how much more likely D, E and H become, and the risks that drive the total.
How to use it
Step 1 | Replace the ten risks on the Risks sheet with your own: probability and cost range.
Step 2 | Change the links in the 'Triggered?' column on the Risks sheet (an OR or an AND of the risks that raise it), and the raised probabilities and the impact factor on the Inputs sheet. A risk can only be triggered by risks above it.
Step 3 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set).
Step 4 | Compare the contingency without and with the links: if they differ a lot, the links belong in the register.
Workbook map
Inputs | The rules that link the risks; the contingency confidence level.
Risks | The register; this iteration without and with the links; outputs and checks.
Results | Contingency both ways, S-curves, the linked risks' probabilities and the ranking of the risks.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Money | US$ million (US$m).
On its own | A risk's probability when nothing is known about the other risks: the register's usual number.
With the links | The probability, or impact, once it is known which of the risks that trigger it have happened.
Draws | Each risk's chance draw and how-bad draw are uniform numbers between 0 and 1, shared by both versions of the register.
Key assumptions and limitations
Links | Only the three links on the Inputs sheet are modelled: every other pair of risks is independent.
Order | A risk is only triggered by risks above it in the list, so the links are worked out from top to bottom.
Impacts | Each cost range is a PERT distribution from 80% to 150% of its most likely value.
Data | The project and its risks are invented for this example. The probabilities, cost ranges and links are those of ModelRisk's earlier Cascading Risks example.
ModelRisk functions used
VoseUniform | The two draws per risk: whether it happens and how bad it is.
VoseBernoulli | Whether a risk happens: VoseBernoulli(probability, chance draw). With the same draw, a higher probability makes the risk happen in every iteration it happened in before, and in some more.
VosePERT | The cost if the risk happens, placed in its range by the how-bad draw (the U argument).
VoseInput, VoseOutput | Name each risk's cost with the links and the totals, for the Results Viewer and the sensitivity analysis.
VoseSimMean, VoseSimPercentile | Statistics of the simulation for the tables and charts on the Results sheet.
VoseSimSensitivityMean | The tornado chart: each risk ranked by how far the mean total moves across the range of its cost.
Further reading
Dependencies | Vose, D. (2008). Risk Analysis: A Quantitative Guide, 3rd edition. Wiley: modelling correlation and dependencies with logic in the model.
Risk registers | Hillson, D. and Simon, P. (2020). Practical Project Risk Management: The ATOM Methodology, 3rd edition. Berrett-Koehler.
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Cascading Risks |  |  |  | ModelRisk example · General use · GU-01
INPUTS · The rules that link the risks, and the confidence level. The ten risks themselves are on the Risks sheet. Change only the yellow cells.
◂ About |  |  |  | Next: Risks ▸
How to read this sheet: yellow cells are inputs.
1 The links between the risks
What happens to D, E and H when the risks that trigger them happen. Each risk's probability on its own and its cost range are on the Risks sheet.
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
D Foundations redesigned: probability if A or C happens | probability | 50% | Fixed | On its own: 15%. A late approval or bad ground often forces a redesign.
E Programme accelerated: probability if A or D happens | probability | 45% | Fixed | On its own: 22%. A late approval or a redesign leaves less time.
H Major claim: probability if B, C, E and F all happen | probability | 13% | Fixed | On its own: 5%. A contractor hit by all four has grounds for a claim.
H Major claim: cost factor if B, C, E and F all happen | × | 3.2 | Fixed | The claim's whole cost range is multiplied by this factor.
2 Contingency policy
The confidence level at which the contingency is read.
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
Confidence level for the contingency | probability | 80% | Fixed | P80 is a common choice for a project's risk contingency.

## Risks
Cascading Risks | [11 empty] | ModelRisk example · General use · GU-01
RISKS · The ten risks, and what happens to each in this iteration without and with the links.
◂ Inputs | [11 empty] | Next: Results ▸
1 The risk register
Yellow cells are inputs: each risk's probability on its own and its cost if it happens.
ID | Risk | Probability | Cost if it happens (US$m) |  |  | Expected | [5 empty] | Links to other risks
|  | on its own | Low | Most likely | High | on its own
A | Regulator approves the design late | 30% | 7 | 10 | 15 | 3.1 | [5 empty] | Independent of the other risks
B | Specialist contractor not available when needed | 20% | 9.8 | 12 | 18 | 2.5267 | [5 empty] | Independent of the other risks
C | Ground conditions worse than the survey showed | 10% | 10.4 | 13 | 19.5 | 1.365 | [5 empty] | Independent of the other risks
D | Foundations must be redesigned | 15% | 11.2 | 14 | 21 | 2.205 | [5 empty] | Raised to 50% if A or C happens
E | Programme must be accelerated | 22% | 6.4 | 8 | 12 | 1.848 | [5 empty] | Raised to 45% if A or D happens
F | Steel and cable prices rise | 12% | 4.8 | 6 | 9 | 0.756 | [5 empty] | Independent of the other risks
G | Severe weather stops site work | 7% | 6.4 | 8 | 12 | 0.588 | [5 empty] | Independent of the other risks
H | Main contractor files a major claim | 5% | 9.6 | 12 | 18 | 0.63 | [5 empty] | Raised to 13%, cost × 3.2 if B, C, E and F all happen
I | Commissioning tests fail and must be repeated | 19% | 8.8 | 11 | 16.5 | 2.1945 | [5 empty] | Independent of the other risks
J | Key equipment delivered late | 23% | 11.2 | 14 | 21 | 3.381 | [5 empty] | Independent of the other risks
| Expected cost of the register, risks independent |  |  |  |  | 18.5942
2 This iteration
Two draws per risk, used by both versions of the register: the chance draw decides whether the risk happens, the how-bad draw places its cost in the range.
ID | Risk | Chance draw | Happens on its own? | Triggered? | Probability with the links | Happens with the links? | How bad | Cost if it happens | Cost factor | Cost on its own | Cost with the links | How it is calculated
|  | 0 – 1 | 1 = yes | 1 = yes | probability | 1 = yes | 0 – 1 | US$m | × | US$m | US$m
A | Regulator approves the design late | 0.38847 | 0 | – | 30% | 0 | 0.68624 | 11.0784 | 1 | 0 | 0 | Two VoseUniform(0, 1) draws per risk, shared by both versions
B | Specialist contractor not available when needed | 0.50731 | 0 | – | 20% | 0 | 0.48328 | 12.4167 | 1 | 0 | 0 | Happens: VoseBernoulli(probability, chance draw)
C | Ground conditions worse than the survey showed | 0.19132 | 0 | – | 10% | 0 | 0.12443 | 11.7226 | 1 | 0 | 0 | Happens = 1 when the draw is in the top 'probability' of 0 – 1
D | Foundations must be redesigned | 0.51483 | 0 | 0 | 15% | 0 | 0.14371 | 12.7415 | 1 | 0 | 0 | Triggered if A or C happens: then the raised probability
E | Programme must be accelerated | 0.83596 | 1 | 0 | 22% | 1 | 0.49814 | 8.3008 | 1 | 8.3008 | 8.3008 | Triggered if A or D happens; D may itself be raised by A or C
F | Steel and cable prices rise | 0.57284 | 0 | – | 12% | 0 | 0.35215 | 5.9228 | 1 | 0 | 0 | Cost if it happens: VosePERT(low, most likely, high, how bad)
G | Severe weather stops site work | 0.84827 | 0 | – | 7% | 0 | 0.039172 | 6.8454 | 1 | 0 | 0 | Cost = happens × cost if it happens × cost factor
H | Main contractor files a major claim | 0.052588 | 0 | 0 | 5% | 0 | 0.16189 | 11.0119 | 1 | 0 | 0 | B, C, E and F all happen: raised probability and cost factor
I | Commissioning tests fail and must be repeated | 0.11514 | 0 | – | 19% | 0 | 0.87211 | 13.2692 | 1 | 0 | 0 | A higher probability only adds iterations in which it happens
J | Key equipment delivered late | 0.038816 | 0 | – | 23% | 0 | 0.67849 | 15.4816 | 1 | 0 | 0
| Total |  | 1 |  |  | 1 |  |  |  | 8.3008 | 8.3008 | Number of risks that happen, and the two totals
3 Value in this iteration
Key outputs, recorded by ModelRisk at every sample (VoseOutput). Their statistics appear on the Results sheet.
| Output | Unit | Value | [8 empty] | Meaning
| Total cost of the risks, as if independent | US$m | 8.3008 | [8 empty] | Every risk at its probability on its own.
| Total cost of the risks, with the links | US$m | 8.3008 | [8 empty] | What the contingency has to cover.
| Added by the links | US$m | 0 | [8 empty] | Same draws both ways: this is the effect of the links alone.
| Do the links add cost in this iteration? (1 = yes) | 1 / 0 | 0
4 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
| Probabilities are between 0% and 100% |  | OK
| Every cost range is in order (low ≤ most likely ≤ high) |  | OK
| The links only raise: each raised probability ≥ its own, cost factor ≥ 1 |  | OK

## Results
Cascading Risks | [6 empty] | ModelRisk example · General use · GU-01
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Risks
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 Risk contingency without and with the links | [5 empty] | Total cost of the risks — S-curves
The total cost of the risks at the confidence level on the Inputs sheet, from the same draws both ways.
Measure | Unit | Value
Expected cost of the register, risks independent | US$m | 18.5942
Mean total, risks independent (simulated) | US$m | 18.8309
Mean total, with the links (simulated) | US$m | 21.5307
Contingency, risks independent | US$m | 29.772
Contingency, with the links | US$m | 35.1703
Contingency the links add | US$m | 5.3983
Confidence level (Inputs sheet) |  | 80%
2 Cost ranges
P50 / P80 / P90: a 50%, 80% and 90% chance of not being exceeded.
Measure | Unit | P50 | P80 | P90 | Mean
Total, risks independent | US$m | 16.915 | 29.772 | 37.4758 | 18.8309
Total, with the links | US$m | 20.1104 | 35.1703 | 43.9837 | 21.5307
Added by the links | US$m | 0 | 0 | 13.4043 | 2.6998
Measure | Unit | Value
Chance that the links add cost | probability | 19.61%
3 How the links change the linked risks
How often each linked risk happens: on its own, and in the simulation with the links.
Linked risk |  | On its own | With the links | Change
D Foundations redesigned |  | 15% | 28.28% | 13.28%
E Programme accelerated |  | 22% | 31.88% | 9.88%
H Major claim |  | 5% | 5.17% | 0.17%
H's cost multiplied (B, C, E and F all happen) |  | 0% | 0.07% | 0.07%
4 Which risks matter | [5 empty] | Which risks drive the total with the links (US$m)
Lowest and highest mean total with the links over ten equal groups of each risk's cost (VoseSimSensitivityMean).
Input (ranked by influence) | Lowest mean | Highest mean | Rank
D Foundations must be redesigned | 15.5241 | 38.6923 | 1
C Ground conditions worse than the survey showed | 19.6333 | 38.7922 | 2
A Regulator approves the design late | 16.5377 | 35.0618 | 3
J Key equipment delivered late | 18.0637 | 34.0273 | 4
B Specialist contractor not available when needed | 19.0188 | 34.6323 | 5
E Programme must be accelerated | 17.2568 | 31.6433 | 6
I Commissioning tests fail and must be repeated | 19.3156 | 32.5986 | 7
H Main contractor files a major claim | 20.8841 | 33.3904 | 8
G Severe weather stops site work | 20.9192 | 29.73 | 9
F Steel and cable prices rise | 20.7385 | 27.4462 | 10
5 How to read these results
• Both totals come from the same draws. A link only raises a probability, so with the links a risk happens in every iteration in which it happened on its own, and in some more: the difference between the totals is the effect of the links alone, not sampling noise.
• The links add more to the contingency than to the mean: they make risks happen together, so bad outcomes cluster. A contingency set as if the risks were independent is then exceeded more often than its confidence level says: with the inputs as shipped, the independent P80 is exceeded about three times in ten, not two.
• D and E become much more likely because their triggers are common: A happens three times in ten. The rule for H looks dramatic but needs four risks at once, so it applies in very few iterations and adds little to any statistic.
• The tornado ranks the risks by their effect on the total with the links. C happens only one time in ten, yet ranks second: when it happens, D becomes much more likely, and through D so does E. A ranks above risks with larger costs for the same reason.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | TotalOwn | TotalLinked
1% | 99% | 0 | 0
3% | 97% | 0 | 0
5% | 95% | 0 | 0
7% | 93% | 0 | 0
9% | 91% | 0 | 0
11% | 89% | 0 | 0
13% | 87% | 0 | 0
15% | 85% | 0 | 0
17% | 83% | 6.2878 | 6.2878
19% | 81% | 7.4408 | 7.4571
21% | 79% | 8.1173 | 8.2304
23% | 77% | 8.9129 | 9.1735
25% | 75% | 9.4584 | 9.9314
27% | 73% | 10.0717 | 10.6337
29% | 71% | 10.6198 | 11.3779
31% | 69% | 11.169 | 11.9958
33% | 67% | 11.7187 | 12.5843
35% | 65% | 12.2022 | 13.0749
37% | 63% | 12.718 | 13.6293
39% | 61% | 13.1023 | 14.3574
41% | 59% | 13.5795 | 15.145
43% | 57% | 14.1579 | 16.0594
45% | 55% | 14.8248 | 17.272
47% | 53% | 15.5715 | 18.4839
49% | 51% | 16.4456 | 19.6356
51% | 49% | 17.4387 | 20.5199
53% | 47% | 18.5553 | 21.3662
55% | 45% | 19.559 | 22.1413
57% | 43% | 20.3946 | 22.9778
59% | 41% | 21.145 | 23.7244
61% | 39% | 21.8666 | 24.5694
63% | 37% | 22.6608 | 25.4028
65% | 35% | 23.2714 | 26.214
67% | 33% | 23.9734 | 27.1916
69% | 31% | 24.7417 | 28.1721
71% | 29% | 25.4791 | 29.4722
73% | 27% | 26.2508 | 30.7781
75% | 25% | 27.1147 | 32.0569
77% | 23% | 28.0546 | 33.372
79% | 21% | 29.194 | 34.5949
81% | 19% | 30.4291 | 35.8344
83% | 17% | 31.938 | 37.2842
85% | 15% | 33.342 | 38.7773
87% | 13% | 34.9534 | 40.5897
89% | 11% | 36.4774 | 42.9674
91% | 9% | 38.4337 | 45.2705
93% | 7% | 40.3443 | 47.6367
95% | 5% | 43.4299 | 50.3592
97% | 3% | 47.9536 | 54.4363
99% | 1% | 55.2326 | 62.913
Overall mean of TotalLinked |  | 21.5307
Ranked input (chart) |  |  |  | Highest − mean | Lowest − mean
D Foundations must be redesigned |  |  |  | 17.1616 | -6.0066
C Ground conditions worse than the survey showed |  |  |  | 17.2615 | -1.8974
A Regulator approves the design late |  |  |  | 13.5311 | -4.9929
J Key equipment delivered late |  |  |  | 12.4966 | -3.467
B Specialist contractor not available when needed |  |  |  | 13.1016 | -2.5119
E Programme must be accelerated |  |  |  | 10.1126 | -4.2738
I Commissioning tests fail and must be repeated |  |  |  | 11.0679 | -2.215
H Main contractor files a major claim |  |  |  | 11.8598 | -0.64658
G Severe weather stops site work |  |  |  | 8.1994 | -0.61147
F Steel and cable prices rise |  |  |  | 5.9155 | -0.79214

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
1389
0
0
0
0
70
185
198
114
44
1610
0
0
0
0
3
125
149
84
29
1790
0
0
0
0
0
48
76
60
26
1435
0
0
0
0
43
198
203
109
12
1358
0
0
0
0
31
233
217
139
22
1769
0
0
0
0
5
71
84
53
18
1862
0
0
0
0
0
15
52
45
26
1911
0
0
0
0
0
18
36
24
11
1618
0
0
0
0
13
125
145
85
14
1517
0
0
0
0
3
144
191
116
29
441
554
444
304
148
70
30
6
2
1
432
446
411
294
205
128
51
24
4
5
1616
0
69
72
67
81
30
20
33
12