## About
Simple Project Schedule with Risks |  | ModelRisk example · General use · GU-04
Why does a project built from most-likely durations finish late? Sixteen activities, three paths, three risks.
Next: Inputs ▸
Model card
Industry | General use
Difficulty | ★★☆☆☆ A small network of activities with uncertain durations, parallel paths, risk events and alternative ways of working.
Business question | A factory building has sixteen activities on three parallel paths and three risks that can delay them. The plan, built from each activity's most likely duration, finishes in week 68. How likely is that, when will the project really finish, and how likely is it to meet the contract date?
Who it is for | Project planners and managers who build schedules from single-point estimates, and anyone new to schedule risk analysis.
Main outputs | The finish week and date at P50 / P80 / P90 · the chance of meeting the plan and the contract date · how often each path is critical · how often each risk happens · the activities that drive the finish.
ModelRisk techniques | Finish-to-start logic with MAX over parallel predecessors · triangular durations (VoseTriangle) · risk events that add delay (VoseBernoulli) with one probability that depends on the others · alternative ways of doing an activity (VoseDiscrete) · criticality of each path · tornado ranking of the activities (VoseSimSensitivityMean).
File | GU-04 Simple project schedule with risks · Version 1.0 · October 2026 · re-issues the examples Schedule Model With Risks, Project Schedule 1–3, Silo and Hospital · built with ModelRisk 10
The business question
A company is building a small factory. The schedule has sixteen activities. After design and approvals, three activities run side by side, and then three paths follow: the building itself (foundations, steel frame, roof), the site services (ground works, drainage, utility connections) and the process equipment (order, manufacture, installation). Commissioning and fit-out can start only when all three are done, followed by the handover tests. Each duration is uncertain, between 80% and 150% of its most likely value. Ground works can go three ways: as normal, with a problem, or better than planned. Three risks can add delay: storm damage to the cladding, a utility company that connects late, and an installation crew that loses its slot, which is twice as likely if one of the other two has already delayed the site. The plan, with every activity at its most likely duration and no risks, finishes in week 68, and the contract allows 80 weeks.
How the model works
Three sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | The date the project starts and the contract completion date.
2 Schedule | Each activity starts when the last of its predecessors finishes (MAX) and lasts a triangular duration. Ground works' duration depends on which of its three ways happens (VoseDiscrete). Each risk happens with its probability (VoseBernoulli) and adds its delay to the activity it affects; the crew risk's probability is raised if either other risk happened. The plan column repeats the logic with most likely durations and no risks.
3 Results | The finish week and date at P50 / P80 / P90 against the plan and the contract, how often each path is the critical one, how often each risk happens, and the activities that drive the finish.
How to use it
Step 1 | Set the start and contract dates on the Inputs sheet.
Step 2 | Replace the activities, their durations and 'starts after' links on the Schedule sheet: a new link is a new reference in the MAX of the Start column.
Step 3 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set).
Step 4 | Use the P80 date rather than the plan for commitments, and the critical-path shares to decide where to act.
Workbook map
Inputs | Project start and contract dates.
Schedule | Activities, ground works' ways, risks, this iteration's dates and the plan; outputs and checks.
Results | Finish dates, chances of meeting the plan and the contract, critical paths, risks and drivers.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Time | Weeks from the project start; dates are the start date plus 7 days per week.
Plan | Every activity at its most likely duration, ground works as normal, no risks.
Critical path | The path among the three that finishes last in an iteration: it sets the start of commissioning.
Key assumptions and limitations
Finish-to-start | An activity starts as soon as all its predecessors have finished; no lags, no resource limits.
Durations | Triangular from 80% to 150% of the most likely value, as in the original example.
Risk delays | Added to the duration of the activity a risk affects. Storm damage adds 20% to 50% of the roof's duration.
Data | The project is invented for this example. The network, durations and risks are those of ModelRisk's earlier Schedule Model With Risks example, and ground works' three ways those of Project Schedule 3.
ModelRisk functions used
VoseTriangle | Each activity's duration, and each risk's delay if it happens.
VoseDiscrete | Which way ground works go: normal, with a problem, or better than planned.
VoseBernoulli | Whether each risk happens; the crew risk's probability depends on the other two.
VoseInput, VoseOutput | Name each activity's duration and the finish week, for the Results Viewer and the tornado.
VoseSimMean, VoseSimPercentile | Statistics of the simulation: chances (means of 1/0 outcomes) and finish dates.
VoseSimSensitivityMean | The tornado chart: the activities whose durations move the mean finish most.
Further reading
Schedule risk | Vose, D. (2008). Risk Analysis: A Quantitative Guide, 3rd edition. Wiley: project risk analysis.
Merge bias | Hulett, D. (2009). Practical Schedule Risk Analysis. Gower: why parallel paths make projects late.
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Simple Project Schedule with Risks |  |  |  | ModelRisk example · General use · GU-04
INPUTS · The start and contract dates. Activities, ground works' three ways and the risks are on the Schedule sheet. Change only the yellow cells.
◂ About |  |  |  | Next: Schedule ▸
How to read this sheet: yellow cells are inputs.
1 Dates
When the project starts, and the completion date in the contract.
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
Project start date | date | 2027-01-04 | Fixed | A Monday.
Contract completion date | date | 2028-07-17 | Fixed | 80 weeks after the start: 12 weeks more than the plan.

## Schedule
Simple Project Schedule with Risks | [12 empty] | ModelRisk example · General use · GU-04
SCHEDULE · Sixteen activities on three paths, ground works' three ways and three risks: this iteration's dates, and the plan.
◂ Inputs | [12 empty] | Next: Results ▸
1 Activities
Yellow cells are inputs. Each activity starts when the last activity it follows has finished.
ID | Activity | Starts after | Duration (weeks) |  |  | This iteration (weeks from the start) |  |  |  |  | Plan |  | How it is calculated
|  |  | Low | Most likely | High | duration | risk delay | start | finish | finish date | start | finish
A | Design and approvals | start | 8 | 10 | 15 | 9.4456 | 0 | 0 | 9.4456 | 2027-03-11 02:52 | 0 | 10 | Duration: VoseTriangle(low, most likely, high)
B | Site clearance | A | 9.6 | 12 | 18 | 16.5107 | 0 | 9.4456 | 25.9564 | 2027-07-04 16:40 | 10 | 22 | Start: MAX of the finishes of the activities it follows
C | Procure structural steel | A | 10.4 | 13 | 19.5 | 14.1675 | 0 | 9.4456 | 23.6132 | 2027-06-18 07:01 | 10 | 23 | Finish = start + duration + risk delay
D | Detailed engineering | A | 6.4 | 8 | 12 | 8.9028 | 0 | 9.4456 | 18.3484 | 2027-05-12 10:32 | 10 | 18 | Finish date = start date + 7 × finish week
E | Foundations | B, C, D | 5.6 | 7 | 10.5 | 8.378 | 0 | 25.9564 | 34.3344 | 2027-09-01 08:10 | 23 | 30 | Plan: the same logic with most likely durations and no risks
F | Steel frame | E | 7.2 | 9 | 13.5 | 11.4542 | 0 | 34.3344 | 45.7886 | 2027-11-20 12:29 | 30 | 39
G | Roof and cladding | F | 8.8 | 11 | 16.5 | 15.5311 | 0 | 45.7886 | 61.3197 | 2028-03-08 05:42 | 39 | 50 | Risk delay from R1 (section 3)
H | Ground works | B, C, D | 3 ways | 3 ways | 3 ways | 10.7442 | 0 | 25.9564 | 36.7006 | 2027-09-17 21:42 | 23 | 30 | Duration from its three ways (section 2)
I | Drainage | H | 4.8 | 6 | 9 | 6.3234 | 0 | 36.7006 | 43.024 | 2027-11-01 04:02 | 30 | 36
J | Utility connections | I | 6.4 | 8 | 12 | 10.9371 | 0 | 43.024 | 53.9611 | 2028-01-16 17:28 | 36 | 44 | Risk delay from R2 (section 3)
K | Order process equipment | B, C, D | 4 | 5 | 7.5 | 6.0078 | 0 | 25.9564 | 31.9642 | 2027-08-15 17:59 | 23 | 28
L | Equipment manufacture | K | 7.2 | 9 | 13.5 | 9.1702 | 0 | 31.9642 | 41.1344 | 2027-10-18 22:35 | 28 | 37
M | Equipment installation | L | 8.8 | 11 | 16.5 | 15.6402 | 5.873 | 41.1344 | 62.6476 | 2028-03-17 12:48 | 37 | 48 | Risk delay from R3 (section 3)
N | Commissioning | G, J, M | 8 | 10 | 15 | 13.3045 | 0 | 62.6476 | 75.952 | 2028-06-18 15:57 | 50 | 60
O | Fit-out | G, J, M | 8 | 10 | 15 | 14.085 | 0 | 62.6476 | 76.7325 | 2028-06-24 03:04 | 50 | 60
P | Handover tests | N, O | 6.4 | 8 | 12 | 8.5201 | 0 | 76.7325 | 85.2526 | 2028-08-22 18:27 | 60 | 68
2 Activity H, ground works: three ways it can go
Yellow cells are inputs. VoseDiscrete picks the way; its duration range applies.
Way |  | Probability | Duration (weeks) |  |  | If this way | [6 empty] | How it is calculated
|  |  | Low | Most likely | High | weeks
1 | Normal | 70% | 6 | 7 | 9 | 7.6103 | [6 empty] | The plan assumes this way, at its most likely duration
2 | Problem | 20% | 10 | 12 | 15 | 10.7442 | [6 empty] | A problem: much longer
3 | Opportunity | 10% | 5 | 6 | 8 | 6.3416 | [6 empty] | Better than planned
| Way this iteration | 2 | [10 empty] | VoseDiscrete(ways, probabilities)
| Ground works' duration this iteration |  |  |  |  | 10.7442 | [6 empty] | The duration of the way that happens
3 Risks
Yellow cells are inputs. A risk that happens adds its delay to the activity it affects.
ID | Risk | Affects | Delay if it happens |  |  | Probability | If R1 or R2 | This iteration |  |  |  |  | How it is calculated
|  |  | Low | Most likely | High | on its own | happened | probability | happens? | delay (wk)
R1 | Storm damage to the cladding | G | 20% | 30% | 50% | 30% |  | 30% | 0 | 0 |  |  | Delay = happens × VoseTriangle(20%, 30%, 50%) × G's duration
R2 | Utility company connects late | J | 3 | 4 | 6 | 50% |  | 50% | 0 | 0 |  |  | Delay = happens × VoseTriangle(low, most likely, high)
R3 | Installation crew loses its slot | M | 4 | 6 | 7 | 20% | 40% | 20% | 1 | 5.873 |  |  | Probability raised if R1 or R2 happened in this iteration
4 Value in this iteration
Key outputs, recorded by ModelRisk at every sample (VoseOutput). Their statistics appear on the Results sheet.
| Output | Unit | Value | [9 empty] | Meaning
| Finish (weeks from the start) | weeks | 85.2526 | [9 empty] | The handover tests' finish.
| Finish date | date | 2028-08-22 18:27
| Planned finish (no risks) | weeks | 68 | [9 empty] | The same in every iteration.
| Contract completion | weeks | 80
| By the planned week? (1 = yes) | 1 / 0 | 0
| By the contract date? (1 = yes) | 1 / 0 | 0
| Roof path critical? (1 = yes) | 1 / 0 | 0
| Utilities path critical? (1 = yes) | 1 / 0 | 0
| Equipment path critical? (1 = yes) | 1 / 0 | 1
5 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
| All ranges: low ≤ most likely ≤ high |  | OK
| Ground works' three probabilities add up to 100% |  | OK
| Risk probabilities are between 0% and 100% |  | OK
| The contract date is after the start |  | OK
Formulas:
finish date = StartDate+7*[finish]

## Results
Simple Project Schedule with Risks | [6 empty] | ModelRisk example · General use · GU-04
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Schedule
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 When will the project finish? | [5 empty] | Finish week — S-curve
The finish week against the plan (most likely durations, no risks) and the contract.
Measure | Unit | Value
Planned finish (most likely durations, no risks) | weeks | 68
Mean finish (simulated) | weeks | 78.8996
Chance of finishing by the planned week | probability | 0.14%
Contract completion | weeks | 80
Chance of meeting the contract date | probability | 61.48%
2 Finish dates
P50 / P80 / P90: a 50%, 80% and 90% chance of finishing by then.
Measure | Unit | P50 | P80 | P90
Finish | weeks | 78.7542 | 82.3241 | 84.1932
Finish date | date | 2028-07-08 06:42 | 2028-08-02 06:27 | 2028-08-15 08:27
3 Which path is critical
How often each of the three paths finishes last and so sets the start of commissioning.
Path |  | Probability
Roof path (E → F → G) |  | 58.11%
Utilities path (H → I → J) |  | 8.57%
Equipment path (K → L → M) |  | 33.32%
Total |  | 100%
4 The risks
How often each risk happens in the simulation, and the delay it adds on average over all iterations.
Risk |  | Probability | Happens | Mean delay
R1 Storm damage to the cladding (on G) |  | 30% | 30.76% | 1.2345
R2 Utility company connects late (on J) |  | 50% | 50.47% | 2.1855
R3 Installation crew loses its slot (on M) |  | 20% | 33.38% | 1.8924
5 Which activities matter | [5 empty] | Which activities drive the finish (weeks)
Lowest and highest mean finish over ten equal groups of each activity's duration (VoseSimSensitivityMean).
Input (ranked by influence) | Lowest mean | Highest mean | Rank
A Design and approvals | 76.8265 | 81.5324 | 1
C Procure structural steel | 77.4593 | 81.7164 | 2
G Roof and cladding | 77.408 | 81.1805 | 3
P Handover tests | 77.3254 | 81.0112 | 4
N Commissioning | 77.9511 | 80.9609 | 5
O Fit-out | 77.8509 | 80.7813 | 6
F Steel frame | 78.0136 | 80.4592 | 7
B Site clearance | 78.1445 | 80.4799 | 8
E Foundations | 78.189 | 80.2561 | 9
M Equipment installation | 78.3262 | 80.2305 | 10
6 How to read these results
• The plan, with every activity at its most likely duration and no risks, finishes in week 68, and the simulation almost never achieves it. Three things push the finish out: each duration can run to 150% of its most likely value but only down to 80%; commissioning waits for the slowest of three paths; and the risks add delay.
• Plan on the P80 date rather than the most likely one. The contract's 80 weeks give about a 60% chance of finishing on time.
• The roof path is critical in about six iterations out of ten and the equipment path in about three. A plan that watches only the roof path misses a third of the ways the project can be late.
• The installation crew's risk is entered at 20% but happens about one time in three: it rises to 40% whenever storm damage or the utility company has already delayed the site, and the utility risk happens half the time.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | Finish | line at PlanFinish | line at ContractWeeks
1% | 99% | 70.0844 | 68 | 80
3% | 97% | 71.6366 | 68 | 80
5% | 95% | 72.442 | 68 | 80
7% | 93% | 73.0683 | 68 | 80
9% | 91% | 73.5541 | 68 | 80
11% | 89% | 73.9487 | 68 | 80
13% | 87% | 74.2832 | 68 | 80
15% | 85% | 74.6193 | 68 | 80
17% | 83% | 74.9841 | 68 | 80
19% | 81% | 75.316 | 68 | 80
21% | 79% | 75.5849 | 68 | 80
23% | 77% | 75.8486 | 68 | 80
25% | 75% | 76.1076 | 68 | 80
27% | 73% | 76.3345 | 68 | 80
29% | 71% | 76.5587 | 68 | 80
31% | 69% | 76.7829 | 68 | 80
33% | 67% | 77.0025 | 68 | 80
35% | 65% | 77.1867 | 68 | 80
37% | 63% | 77.3975 | 68 | 80
39% | 61% | 77.6009 | 68 | 80
41% | 59% | 77.8045 | 68 | 80
43% | 57% | 78.0344 | 68 | 80
45% | 55% | 78.2457 | 68 | 80
47% | 53% | 78.4403 | 68 | 80
49% | 51% | 78.658 | 68 | 80
51% | 49% | 78.8569 | 68 | 80
53% | 47% | 79.0522 | 68 | 80
55% | 45% | 79.2569 | 68 | 80
57% | 43% | 79.4851 | 68 | 80
59% | 41% | 79.7238 | 68 | 80
61% | 39% | 79.952 | 68 | 80
63% | 37% | 80.1824 | 68 | 80
65% | 35% | 80.4101 | 68 | 80
67% | 33% | 80.651 | 68 | 80
69% | 31% | 80.8802 | 68 | 80
71% | 29% | 81.1099 | 68 | 80
73% | 27% | 81.375 | 68 | 80
75% | 25% | 81.6523 | 68 | 80
77% | 23% | 81.9175 | 68 | 80
79% | 21% | 82.1942 | 68 | 80
81% | 19% | 82.4804 | 68 | 80
83% | 17% | 82.8241 | 68 | 80
85% | 15% | 83.1727 | 68 | 80
87% | 13% | 83.5603 | 68 | 80
89% | 11% | 83.9875 | 68 | 80
91% | 9% | 84.4883 | 68 | 80
93% | 7% | 85.0524 | 68 | 80
95% | 5% | 85.7193 | 68 | 80
97% | 3% | 86.6887 | 68 | 80
99% | 1% | 88.5134 | 68 | 80
Overall mean of Finish |  | 78.8996
Ranked input (chart) |  |  |  | Highest − mean | Lowest − mean
A Design and approvals |  |  |  | 2.6328 | -2.0731
C Procure structural steel |  |  |  | 2.8168 | -1.4403
G Roof and cladding |  |  |  | 2.2809 | -1.4916
P Handover tests |  |  |  | 2.1116 | -1.5742
N Commissioning |  |  |  | 2.0613 | -0.94851
O Fit-out |  |  |  | 1.8817 | -1.0487
F Steel frame |  |  |  | 1.5596 | -0.88601
B Site clearance |  |  |  | 1.5803 | -0.7551
E Foundations |  |  |  | 1.3565 | -0.71063
M Equipment installation |  |  |  | 1.3309 | -0.57342
Formulas:
Value = IFERROR(StartDate+7*[Value, row above],"–")
P80 = IFERROR(StartDate+7*[P80, row above],"–")
P90 = IFERROR(StartDate+7*[P90, row above],"–")

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
92
218
347
360
292
231
202
132
93
33
96
227
348
359
300
250
165
145
78
32
96
200
339
341
297
272
194
142
82
37
69
215
358
342
297
252
197
157
81
32
91
207
347
344
308
257
195
136
84
31
92
188
350
345
317
263
195
137
80
33
93
205
340
343
304
254
197
143
89
32
96
587
682
202
0
45
114
148
89
37
71
204
349
379
320
222
203
122
86
44
83
202
350
344
302
257
188
162
82
30
89
247
341
332
311
243
195
143
74
25
74
209
346
362
289
269
196
121
102
32
69
210
362
327
312
248
210
128
92
42
86
200
343
358
310
264
164
135
97
43
63
223
349
334
285
255
215
154
94
28
111
216
363
336
302
238
190
123
91
30
10
54
260
453
525
420
206
63
7
2