## About
Correlation Through a Common Factor (Look-up Table) |  | ModelRisk example · General use · GU-07
How much later does a project finish when bad weather hits every activity at once? Correlation through a common factor.
Next: Inputs ▸
Model card
Industry | General use
Difficulty | ★★☆☆☆ One shared random factor and a look-up table make six durations move together, without a correlation matrix.
Business question | Six building activities in a row are all slowed by bad weather and sped up by good weather, each to its own degree. How long will the work take, and how much does it matter that they all face the same season rather than weather of their own?
Who it is for | Anyone who has to correlate many variables that depend on one outside influence: weather, the economy, a market, an exchange rate.
Main outputs | Total time at P10 / median / P90 with no weather effect, with one shared season, and with independent weather for each activity · the chance of missing the deadline both ways · the correlation the shared weather creates · the drivers.
ModelRisk techniques | A common factor (VoseDiscrete weather index) and a look-up table of its effect on each activity (INDEX) · the same base durations with shared and with independent weather, to isolate the effect of sharing · VoseSimCorrelation · tornado ranking (VoseSimSensitivityMean).
File | GU-07 Correlation through a common factor · Version 1.0 · October 2026 · re-issues the example Correlation Using Look-up Tables · built with ModelRisk 10
The business question
A contractor schedules six activities one after the other: archaeology, digging the foundations, formwork, laying the foundations, walls and floors, and the roofing. Each has a three-point estimate for normal weather. The season's weather is graded from 1 (very poor) to 5 (very good), and a table says how much each activity's duration changes with it: in very poor weather laying the foundations takes 40% longer, in very good weather 18% less. All six activities face the same season, so the weather makes them late or early together. The model compares three versions from the same base durations: no weather effect, one shared season, and a season of its own for each activity.
How the model works
Three sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | Each activity's duration in normal weather as a triangular distribution, and the deadline.
2 Activities | The weather table gives each activity's change in duration for each grade. With shared weather, one draw of the weather index picks the column for every activity (INDEX); with independent weather each activity draws its own index. Both versions use the same base durations.
3 Results | The total time in the three versions, the chance of missing the deadline with shared and with independent weather, the correlation between two activities, and the tornado.
How to use it
Step 1 | Change the base durations and the deadline on the Inputs sheet.
Step 2 | Change the weather's chances and its table on the Activities sheet: one row per activity, one column per grade.
Step 3 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set).
Step 4 | Compare the shared and the independent versions: the difference is what ignoring the correlation would hide.
Workbook map
Inputs | Base durations and the deadline.
Activities | The weather's chances and effects, and this iteration's durations in the three versions; outputs and checks.
Results | Totals three ways, deadline, correlation and drivers.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Time | Weeks.
Weather index | 1 very poor, 2 poor, 3 normal, 4 good, 5 very good.
Change | The percentage added to (or taken off) an activity's normal-weather duration.
Key assumptions and limitations
In sequence | The six activities run one after the other; the total is their sum.
One season | With shared weather, the whole job sees one season's weather; the independent version is for comparison only.
Data | The activities, durations, weather table and weather weights are those of ModelRisk's earlier Correlation Using Look-up Tables example.
ModelRisk functions used
VoseTriangle | Each activity's duration in normal weather.
VoseDiscrete | The weather index: once for the shared season, once per activity for the independent version.
INDEX (Excel) | The look-up: the change in duration for this weather grade, from the activity's row of the table.
VoseInput, VoseOutput | Name the base durations, the weather and the three totals.
VoseSimCorrelation | The rank correlation the shared weather creates between two activities.
VoseSimMean, VoseSimStdev, VoseSimPercentile | Statistics of the simulation.
VoseSimSensitivityMean | The tornado chart: what moves the mean total with shared weather.
Further reading
Correlation | Vose, D. (2008). Risk Analysis: A Quantitative Guide, 3rd edition. Wiley: modelling correlation through a common factor and look-up tables.
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Correlation Through a Common Factor (Look-up Table) | [7 empty] | ModelRisk example · General use · GU-07
INPUTS · Base durations and the deadline. The weather's chances and its effect on each activity are tables on the Activities sheet. Change only the yellow cells.
◂ About | [7 empty] | Next: Activities ▸
How to read this sheet: yellow cells are inputs. Orange cells hold ModelRisk distributions and show the current random sample (press F9 to draw again).
1 Base durations
Each activity's duration in normal weather (weeks).
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Archaeology | weeks | 4.5131 | Triangle | 3 | 4 | 6 |  | Low, most likely and high, as in the original example.
Dig foundations | weeks | 9.4369 | Triangle | 9 | 11 | 13
Formwork | weeks | 2.3449 | Triangle | 2 | 2 | 3
Lay foundations | weeks | 7.1932 | Triangle | 6 | 7 | 9
Walls and floors | weeks | 17.8108 | Triangle | 15 | 17 | 21
Lay roofing | weeks | 6.7279 | Triangle | 6 | 7 | 9
2 Deadline
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Deadline for the six activities | weeks | 55 | Fixed |  |  |  |  | About five weeks more than with no weather effect.

## Activities
Correlation Through a Common Factor (Look-up Table) | [7 empty] | ModelRisk example · General use · GU-07
ACTIVITIES · The weather's effect on each activity, and this iteration's durations with shared and with independent weather.
◂ Inputs | [7 empty] | Next: Results ▸
1 The weather
Yellow cells are inputs: the chance of each grade (the original's weights 2, 5, 4, 3, 2 out of 16).
Grade | Weather | Probability
1 | Very poor | 12.5%
2 | Poor | 31.25%
3 | Normal | 25%
4 | Good | 18.75%
5 | Very good | 12.5%
| Weather index this season | 5 | [5 empty] | VoseDiscrete(grades, probabilities): one draw shared by every activity
2 How the weather changes each activity
Yellow cells are inputs: the change in duration for each weather grade.
ID | Activity | Weather grade
|  | 1 very poor | 2 poor | 3 normal | 4 good | 5 very good
1 | Archaeology | 40% | 28% | 0% | 0% | -2% |  | +40% = 40% longer than in normal weather
2 | Dig foundations | 30% | 20% | 0% | -6% | -10%
3 | Formwork | 10% | 4% | 0% | 0% | -3%
4 | Lay foundations | 40% | 25% | 0% | -12% | -18%
5 | Walls and floors | 10% | 4% | 0% | 0% | -2%
6 | Lay roofing | 20% | 8% | 0% | -4% | -6%
3 This iteration
The same base durations in three versions: no weather effect, the season's weather shared by every activity, and a weather draw of its own for each activity.
ID | Activity | Base | Shared weather |  | Independent weather |  |  | How it is calculated
|  | weeks | change | weeks | own index | change | weeks
1 | Archaeology | 4.5131 | -2% | 4.4229 | 3 | 0% | 4.5131 | Base: from the Inputs sheet (VoseTriangle)
2 | Dig foundations | 9.4369 | -10% | 8.4932 | 5 | -10% | 8.4932 | Shared: INDEX(the activity's row, the season's weather index)
3 | Formwork | 2.3449 | -3% | 2.2745 | 2 | 4% | 2.4387 | Duration = base × (1 + change)
4 | Lay foundations | 7.1932 | -18% | 5.8985 | 4 | -12% | 6.33 | Independent: each activity draws its own index (VoseDiscrete)
5 | Walls and floors | 17.8108 | -2% | 17.4545 | 3 | 0% | 17.8108 | Same base durations in every version
6 | Lay roofing | 6.7279 | -6% | 6.3242 | 4 | -4% | 6.4588
| Total | 48.0268 |  | 44.8678 |  |  | 46.0446
4 Value in this iteration
Key outputs, recorded by ModelRisk at every sample (VoseOutput). Their statistics appear on the Results sheet.
| Output | Unit | Value |  |  |  |  | Meaning
| Total, no weather effect | weeks | 48.0268
| Total, shared weather | weeks | 44.8678 |  |  |  |  | The real case: one season for the whole job.
| Total, independent weather | weeks | 46.0446 |  |  |  |  | For comparison only.
| Late, shared weather? (1 = yes) | 1 / 0 | 0
| Late, independent weather? (1 = yes) | 1 / 0 | 0
5 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
| Normal weather (grade 3) changes nothing |  |  | OK
| The weather's chances add up to 100% |  |  | OK

## Results
Correlation Through a Common Factor (Look-up Table) | [6 empty] | ModelRisk example · General use · GU-07
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Activities
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 Total time three ways | [5 empty] | Total time — three versions
The same base durations with no weather effect, with the season shared by every activity, and with independent weather for each.
Measure | Unit | 10th pct | Median | 90th pct | Mean
No weather effect | weeks | 47.5987 | 49.9561 | 52.5044 | 50.0069
Shared weather | weeks | 46.4629 | 51.3548 | 60.3072 | 52.7186
Independent weather | weeks | 48.8218 | 52.6238 | 56.8043 | 52.7202
Measure | Unit | Value
Standard deviation, shared weather | weeks | 5.3552
Standard deviation, independent weather | weeks | 3.0974
Standard deviation, no weather effect | weeks | 1.8783
2 What sharing the weather does
The deadline is on the Inputs sheet.
Measure | Unit | Value
Chance of missing the deadline, shared weather | probability | 36.65%
Chance of missing the deadline, independent weather | probability | 23.04%
Rank correlation, digging and laying foundations: shared |  | 0.7913
Rank correlation, digging and laying foundations: independent |  | 0.0084943
3 What moves the total | [5 empty] | What moves the total, shared weather (weeks)
Lowest and highest mean total with shared weather over ten equal groups of each input (VoseSimSensitivityMean).
Input (ranked by influence) | Lowest mean | Highest mean | Rank
Weather index this season | 46.6405 | 61.4645 | 1
Walls and floors | 50.6174 | 55.0447 | 2
Dig foundations | 51.2346 | 54.3511 | 3
Archaeology | 51.6695 | 54.4828 | 4
Lay foundations | 51.693 | 54.0573 | 5
Lay roofing | 51.8709 | 54.0987 | 6
Formwork | 52.3233 | 53.3622 | 7
4 How to read these results
• The weather adds about 2.7 weeks on average in both weather versions: sharing the season does not change the mean.
• It changes the spread. With one season for the whole job, the standard deviation is about 5.3 weeks against 3.1 with independent weather, and the 90th percentile about 60 weeks against 57: a bad season slows every activity at once, while independent weather averages out.
• So the chance of missing the 55-week deadline is about 37% with shared weather, and only about 23% if the correlation were ignored.
• The look-up table correlates the activities without a correlation coefficient: digging and laying the foundations move together (rank correlation about 0.8) because they read the same column of the table. The tornado puts the weather first.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | TotalShared | TotalOwn | TotalBase | line at Deadline
1% | 99% | 44.0463 | 46.0343 | 45.976 | 55
3% | 97% | 44.931 | 47.1214 | 46.6494 | 55
5% | 95% | 45.5239 | 47.7369 | 47.0123 | 55
7% | 93% | 45.9402 | 48.2071 | 47.2997 | 55
9% | 91% | 46.3049 | 48.6387 | 47.5081 | 55
11% | 89% | 46.603 | 48.9656 | 47.6915 | 55
13% | 87% | 46.8834 | 49.2315 | 47.8514 | 55
15% | 85% | 47.1457 | 49.5117 | 48.0096 | 55
17% | 83% | 47.3945 | 49.7368 | 48.1684 | 55
19% | 81% | 47.6334 | 49.945 | 48.3105 | 55
21% | 79% | 47.8244 | 50.146 | 48.4354 | 55
23% | 77% | 48.056 | 50.3738 | 48.5556 | 55
25% | 75% | 48.3105 | 50.5671 | 48.6762 | 55
27% | 73% | 48.5091 | 50.7713 | 48.7933 | 55
29% | 71% | 48.7291 | 50.9411 | 48.911 | 55
31% | 69% | 48.9612 | 51.0853 | 49.0075 | 55
33% | 67% | 49.1353 | 51.2673 | 49.1028 | 55
35% | 65% | 49.3482 | 51.439 | 49.2084 | 55
37% | 63% | 49.5808 | 51.5938 | 49.3131 | 55
39% | 61% | 49.7846 | 51.7482 | 49.4172 | 55
41% | 59% | 50.0219 | 51.9087 | 49.5218 | 55
43% | 57% | 50.2872 | 52.0658 | 49.6257 | 55
45% | 55% | 50.5321 | 52.2276 | 49.7173 | 55
47% | 53% | 50.8293 | 52.3843 | 49.8151 | 55
49% | 51% | 51.1267 | 52.5528 | 49.9126 | 55
51% | 49% | 51.5551 | 52.6922 | 50.0075 | 55
53% | 47% | 52.078 | 52.8356 | 50.112 | 55
55% | 45% | 52.7349 | 52.9964 | 50.2166 | 55
57% | 43% | 53.3553 | 53.1536 | 50.3163 | 55
59% | 41% | 53.9734 | 53.3086 | 50.4061 | 55
61% | 39% | 54.4491 | 53.457 | 50.4986 | 55
63% | 37% | 54.9176 | 53.6516 | 50.587 | 55
65% | 35% | 55.2755 | 53.8261 | 50.6937 | 55
67% | 33% | 55.6268 | 54.0053 | 50.798 | 55
69% | 31% | 55.9805 | 54.2141 | 50.9085 | 55
71% | 29% | 56.3464 | 54.3814 | 51.0281 | 55
73% | 27% | 56.7086 | 54.5732 | 51.134 | 55
75% | 25% | 57.0814 | 54.7746 | 51.2613 | 55
77% | 23% | 57.3927 | 55.0054 | 51.3906 | 55
79% | 21% | 57.7287 | 55.2054 | 51.524 | 55
81% | 19% | 58.1308 | 55.4355 | 51.668 | 55
83% | 17% | 58.5719 | 55.6911 | 51.8276 | 55
85% | 15% | 59.0058 | 55.98 | 52.0064 | 55
87% | 13% | 59.4676 | 56.2703 | 52.1767 | 55
89% | 11% | 60.013 | 56.6025 | 52.3832 | 55
91% | 9% | 60.6423 | 56.9952 | 52.623 | 55
93% | 7% | 61.3552 | 57.4627 | 52.89 | 55
95% | 5% | 62.077 | 58.0211 | 53.191 | 55
97% | 3% | 63.0347 | 58.823 | 53.6483 | 55
99% | 1% | 64.7358 | 60.279 | 54.5194 | 55
Overall mean of TotalShared |  | 52.7186
Ranked input (chart) |  |  |  | Highest − mean | Lowest − mean
Weather index this season |  |  |  | 8.7458 | -6.0781
Walls and floors |  |  |  | 2.326 | -2.1012
Dig foundations |  |  |  | 1.6325 | -1.4841
Archaeology |  |  |  | 1.7642 | -1.0491
Lay foundations |  |  |  | 1.3386 | -1.0256
Lay roofing |  |  |  | 1.38 | -0.84774
Formwork |  |  |  | 0.64356 | -0.39534

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
236
0
609
0
505
0
0
386
0
264
20
111
253
418
446
358
238
119
31
6
84
341
435
244
222
281
213
132
39
9
26
90
216
401
470
351
242
132
58
14
60
184
295
370
329
245
204
176
93
44
45
113
198
295
328
352
280
211
127
51
396
324
301
257
208
150
134
113
71
46
79
182
301
346
316
282
220
153
84
37
71
160
331
372
313
253
211
147
103
39
58
195
287
397
332
246
194
150
94
47