## About
Well Cost and Time (AFE) |  | ModelRisk example · Oil and gas · OG-07
What should the AFE for well K-15 be? Days and cost phase by phase, with trouble time and the events that wreck a well budget.
Next: Inputs ▸
Model card
Industry | Oil and gas
Difficulty | ★★★☆☆ Phase-by-phase well estimate with trouble time as a frequency × severity sum and two major risk events.
Business question | Well K-15 is planned to 4,200 m from a jack-up rig. How long will it take and what will it cost, how likely is the deterministic estimate to be exceeded, and how much contingency does a P80 authorisation for expenditure (AFE) need?
Who it is for | Drilling and well engineers, cost engineers and asset managers who prepare or approve AFEs.
Main outputs | Total days and total cost with P50 / P80 / P90 · the chance of exceeding the deterministic estimate · the contingency for a P80 AFE · days at the end of each phase with their range · what drives the cost.
ModelRisk techniques | PERT phase durations and costs · trouble time as a frequency × severity sum (VosePoisson count, VoseAggregateMC of VoseLognormalObject event sizes) · risk events with VoseRiskEvent · time-dependent cost (spread rate × days) · P50 / P80 / P90 reporting.
File | OG-07 Well cost and time (AFE) · Version 1.0 · October 2026 · built with ModelRisk 10
The business question
Well K-15 is an appraisal well, planned to 4,200 m from a jack-up rig. The drilling engineer's deterministic estimate adds up the most likely duration and cost of each phase and puts a 10% allowance on top for trouble time. But wells rarely go to plan. Some trouble — lost circulation, a tight hole, an equipment failure, waiting on weather — happens on almost every well, more often in the difficult sections. And once in a while a major event, such as a stuck drill string that forces a sidetrack, adds weeks. Because most of the rig's cost accrues by the day, every lost day costs money. The model builds the well phase by phase, adds trouble time as a random number of events of random size, adds the two major risk events, and turns days into cost at the spread rate. The AFE then rests on a stated confidence level instead of a single number that is exceeded far more often than not.
How the model works
Three sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | The spread rate (rig, services, fuel, logistics) per day; how often trouble occurs and how many days an event costs; the chance and the size of a sidetrack and of a well-control event, and the phase each can happen in; the trouble allowance used in the deterministic estimate; and the confidence level of the AFE.
2 Well plan | Each phase has a trouble-free duration and a cost of materials and services (PERT), and a trouble factor for how difficult it is. In every iteration the number of trouble events in a phase is Poisson with a mean proportional to its duration and its trouble factor, and VoseAggregateMC adds up the days they cost. A major event adds its days and cost to the phase it happens in. Phase days × spread rate plus materials and services gives the phase cost.
3 Results | Percentiles of total cost and days in the P50 / P80 / P90 form used for AFEs, the chance of exceeding the deterministic estimate, the AFE at the chosen confidence level and its contingency, days at the end of each phase, and what drives the cost.
How to use it
Step 1 | Enter your well's phases, durations and costs on the Well plan sheet, and the spread rate and risk events on the Inputs sheet.
Step 2 | Calibrate the trouble rate and event size from offset wells (non-productive time per 10 days, days per event).
Step 3 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set).
Step 4 | Set the AFE confidence level on the Inputs sheet (80% as shipped), simulate again, and read the AFE and its contingency on the Results sheet.
Workbook map
Inputs | Spread rate, trouble time, major risk events, the deterministic allowance and the AFE level.
Well plan | The seven phases with their ranges; this iteration's duration, trouble time and cost per phase; totals and checks.
Results | AFE figures, the S-curve of cost, days by phase, and the cost drivers.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Money | US$ million (US$m); the spread rate is in US$ thousand per day (US$k/d).
Time | Days of rig time, 24 hours a day.
P50 / P80 / P90 | Cost-estimating convention: P80 is the value with an 80% chance of not being exceeded.
Trouble time | Non-productive time (NPT): rig time lost to unplanned events.
Key assumptions and limitations
Trouble time | Events occur at random (Poisson) at a rate proportional to time spent in each phase; event sizes are independent and Lognormal.
Major events | Each happens at most once, in one phase: as shipped, a sidetrack in the 12¼-in section and a well-control event in the reservoir section.
Costs | Every day costs the spread rate; materials and services are independent of days. No escalation or exchange-rate risk.
Data | Phases, durations, costs and rates are invented for this example.
ModelRisk functions used
VosePERT | Trouble-free duration and the cost of materials and services of each phase, and the spread rate.
VosePoisson, VoseAggregateMC, VoseLognormalObject | Trouble time: a Poisson number of events per phase, each of Lognormal size, summed by VoseAggregateMC.
VoseRiskEvent, VosePERTObject | The sidetrack and the well-control event: zero, or a PERT number of days.
VoseInput, VoseOutput | Name the uncertain quantities and the outputs for the Results Viewer and the sensitivity analysis.
VoseSimMean, VoseSimPercentile, VoseSimProbability | Statistics of the simulation for the tables and charts on the Results sheet.
VoseSimSensitivityMean | The tornado chart: the ten VoseInputs that move the mean total cost most across their range, ranked.
Further reading
Well cost estimating | Adams, N. J. (1985). Drilling Engineering: A Complete Well Planning Approach. PennWell.
Risk analysis | Vose, D. (2008). Risk Analysis: A Quantitative Guide, 3rd edition. Wiley — chapters on aggregate distributions and project risk.
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Well Cost and Time (AFE) | [7 empty] | ModelRisk example · Oil and gas · OG-07
INPUTS · Rates, trouble time, the major risk events and the AFE level. Each phase's durations, costs and trouble factor are on the Well plan sheet. Change only the yellow cells.
◂ About | [7 empty] | Next: Well plan ▸
How to read this sheet: yellow cells are inputs. Orange cells hold ModelRisk distributions and show the current random sample (press F9 to draw again). Low / Most likely / High are the minimum, most likely and maximum for PERT. Mean is the distribution's average (VoseMean); it shows ✗ if a range is out of order.
1 Rig and spread rate
Everything that costs money by the day.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Spread rate | US$k/d | 340.9883 | PERT | 330 | 360 | 410 | 363.3333 | Jack-up day rate with services, fuel, logistics and supervision; the range covers the service contracts still open.
2 Trouble time
Frequent, smaller events: lost circulation, tight hole, equipment failure, waiting on weather.
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Trouble events per 10 days of operations | events | 1 | Fixed |  |  |  |  | Offset wells: 61 events in 610 rig days. Multiplied by each phase's trouble factor.
Trouble events per day of operations | events / day | 0.1 | Calculated |  |  |  |  | The rate above ÷ 10. A phase expects this × its days × its trouble factor events.
Days lost per event, mean | days | 1.2 | Fixed |  |  |  |  | Offset wells: average non-productive time per event.
Days lost per event, standard deviation | days | 1 | Fixed |  |  |  |  | A Lognormal with this mean and spread: many short events, a few long ones.
3 Major risk events
Rare events that add weeks. Each happens at most once, in the section where it can occur.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Chance of a sidetrack | probability | 10% | Fixed |  |  |  |  | Stuck pipe in the 12¼-in section that cannot be freed: 2 of 18 offset wells.
Days lost to a sidetrack | days | 14.3294 | Risk event · PERT | 8 | 14 | 25 | 1.4833 | Fishing, plugging back and re-drilling the section.
Direct cost of a sidetrack | US$m | 2.5 | Fixed |  |  |  |  | Equipment lost in the hole, cement plugs, extra casing; on top of the rig days.
Phase in which a sidetrack can happen | 1 – 7 | 4 | Fixed |  |  |  |  | Phase number on the Well plan sheet: 4 = the 12¼-in section.
Chance of a well-control event | probability | 3% | Fixed |  |  |  |  | Influx in the reservoir section; pressure is better known after the 2024 appraisal well.
Days lost to a well-control event | days | 0 | Risk event · PERT | 5 | 10 | 20 | 0.325 | Shut in, circulate out the influx, raise the mud weight.
Direct cost of a well-control event | US$m | 1.5 | Fixed |  |  |  |  | Kill mud, specialist services.
Phase in which a well-control event can happen | 1 – 7 | 5 | Fixed |  |  |  |  | Phase number on the Well plan sheet: 5 = the 8½-in reservoir section.
4 Deterministic estimate and AFE
The single-number estimate the simulation is compared with, and the AFE's confidence level.
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Trouble-time allowance in the deterministic estimate | of trouble-free days | 10% | Fixed |  |  |  |  | Added to the sum of the most likely phase durations, as many deterministic AFEs do.
AFE confidence level | probability | 80% | Fixed |  |  |  |  | The AFE is the total cost with this chance of not being exceeded: 80% (P80) is common; some companies use 50% or 90%.

## Well plan
Well Cost and Time (AFE) | [10 empty] | ModelRisk example · Oil and gas · OG-07
WELL PLAN · Seven phases from mobilisation to abandonment: ranges, then this iteration's days and cost.
◂ Inputs | [10 empty] | Next: Results ▸
1 Phases
Yellow cells are inputs: the trouble-free duration, the cost of materials and services, and how trouble-prone the phase is.
No. | Phase | Depth | Duration (days) |  |  | Materials and services (US$m) |  |  | Trouble |  | Note
|  | m, at end | Low | Most likely | High | Low | Most likely | High | factor
1 | Mobilise and rig up | – | 3 | 4 | 6 | 1 | 1.2 | 1.5 | 0.5 |  | Tow, preload and rig up the jack-up; mobilisation fee
2 | 26-in surface hole, 20-in casing | 450 | 4 | 5 | 7 | 1.6 | 1.8 | 2.2 | 0.8 |  | Shallow gas is mapped as unlikely
3 | 17½-in hole, 13⅜-in casing | 1800 | 8 | 10 | 14 | 3 | 3.4 | 4 | 1 |  | Reactive shales: tight hole is common
4 | 12¼-in hole, 9⅝-in casing | 3400 | 12 | 15 | 21 | 4 | 4.6 | 5.6 | 1.3 |  | Long section through faulted chalk: losses and stuck pipe
5 | 8½-in reservoir section | 4200 | 8 | 10 | 15 | 2.5 | 3 | 3.8 | 1.5 |  | Depleted reservoir in offset wells: lost circulation
6 | Logging and testing | – | 5 | 6 | 9 | 3.5 | 4.2 | 5.5 | 0.8 |  | Wireline logs, cores and a drill-stem test
7 | Plug, abandon and rig down | – | 4 | 5 | 7 | 1.2 | 1.5 | 2 | 0.5 |  | Cement plugs, cut and pull casing, demobilise
| Total, most likely values |  |  | 55 |  |  | 19.7
2 Major risk events in this iteration
Each event's days come from its risk event on the Inputs sheet: zero when it does not happen.
| Event | Phase | Days lost | Direct cost | [6 empty] | How it is calculated
|  | no. | days | US$m
| Sidetrack | 4 | 14.3294 | 2.5 | [6 empty] | Phase from Inputs; days from the risk event; the direct cost only if the event happens
| Well-control event | 5 | 0 | 0
3 This iteration, phase by phase
Money in US$m. Trouble events are Poisson with mean = events per day × duration × trouble factor.
No. | Phase | Duration | Trouble | Trouble | Major | Phase | Days at | Materials, | Major event | Phase | How it is calculated
|  | days | events | days | event days | days | end of phase | services | cost | cost
1 | Mobilise and rig up | 3.469 | 0 | 0 | 0 | 3.469 | 3.469 | 1.1937 | 0 | 2.3766 | Duration and materials: PERT from the table above
2 | 26-in surface hole, 20-in casing | 4.4386 | 0 | 0 | 0 | 4.4386 | 7.9076 | 1.696 | 0 | 3.2095 | Trouble days: VoseAggregateMC adds up the events' Lognormal sizes
3 | 17½-in hole, 13⅜-in casing | 9.808 | 0 | 0 | 0 | 9.808 | 17.7155 | 3.5356 | 0 | 6.88
4 | 12¼-in hole, 9⅝-in casing | 16.0784 | 2 | 1.5229 | 14.3294 | 31.9307 | 49.6462 | 5.2123 | 2.5 | 18.6003 | Major event days and cost: SUMIF over the events in this phase (section 2)
5 | 8½-in reservoir section | 9.6682 | 0 | 0 | 0 | 9.6682 | 59.3144 | 2.9899 | 0 | 6.2867
6 | Logging and testing | 6.5431 | 2 | 1.3315 | 0 | 7.8746 | 67.189 | 4.0709 | 0 | 6.7561
7 | Plug, abandon and rig down | 5.1523 | 0 | 0 | 0 | 5.1523 | 72.3413 | 1.3413 | 0 | 3.0982 | Phase cost = days × spread rate ÷ 1000 (US$k to US$m) + materials + major event cost
| Total | 55.1575 | 4 | 2.8544 | 14.3294 | 72.3413 |  | 20.0399 | 2.5 | 47.2074
4 Value in this iteration
Key outputs, recorded by ModelRisk at every sample (VoseOutput). Their statistics appear on the Results sheet.
| Output | Unit | Value |  | Meaning
| Total cost of the well | US$m | 47.2074 |  | Rig and spread, materials and services, major event costs.
| Total days | days | 72.3413 |  | From the start of mobilisation to rig release.
| Trouble time (all phases) | days | 2.8544 |  | Days lost to the frequent, smaller events. Marked as an input, for the tornado chart.
| Major event days | days | 14.3294 |  | Days lost to a sidetrack or a well-control event.
| A major event happens? (1 = yes) | 1 / 0 | 1 |  | Sidetrack or well-control event in this iteration.
| Materials and services | US$m | 20.0399 |  | Everything that is not charged by the day.
| Deterministic estimate: days | days | 60.5 |  | Sum of most likely durations plus the trouble allowance.
| Deterministic estimate: cost | US$m | 41.48 |  | Deterministic days × most likely spread rate + most likely materials and services.
5 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
| Phase durations: Low ≤ Most likely ≤ High |  | OK
| Phase costs: Low ≤ Most likely ≤ High |  | OK
| Trouble factors are not negative |  | OK
| Each major event's phase is a phase of the well |  | OK

## Results
Well Cost and Time (AFE) | [6 empty] | ModelRisk example · Oil and gas · OG-07
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Well plan
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 The AFE | [5 empty] | Total well cost — S-curve
The AFE is the cost at the confidence level on Inputs (P80 as shipped). The deterministic estimate is the usual single number.
Measure | Unit | Value
Deterministic estimate, with trouble allowance | US$m | 41.48
Mean cost of the well | US$m | 44.3455
Chance of staying within the deterministic estimate | probability | 15.56%
Chance of exceeding the deterministic estimate | probability | 84.44%
AFE (P80 cost) | US$m | 46.3262
Contingency over the deterministic estimate | US$m | 4.8462
Contingency as a share of the deterministic estimate |  | 11.68%
2 Cost and days
P50 / P80 / P90: a 50%, 80% and 90% chance of not being exceeded.
Measure | Unit | P50 | P80 | P90 | Mean
Total cost of the well | US$m | 43.6689 | 46.3262 | 49.0363 | 44.3455
Total days | days | 64.8397 | 70.7777 | 75.833 | 66.1342
Trouble time | days | 6.6802 | 10.155 | 12.2433 | 7.2048
Major event days | days | 0 | 0 | 11.0593 | 1.7712
Materials and services | US$m | 20.0148 | 20.541 | 20.8137 | 20.0266
Chance of a sidetrack or a well-control event | probability |  |  |  | 12.57%
3 Days at the end of each phase | [5 empty] | Days at the end of each phase — 10th to 90th percentile
The time–depth plan with its range: 10th percentile, median and 90th percentile.
Measure | Unit | 10th pct | Median | 90th pct | Mean
1 Mobilise and rig up | days | 3.4847 | 4.2414 | 5.4066 | 4.4123
2 26-in surface hole, 20-in casing | days | 8.5392 | 9.803 | 11.9383 | 10.0734
3 17½-in hole, 13⅜-in casing | days | 18.7397 | 21.3196 | 24.8196 | 21.6285
4 12¼-in hole, 9⅝-in casing | days | 35.127 | 39.7514 | 49.1898 | 41.0185
5 8½-in reservoir section | days | 46.6479 | 52.4393 | 63.0928 | 53.7189
6 Logging and testing | days | 53.3634 | 59.3669 | 70.2793 | 60.6674
7 Plug, abandon and rig down | days | 58.7351 | 64.8397 | 75.833 | 66.1342
4 What drives the cost of the well | [5 empty] | What drives the cost of the well (US$m)
Lowest and highest mean total cost over ten equal groups of each input (VoseSimSensitivityMean), drawn from the overall mean.
Input (ranked by influence) | Lowest mean | Highest mean | Rank
Sidetrack days | 43.5806 | 51.41 | 1
Well control days | 44.1971 | 49.1452 | 2
Trouble time | 42.2389 | 47.1345 | 3
Spread rate | 42.7601 | 46.1727 | 4
Duration, 12¼-in hole | 43.2566 | 45.6198 | 5
Duration, 8½-in hole | 43.5459 | 45.2861 | 6
Duration, 17½-in hole | 43.6385 | 45.0201 | 7
Materials and services, Logging | 43.7787 | 45.1306 | 8
Materials and services, 12¼-in hole | 43.7894 | 44.8018 | 9
Materials and services, 17½-in hole | 43.9917 | 44.9598 | 10
5 How to read these results
• The deterministic estimate is exceeded far more often than not, even with its trouble allowance: most likely values add up to less than the median, trouble time is almost certain and its average is larger than the allowance, and the major events can only add time.
• An AFE at P80 is exceeded in 20% of wells; the contingency is the amount the AFE adds to the deterministic estimate to get there. Companies that set the AFE at P50 should expect to need a supplement about half the time.
• The sidetrack drives the upper end of the S-curve: it happens in one well in ten, but when it does it adds two weeks and several million dollars. Reducing that risk (better stuck-pipe practices, a contingency liner) narrows the range more than shaving days off the plan.
• Most of the cost accrues by the day, so the spread rate and every lost day matter. Trouble time is one of the largest drivers: individually small events add up to about a week on average, and some wells lose nearly twice that.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | TotalCost
1% | 99% | 39.2917
3% | 97% | 39.9468
5% | 95% | 40.3325
7% | 93% | 40.6162
9% | 91% | 40.8401
11% | 89% | 41.067
13% | 87% | 41.2486
15% | 85% | 41.4336
17% | 83% | 41.5902
19% | 81% | 41.7385
21% | 79% | 41.8743
23% | 77% | 42.014
25% | 75% | 42.1426
27% | 73% | 42.2601
29% | 71% | 42.3931
31% | 69% | 42.533
33% | 67% | 42.6504
35% | 65% | 42.7714
37% | 63% | 42.8908
39% | 61% | 43.0037
41% | 59% | 43.1261
43% | 57% | 43.2486
45% | 55% | 43.3739
47% | 53% | 43.4959
49% | 51% | 43.619
51% | 49% | 43.7266
53% | 47% | 43.853
55% | 45% | 43.973
57% | 43% | 44.099
59% | 41% | 44.2418
61% | 39% | 44.3769
63% | 37% | 44.515
65% | 35% | 44.6823
67% | 33% | 44.8582
69% | 31% | 45.0199
71% | 29% | 45.2022
73% | 27% | 45.4015
75% | 25% | 45.6498
77% | 23% | 45.8956
79% | 21% | 46.1784
81% | 19% | 46.4735
83% | 17% | 46.829
85% | 15% | 47.2773
87% | 13% | 47.8892
89% | 11% | 48.6414
91% | 9% | 49.4918
93% | 7% | 50.4585
95% | 5% | 51.5242
97% | 3% | 52.6935
99% | 1% | 54.6643
Overall mean of TotalCost |  | 44.3455
Ranked input (chart) |  |  |  | Highest − mean | Lowest − mean
Sidetrack days |  |  |  | 7.0645 | -0.76494
Well control days |  |  |  | 4.7997 | -0.14844
Trouble time |  |  |  | 2.789 | -2.1066
Spread rate |  |  |  | 1.8271 | -1.5854
Duration, 12¼-in hole |  |  |  | 1.2743 | -1.089
Duration, 8½-in hole |  |  |  | 0.94059 | -0.79959
Duration, 17½-in hole |  |  |  | 0.67457 | -0.70707
Materials and services, Logging |  |  |  | 0.78504 | -0.5668
Materials and services, 12¼-in hole |  |  |  | 0.45627 | -0.55609
Materials and services, 17½-in hole |  |  |  | 0.61425 | -0.35385
Period | 10th percentile | Median | 90th percentile | Mean
Mobilise | 3.4847 | 4.2414 | 5.4066 | 4.4123
26-in hole | 8.5392 | 9.803 | 11.9383 | 10.0735
17½-in hole | 18.7397 | 21.3196 | 24.8196 | 21.6285
12¼-in hole | 35.127 | 39.7514 | 49.1898 | 41.0183
8½-in hole | 46.6479 | 52.4393 | 63.0928 | 53.7185
Logging | 53.3634 | 59.3669 | 70.2793 | 60.6665
Abandon | 58.7351 | 64.8397 | 75.833 | 66.1333

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
77
184
298
349
362
293
240
131
58
8
1821
0
0
5
18
45
47
39
18
7
1943
0
0
9
13
10
11
11
1
2
120
251
348
318
338
278
179
100
53
15
918
853
164
38
17
1
6
1
1
1
73
182
294
338
374
313
239
124
54
9
85
206
322
354
331
306
186
132
62
16
731
985
218
41
16
6
2
0
0
1
100
242
350
401
358
252
163
94
32
8
93
227
337
382
331
281
198
98
42
11
155
548
659
398
156
50
22
7
3
2
75
197
302
310
384
302
239
124
50
17
91
226
312
350
318
290
214
120
59
20
121
795
692
199
97
61
28
6
0
1
64
200
309
370
336
318
203
134
52
14
117
264
362
359
333
249
168
89
44
15
52
466
754
412
165
87
41
19
3
1
51
168
326
351
363
288
249
140
50
14
155
291
379
354
302
227
151
91
40
10
46
413
701
469
191
95
50
27
6
2
90
209
315
335
356
273
229
119
61
13
84
278
367
347
351
255
184
86
42
6
41
370
675
516
211
101
49
28
6
3
79
207
314
340
334
271
251
127
49
28
46
465
818
390
120
92
45
23
0
1
41
370
675
516
211
101
49
28
6
3
180
481
571
407
215
95
33
9
5
4
1767
0
9
23
48
66
48
27
10
2
1767
0
0
0
0
0
0
0
0
233
8
44
153
338
447
454
313
164
57
22