## About
Field Development Concept Selection |  | ModelRisk example · Oil and gas · OG-08
Tieback, FPSO, or start small and expand? Three development concepts for the Osprey discovery, and the value of flexibility.
Next: Inputs ▸
Model card
Industry | Oil and gas
Difficulty | ★★★★☆ Three 25-year development cash-flow models on common random numbers, with a decision rule inside the simulation.
Business question | Which development concept should the company choose for the Osprey discovery while the size of the reservoir is still uncertain: a cheap subsea tieback to a nearby host, a large standalone FPSO, or a tieback with the option to expand if the reservoir proves large — and what is that option worth?
Who it is for | Asset and development managers, concept-select teams, reservoir and facilities engineers, and investment committees.
Main outputs | For each concept: expected NPV (EMV), chance of losing money, range of NPV, volume produced · how often each concept turns out best · the value of the option to expand · what drives the value of the flexible concept.
ModelRisk techniques | Lognormal recoverable volume (P90/P10) · mean-reverting oil price (VoseTimeGBMVR) · capacity- and deliverability-limited production with an economic limit · common random numbers across concepts · a decision rule on an imperfect estimate inside the simulation (real option) · frequency of the best decision.
File | OG-08 Field development concept selection · Version 1.0 · October 2026 · built with ModelRisk 10
The business question
Osprey is an oil discovery 25 km from the Kestrel platform, which has spare processing capacity for a few more years. The appraisal wells leave a wide range for the recoverable volume. A subsea tieback to Kestrel is cheap and quick, but its throughput is capped by the host's spare capacity and it must stop when Kestrel shuts down, leaving oil behind if the reservoir is large. A standalone floating production vessel (FPSO) has the capacity and the life to produce a large reservoir, but it costs more than twice as much and loses money if the reservoir is small. The third concept starts as a tieback and keeps an option: after two years of production, when the reservoir is better known, it adds a second phase — more capacity and a longer host life — if the estimate of the volume exceeds a threshold. The model evaluates the three concepts on the same simulated reservoir and oil price, so that their differences come from the concepts alone, and puts a value on the flexibility.
How the model works
Three sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | The recoverable volume (Lognormal from P90 and P10), how fast the reservoir can deliver, the oil price model, a common cost overrun factor, and for each concept its capital cost, capacity, first-oil year, operating costs and constraints — the host's remaining life for the tiebacks, a possible one-year delay for the FPSO, the expansion rule for the third concept.
2 Concepts | Each year, production is the smaller of the facility's capacity and what the reservoir can deliver (a share of the remaining volume). Production stops at the economic limit, or when the host shuts down. For the third concept, the volume is estimated with an error after two years of production; if the estimate exceeds the threshold, the expansion is built. The three concepts are the same block of rows; they differ only in the parameter table at the top of the sheet and in their capital phasing. Cash flows are discounted at 10% (real, pre-tax).
3 Results | EMV, chance of loss and range of NPV for each concept, how often each one turns out best, the value of the option to expand, and the drivers of the flexible concept's value.
How to use it
Step 1 | Review the reservoir range and each concept's costs and constraints on the Inputs sheet.
Step 2 | Press F9 on the Concepts sheet to see how the three concepts play out on one reservoir and one price path.
Step 3 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set).
Step 4 | Change the expansion threshold or the cost of the second phase and simulate again to see how the option's value changes.
Workbook map
Inputs | Reservoir, price, shared costs, and the parameters of the three concepts.
Concepts | This iteration's draws, what differs between the concepts, then 25 years of production and cash flow for each concept; outputs and checks.
Results | Concept comparison, the best concept in hindsight, the value of flexibility, drivers.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Money | US$ million (US$m), real 2026 terms; NPV at a 10% real discount rate, mid-year, before tax.
Volumes | MMbbl = million barrels; kb/d = thousand barrels per day.
Years | Year 0 is the investment decision (2026); first oil follows in year 3 or 4.
P90 / P10 | Petroleum convention for the recoverable volume: P90 is the low estimate (90% chance of being exceeded).
Key assumptions and limitations
Production | Each year, the reservoir can deliver at most a fixed share of the volume still in place; the facility caps the rest. No ramp-down of the host's ullage, no water handling limits.
Option | The volume estimate at the expansion decision has a 15% error (Lognormal). The second phase takes two years to build and also buys eight more years of host life.
Economics | Pre-tax, real terms; no inflation, no fiscal regime; costs are certain apart from a common overrun factor.
Data | The discovery, the host and all costs are invented for this example.
ModelRisk functions used
VoseLognormalAlt, VosePERT, VoseBernoulli, VoseNormal | Recoverable volume, deliverability, long-term price, overrun, host life, FPSO delay and the error of the volume estimate.
VoseTimeGBMVR | A 25-year mean-reverting oil price path, shared by the three concepts.
VoseInput, VoseOutput | Name the uncertain inputs and the outputs for the Results Viewer and the sensitivity analysis.
VoseSimMean, VoseSimPercentile, VoseSimProbability | Statistics of the simulation for the tables and charts on the Results sheet.
VoseSimSensitivityMean | The tornado chart: every VoseInput ranked by how far the mean NPV of concept C moves across its range.
Further reading
Flexibility | de Neufville, R. and Scholtes, S. (2011). Flexibility in Engineering Design. MIT Press.
Petroleum economics | Mian, M. A. (2011). Project Economics and Decision Analysis, Volume II: Probabilistic Models, 2nd edition. PennWell.
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Field Development Concept Selection | [7 empty] | ModelRisk example · Oil and gas · OG-08
INPUTS · Every assumption the model uses, with its uncertainty and its basis. Change only the yellow cells.
◂ About | [7 empty] | Next: Concepts ▸
How to read this sheet: yellow cells are inputs. Orange cells hold ModelRisk distributions and show the current random sample (press F9 to draw again). Low / Most likely / High are the minimum, most likely and maximum for PERT; the P90 (low) and P10 (high) estimates for Lognormal — P90 means a 90% chance of being exceeded. Mean is the distribution's average (VoseMean); it shows ✗ if a range is out of order. A phasing table gives the year of each payment and the share of the cost paid in it.
1 Reservoir
Shared by all three concepts: how much oil there is and how fast it can be produced.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Recoverable volume | MMbbl | 133.9652 | Lognormal · P90, P10 | 70 | – | 220 | 137.1213 | Appraisal wells and seismic: wide range because the eastern fault block is untested.
Deliverability: maximum production per year | of remaining | 23.01% | PERT | 15% | 20% | 26% | 20.17% | The most the wells can produce in a year, as a share of the oil still in place; sets the decline once capacity no longer binds.
Production uptime | share of the year | 92% | Fixed |  |  |  |  | Planned and unplanned shutdowns.
Production in the first-oil year | share of capacity | 50% | Fixed |  |  |  |  | Start-up: the wells come on stream through the year.
2 Oil price
A mean-reverting price path (VoseTimeGBMVR), the same for all concepts.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Oil price now | US$/bbl | 75 | Fixed |  |  |  |  | Brent, real 2026.
Long-term oil price | US$/bbl | 63.9669 | PERT | 55 | 70 | 95 | 71.6667 | Company planning range.
Annual price volatility |  | 25% | Fixed |  |  |  |  | Standard deviation of annual log returns.
Reversion factor | per year | 0.35 | Fixed |  |  |  |  | Share of the gap to the long-term price closed each year.
3 Shared costs and timing
Shared by all concepts.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Capital cost overrun factor | × | 1.0574 | PERT | 0.95 | 1.05 | 1.35 | 1.0833 | Applied to every concept's capital cost: market rates and execution risk.
Discount rate | real, per year | 10% | Fixed |  |  |  |  | Company hurdle rate for development projects.
Year of the investment decision | year | 2026 | Fixed |  |  |  |  | Year 0 of the cash flows.
4 Concept A: subsea tieback
Wells and a 25 km pipeline to the Kestrel platform, which processes the oil for a tariff.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Capital cost | US$m | 650 | Fixed |  |  |  |  | Subsea wells, manifold, pipeline and host modifications; phased as in the table below.
Capacity (host spare capacity) | kb/d | 40 | Fixed |  |  |  |  | Kestrel's ullage is the limit.
First oil | year | 3 | Fixed |  |  |  |  | Two years of execution after the investment decision.
Processing tariff | US$/bbl | 8 | Fixed |  |  |  |  | Paid to Kestrel's owners for each barrel.
Variable operating cost | US$/bbl | 5 | Fixed |  |  |  |  | Chemicals, power, transport.
Fixed operating cost | US$m per year | 40 | Fixed |  |  |  |  | Subsea intervention and inspection.
Kestrel's remaining life | years from now | 15.614 | PERT | 10 | 13 | 18 | 13.3333 | The host shuts down when its own fields deplete; rounded to whole years in the model.
Abandonment cost | US$m | 80 | Fixed |  |  |  |  | The year after production stops.
5 Concept B: standalone FPSO
A leased floating production vessel over the field: no host constraints.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Capital cost | US$m | 1500 | Fixed |  |  |  |  | Wells, risers, mooring and the FPSO conversion; phased as in the table below.
Capacity | kb/d | 75 | Fixed |  |  |  |  | Sized for the high case.
First oil, on schedule | year | 4 | Fixed |  |  |  |  | Three years of execution.
Chance that first oil slips by a year | probability | 30% | Fixed |  |  |  |  | The conversion yard has delivered three of its last ten vessels late.
First oil delayed by a year? | 1 = yes | 0 | Bernoulli | – | – | – |  | Drawn in every iteration from the chance above.
Variable operating cost | US$/bbl | 5 | Fixed |  |  |  |  | Chemicals, fuel, offloading.
Fixed operating cost | US$m per year | 110 | Fixed |  |  |  |  | Vessel lease, crew, maintenance.
Abandonment cost | US$m | 250 | Fixed |  |  |  |  | The year after production stops.
6 Concept C: tieback with option to expand
Starts as concept A. A second phase is built if the volume, estimated after two years of production, is above the threshold.
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Expansion decision | year | 5 | Fixed |  |  |  |  | After two years of production history.
Expand if the estimated volume exceeds | MMbbl | 110 | Fixed |  |  |  |  | The volume that pays for the second phase.
Error of the volume estimate at the decision | standard deviation | 15% | Fixed |  |  |  |  | Lognormal error: the estimate is within about ±15% of the true volume two times in three.
Capital cost of the second phase | US$m | 450 | Fixed |  |  |  |  | Infill wells, a second flowline, host debottlenecking; phased as in the table below.
Years to build the second phase | years | 2 | Fixed |  |  |  |  | Its capacity is available this many years after the decision.
Extra capacity | kb/d | 35 | Fixed |  |  |  |  | Available once the second phase is built.
Host life extension | years | 8 | Fixed |  |  |  |  | Bought with the second phase: Kestrel stays on for Osprey.
7 Capital phasing
When each concept's capital is paid: the year of each payment and its share of the capital cost.
Assumption | Unit | Total | Uncertainty | Payment 1 | Payment 2 | Payment 3 | Payment 4 | Basis / source (illustrative)
Concept A, and C's first phase: paid in year | year |  | Fixed · phasing | 0 | 1 | 2 |  | Years after the investment decision.
share of the cost paid | share | 100% | must total 100% | 30% | 40% | 30% |  | The shares must add up to 100%.
Concept B: paid in year | year |  | Fixed · phasing | 0 | 1 | 2 | 3 | Wells, risers and mooring first; the FPSO conversion in the last two payments.
share of the cost paid | share | 100% | must total 100% | 20% | 35% | 30% | 15% | The shares must add up to 100%.
moves a year later if first oil slips (1 = yes) | 1 / 0 |  | Fixed | 0 | 0 | 1 | 1
year in this iteration | year |  | Calculated | 0 | 1 | 2 | 3 | The conversion payments move with a late first oil.
Concept C's second phase: paid in year after the decision | year |  | Fixed · phasing | 0 | 1 |  |  | Spent while the second phase is built.
share of the cost paid | share | 100% | must total 100% | 50% | 50% |  |  | The shares must add up to 100%.

## Concepts
Field Development Concept Selection | [28 empty] | ModelRisk example · Oil and gas · OG-08
CONCEPTS · The three concepts on the same reservoir and price: 25 years of production and cash flow (US$m).
◂ Inputs | [28 empty] | Next: Results ▸
Year after the investment decision |  | Total | Open | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Calendar year |  |  |  | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051
1 This iteration's reservoir and decisions
Single values drawn once per iteration and used by the timelines below.
Quantity | Unit | Value |  | 2026: How it is calculated
Last year of the cash flows | year | 25 |  | 2026: The year columns of this sheet
One thousand barrels a day, for a year | MMbbl | 0.365 |  | 2026: 365 days ÷ 1,000
Kestrel shuts down after year | year | 16 |  | 2026: Host life, rounded to whole years
FPSO first oil | year | 4 |  | 2026: On schedule, or one year late
Concept C: volume estimate at the decision | MMbbl | 136.1229 |  | 2026: True volume × a Lognormal error
Concept C: build the second phase? (1 = yes) | 1 / 0 | 1 |  | 2026: The decision rule: expand if the estimate exceeds the threshold
Concept C: Kestrel shuts down after year | year | 24 |  | 2026: Extended if the second phase is built
2 What differs between the concepts
One column per concept — A, B and C, not years. The three blocks below are the same rows; each reads only its own column.
Parameter | Unit |  |  | 2026: A; 2027: B; 2028: C
Capital cost, first phase | US$m |  |  | 2026: 650; 2027: 1500; 2028: 650
Capital cost, second phase | US$m |  |  | 2026: 0; 2027: 0; 2028: 450; 2030: C only, and only in the iterations where it expands
Capacity | kb/d |  |  | 2026: 40; 2027: 75; 2028: 40
Extra capacity from the second phase | kb/d |  |  | 2026: 0; 2027: 0; 2028: 35; 2030: As above
…available from year | year |  |  | 2026: 0; 2027: 0; 2028: 7; 2030: The decision year plus the years to build
First oil | year |  |  | 2026: 3; 2027: 4; 2028: 3; 2030: B's is a year late in some iterations
Last year production is possible | year |  |  | 2026: 16; 2027: 25; 2028: 24; 2030: The tiebacks stop when Kestrel shuts down; the FPSO has no host
Cost per barrel produced | US$/bbl |  |  | 2026: 13; 2027: 5; 2028: 13; 2030: Variable cost, plus Kestrel's tariff for the tiebacks
Fixed operating cost | US$m per year |  |  | 2026: 40; 2027: 110; 2028: 40
Abandonment cost | US$m |  |  | 2026: 80; 2027: 250; 2028: 80
3 Oil price and discounting
One price path per iteration, shared by the concepts.
Oil price (real) | US$/bbl |  |  | 75 | 68.9773 | 72.3509 | 83.2706 | 78.7632 | 84.716 | 82.7791 | 120.7378 | 77.5838 | 101.2345 | 103.728 | 91.0842 | 66.023 | 72.3859 | 75.3725 | 54.7086 | 77.6018 | 75.8108 | 98.1493 | 94.4246 | 68.3504 | 83.5413 | 89.1442 | 61.2266 | 58.0543 | 87.9019
Discount factor (mid-year) |  |  |  | 0.95346 | 0.86678 | 0.78799 | 0.71635 | 0.65123 | 0.59203 | 0.5382 | 0.48928 | 0.4448 | 0.40436 | 0.3676 | 0.33418 | 0.3038 | 0.27618 | 0.25108 | 0.22825 | 0.2075 | 0.18864 | 0.17149 | 0.1559 | 0.14173 | 0.12884 | 0.11713 | 0.10648 | 0.096801 | 0.088001
4 Concept A: Subsea tieback
Capped by the host's spare capacity; stops when Kestrel shuts down.
Capital spend, first phase | US$m | 687.3294 |  | 206.1988 | 274.9317 | 206.1988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital spend, second phase | US$m | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production possible (1 = yes) | 1 / 0 |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capacity | kb/d |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Capacity this year | MMbbl |  |  | 13.432 | 13.432 | 13.432 | 6.716 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432
Volume remaining, start of year | MMbbl |  |  | 133.9652 | 133.9652 | 133.9652 | 133.9652 | 127.2492 | 113.8172 | 100.3852 | 86.9532 | 73.5212 | 60.0892 | 46.6572 | 35.9213 | 27.6558 | 21.2921 | 16.3928 | 12.6208 | 9.7167 | 7.4809 | 7.4809 | 7.4809 | 7.4809 | 7.4809 | 7.4809 | 7.4809 | 7.4809 | 7.4809
Potential production | MMbbl |  |  | 0 | 0 | 0 | 6.716 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 10.7359 | 8.2655 | 6.3636 | 4.8993 | 3.772 | 2.9041 | 2.2358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating margin if produced | US$m |  |  | -40 | -40 | -40 | 431.9374 | 843.3319 | 923.2892 | 897.2727 | 1407.1336 | 827.489 | 1145.1654 | 934.0436 | 605.4069 | 297.4182 | 250.9521 | 195.2691 | 81.1243 | 104.4388 | -40 | -40 | -40 | -40 | -40 | -40 | -40 | -40 | -40
Producing (1 = yes) | 1 / 0 | 14 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Oil production | MMbbl | 126.4843 |  | 0 | 0 | 0 | 6.716 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 13.432 | 10.7359 | 8.2655 | 6.3636 | 4.8993 | 3.772 | 2.9041 | 2.2358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative production | MMbbl |  | 0 | 0 | 0 | 0 | 6.716 | 20.148 | 33.58 | 47.012 | 60.444 | 73.876 | 87.308 | 98.0439 | 106.3094 | 112.673 | 117.5724 | 121.3444 | 124.2484 | 126.4843 | 126.4843 | 126.4843 | 126.4843 | 126.4843 | 126.4843 | 126.4843 | 126.4843 | 126.4843 | 126.4843
Revenue | US$m | 11148.5676 |  | 0 | 0 | 0 | 559.2454 | 1057.9479 | 1137.9052 | 1111.8887 | 1621.7496 | 1042.105 | 1359.7814 | 1113.6098 | 752.8588 | 420.1453 | 354.6436 | 284.3051 | 158.877 | 173.5046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating cost | US$m | -2204.2953 |  | 0 | 0 | 0 | -127.308 | -214.616 | -214.616 | -214.616 | -214.616 | -214.616 | -214.616 | -179.5662 | -147.4519 | -122.7271 | -103.6915 | -89.036 | -77.7528 | -69.0658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Abandoned this year (1 = yes) | 1 / 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Abandonment | US$m | -80 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net cash flow | US$m | 8176.943 |  | -206.1988 | -274.9317 | -206.1988 | 431.9374 | 843.3319 | 923.2892 | 897.2727 | 1407.1336 | 827.489 | 1145.1654 | 934.0436 | 605.4069 | 297.4182 | 250.9521 | 195.2691 | 81.1243 | 104.4388 | -80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Present value | US$m | 3589.8212 |  | -196.6028 | -238.3065 | -162.4817 | 309.4186 | 549.2012 | 546.6105 | 482.9165 | 688.4782 | 368.0649 | 463.0605 | 343.3555 | 202.3166 | 90.3564 | 69.309 | 49.0275 | 18.5167 | 21.6712 | -15.091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 Concept B: Standalone FPSO
Larger capacity, no host limit; first oil a year later, or two if the yard is late.
Capital spend, first phase | US$m | 1586.1447 |  | 317.2289 | 555.1506 | 475.8434 | 237.9217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital spend, second phase | US$m | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production possible (1 = yes) | 1 / 0 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Capacity | kb/d |  |  | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75
Capacity this year | MMbbl |  |  | 25.185 | 25.185 | 25.185 | 25.185 | 12.5925 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185
Volume remaining, start of year | MMbbl |  |  | 133.9652 | 133.9652 | 133.9652 | 133.9652 | 133.9652 | 121.3727 | 96.1877 | 74.0548 | 57.0147 | 43.8955 | 33.7951 | 26.0188 | 20.0319 | 15.4225 | 11.8738 | 9.1416 | 9.1416 | 9.1416 | 9.1416 | 9.1416 | 9.1416 | 9.1416 | 9.1416 | 9.1416 | 9.1416 | 9.1416
Potential production | MMbbl |  |  | 0 | 0 | 0 | 0 | 12.5925 | 25.185 | 22.1329 | 17.0401 | 13.1191 | 10.1004 | 7.7763 | 5.987 | 4.6094 | 3.5487 | 2.7322 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035
Operating margin if produced | US$m |  |  | -110 | -110 | -110 | -110 | 818.8637 | 1897.6472 | 1611.4756 | 1862.1811 | 842.2366 | 862.0079 | 657.7384 | 405.3827 | 171.2767 | 129.1349 | 82.2696 | -5.4382 | 42.7175 | 38.9501 | 85.939 | 78.1041 | 23.2573 | 55.2112 | 66.9968 | 8.2723 | 1.5994 | 64.3836
Producing (1 = yes) | 1 / 0 | 11 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Oil production | MMbbl | 124.8235 |  | 0 | 0 | 0 | 0 | 12.5925 | 25.185 | 22.1329 | 17.0401 | 13.1191 | 10.1004 | 7.7763 | 5.987 | 4.6094 | 3.5487 | 2.7322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative production | MMbbl |  | 0 | 0 | 0 | 0 | 0 | 12.5925 | 37.7775 | 59.9104 | 76.9505 | 90.0696 | 100.17 | 107.9463 | 113.9333 | 118.5426 | 122.0914 | 124.8235 | 124.8235 | 124.8235 | 124.8235 | 124.8235 | 124.8235 | 124.8235 | 124.8235 | 124.8235 | 124.8235 | 124.8235 | 124.8235
Revenue | US$m | 11174.3322 |  | 0 | 0 | 0 | 0 | 991.8262 | 2133.5722 | 1832.14 | 2057.3816 | 1017.8323 | 1022.51 | 806.6199 | 545.3175 | 304.3234 | 256.8786 | 205.9305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating cost | US$m | -1834.1177 |  | 0 | 0 | 0 | 0 | -172.9625 | -235.925 | -220.6644 | -195.2004 | -175.5957 | -160.5021 | -148.8815 | -139.9348 | -133.0468 | -127.7437 | -123.6608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Abandoned this year (1 = yes) | 1 / 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Abandonment | US$m | -250 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net cash flow | US$m | 7504.0698 |  | -317.2289 | -555.1506 | -475.8434 | -237.9217 | 818.8637 | 1897.6472 | 1611.4756 | 1862.1811 | 842.2366 | 862.0079 | 657.7384 | 405.3827 | 171.2767 | 129.1349 | 82.2696 | -250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Present value | US$m | 3257.8303 |  | -302.4659 | -481.1958 | -374.9578 | -170.4353 | 533.2668 | 1123.4551 | 867.3039 | 911.1225 | 374.6246 | 348.5626 | 241.7854 | 135.4719 | 52.0343 | 35.665 | 20.656 | -57.0628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 Concept C: Tieback with option to expand
As A, plus the second phase if the volume estimate is above the threshold.
Capital spend, first phase | US$m | 687.3294 |  | 206.1988 | 274.9317 | 206.1988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital spend, second phase | US$m | 475.8434 |  | 0 | 0 | 0 | 0 | 0 | 237.9217 | 237.9217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production possible (1 = yes) | 1 / 0 |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Capacity | kb/d |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75
Capacity this year | MMbbl |  |  | 13.432 | 13.432 | 13.432 | 6.716 | 13.432 | 13.432 | 13.432 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185 | 25.185
Volume remaining, start of year | MMbbl |  |  | 133.9652 | 133.9652 | 133.9652 | 133.9652 | 127.2492 | 113.8172 | 100.3852 | 86.9532 | 66.9451 | 51.541 | 39.6814 | 30.5506 | 23.5209 | 18.1087 | 13.9419 | 10.7338 | 8.264 | 6.3624 | 4.8984 | 3.7713 | 2.9035 | 2.9035 | 2.9035 | 2.9035 | 2.9035 | 2.9035
Potential production | MMbbl |  |  | 0 | 0 | 0 | 6.716 | 13.432 | 13.432 | 13.432 | 20.008 | 15.4041 | 11.8596 | 9.1307 | 7.0297 | 5.4122 | 4.1668 | 3.208 | 2.4699 | 1.9015 | 1.464 | 1.1271 | 0.86778 | 0.6681 | 0.6681 | 0.6681 | 0.6681 | 0.6681 | 0
Operating margin if produced | US$m |  |  | -40 | -40 | -40 | 431.9374 | 843.3319 | 923.2892 | 897.2727 | 2115.6188 | 954.8578 | 1006.4289 | 788.4124 | 508.9108 | 246.9701 | 207.4513 | 160.0936 | 63.0147 | 82.8435 | 51.955 | 55.9745 | 30.6584 | -3.0203 | 7.1287 | 10.872 | -7.7798 | -9.8992 | -40
Producing (1 = yes) | 1 / 0 | 17 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Oil production | MMbbl | 131.0616 |  | 0 | 0 | 0 | 6.716 | 13.432 | 13.432 | 13.432 | 20.008 | 15.4041 | 11.8596 | 9.1307 | 7.0297 | 5.4122 | 4.1668 | 3.208 | 2.4699 | 1.9015 | 1.464 | 1.1271 | 0.86778 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative production | MMbbl |  | 0 | 0 | 0 | 0 | 6.716 | 20.148 | 33.58 | 47.012 | 67.02 | 82.4242 | 94.2838 | 103.4145 | 110.4443 | 115.8564 | 120.0233 | 123.2313 | 125.7012 | 127.6027 | 129.0667 | 130.1939 | 131.0616 | 131.0616 | 131.0616 | 131.0616 | 131.0616 | 131.0616 | 131.0616
Revenue | US$m | 11752.8226 |  | 0 | 0 | 0 | 559.2454 | 1057.9479 | 1137.9052 | 1111.8887 | 2415.7231 | 1195.1118 | 1200.6042 | 947.1118 | 640.2974 | 357.3285 | 301.6201 | 241.7981 | 135.123 | 147.5636 | 110.987 | 110.6272 | 81.9395 | 0 | 0 | 0 | 0 | 0 | 0
Operating cost | US$m | -2383.8014 |  | 0 | 0 | 0 | -127.308 | -214.616 | -214.616 | -214.616 | -300.1042 | -240.2539 | -194.1753 | -158.6994 | -131.3865 | -110.3584 | -94.1689 | -81.7045 | -72.1083 | -64.7201 | -59.032 | -54.6527 | -51.2811 | 0 | 0 | 0 | 0 | 0 | 0
Abandoned this year (1 = yes) | 1 / 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Abandonment | US$m | -80 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -80 | 0 | 0 | 0 | 0 | 0
Net cash flow | US$m | 8125.8485 |  | -206.1988 | -274.9317 | -206.1988 | 431.9374 | 843.3319 | 685.3675 | 659.351 | 2115.6188 | 954.8578 | 1006.4289 | 788.4124 | 508.9108 | 246.9701 | 207.4513 | 160.0936 | 63.0147 | 82.8435 | 51.955 | 55.9745 | 30.6584 | -80 | 0 | 0 | 0 | 0 | 0
Present value | US$m | 3565.478 |  | -196.6028 | -238.3065 | -162.4817 | 309.4186 | 549.2012 | 405.7549 | 354.8659 | 1035.1238 | 424.7182 | 406.9608 | 289.8213 | 170.0693 | 75.0302 | 57.2947 | 40.1957 | 14.3832 | 17.1901 | 9.8007 | 9.599 | 4.7796 | -11.3381 | 0 | 0 | 0 | 0 | 0
7 Value in this iteration
Key outputs, recorded by ModelRisk at every sample (VoseOutput). Their statistics appear on the Results sheet.
Output | Unit | Value |  | 2026: Meaning
NPV, concept A: subsea tieback | US$m | 3589.8212 |  | 2026: Sum of the present values.
NPV, concept B: standalone FPSO | US$m | 3257.8303
NPV, concept C: tieback with option to expand | US$m | 3565.478
Oil produced, concept A | MMbbl | 126.4843 |  | 2026: Compare with the recoverable volume: oil left behind.
Oil produced, concept B | MMbbl | 124.8235
Oil produced, concept C | MMbbl | 131.0616
Best concept in this iteration (1 = A, 2 = B, 3 = C) | 1 / 2 / 3 | 1 |  | 2026: The concept with the highest NPV, with hindsight.
Concept C expands? (1 = yes) | 1 / 0 | 1
8 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
Every range on the Inputs sheet is in order (no ✗ under Mean) |  | OK
No concept produces more than the recoverable volume |  | OK
Concept C's decision comes after its first oil |  | OK
Every concept spends its full capital cost (the phasing tables) |  | OK

## Results
Field Development Concept Selection | [6 empty] | ModelRisk example · Oil and gas · OG-08
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Concepts
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 Which concept? | [5 empty] | NPV of each concept — cumulative probability
Expected NPV (EMV), chance of losing money and the range of NPV, on the same simulated reservoirs and prices.
Concept | Capital | EMV | Loses money | 10th pct | 90th pct
| US$m | US$m | chance | US$m | US$m
A Subsea tieback | 650 | 2379.4503 | 0.35% | 938.3961 | 3961.7976
B Standalone FPSO | 1500 | 2151.533 | 9.089% | 51.384 | 4706.1786
C Tieback with option to expand | 650 | 2663.9886 | 0.35% | 917.261 | 4809.7072
Highest EMV |  | C Tieback with option to expand
Concept C's capital is phase 1 only; its second phase (Inputs sheet) is spent only if the option is exercised.
2 Which concept turns out best?
Share of simulated futures in which each concept has the highest NPV, with hindsight.
Best concept in hindsight |  | Probability
A Subsea tieback |  | 62.46%
B Standalone FPSO |  | 12.39%
C Tieback with option to expand |  | 25.15%
Total |  | 100%
3 The value of flexibility
What the option to expand is worth, and what it does with the oil.
Measure | Unit | Value
Value of the option: EMV of C − EMV of A | US$m | 284.5383
EMV of C − EMV of B | US$m | 512.4556
Chance that concept C expands | probability | 60.42%
Mean recoverable volume | MMbbl | 137.7844
Mean oil produced, A (tieback) | MMbbl | 106.0548
Mean oil produced, B (FPSO) | MMbbl | 129.1956
Mean oil produced, C (tieback with option) | MMbbl | 130.1481
4 What drives the value of the flexible concept | [5 empty] | What drives the NPV of concept C (US$m)
Lowest and highest mean NPV of concept C over ten equal groups of each input (VoseSimSensitivityMean), drawn from the overall mean.
Input (ranked by influence) | Lowest mean | Highest mean | Rank
Recoverable volume | 937.8914 | 5153.5758 | 1
Volume estimate at decision | 1031.7157 | 4992.6393 | 2
Long-term oil price | 1963.2301 | 3484.3561 | 3
Deliverability | 2524.1831 | 2779.1698 | 4
Capex overrun factor | 2559.6975 | 2804.8778 | 5
Host remaining life | 2583.2479 | 2746.3584 | 6
FPSO delay | 2661.0155 | 2671.0973 | 7
5 How to read these results
• The tieback is cheap and rarely loses money, but its capacity and the host's life cap what it can produce: a large reservoir is left partly in the ground. The FPSO can produce a large reservoir, but its cost makes a loss likely if the reservoir is small.
• The tieback with an option to expand keeps the tieback's protection on the downside and captures much of the FPSO's upside: it spends the extra capital only when the reservoir has shown that it deserves it. The difference in EMV is the value of that flexibility.
• The concept that is best most often is not necessarily the one with the highest EMV: EMV also counts how much a concept wins by. With hindsight the option is sometimes exercised when it should not have been, because the volume estimate has an error; it is still worth having.
• All three concepts are evaluated on the same reservoir and price in every iteration (common random numbers), so the differences between them are real, not sampling noise.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | NPV_A | NPV_B | NPV_C
1% | 99% | 199.3608 | -780.57 | 181.564
3% | 97% | 498.0239 | -474.7879 | 478.2679
5% | 95% | 656.4681 | -273.6723 | 634.7228
7% | 93% | 800.9249 | -124.1597 | 776.4215
9% | 91% | 896.7356 | -12.4676 | 877.1945
11% | 89% | 980.0582 | 103.0024 | 956.1889
13% | 87% | 1075.3783 | 199.1484 | 1043.1727
15% | 85% | 1155.7865 | 271.7346 | 1129.4403
17% | 83% | 1226.0563 | 375.933 | 1200.3037
19% | 81% | 1307.6555 | 471.8685 | 1275.7627
21% | 79% | 1383.6138 | 563.9725 | 1354.6338
23% | 77% | 1447.8983 | 646.3556 | 1421.8538
25% | 75% | 1512.6683 | 727.9221 | 1490.4565
27% | 73% | 1577.1396 | 808.1304 | 1557.9485
29% | 71% | 1634.6419 | 888.4726 | 1617.8352
31% | 69% | 1698.2495 | 963.362 | 1686.4918
33% | 67% | 1756.5591 | 1048.109 | 1756.5591
35% | 65% | 1817.0753 | 1128.0114 | 1824.2933
37% | 63% | 1874.5643 | 1218.874 | 1888.3057
39% | 61% | 1927.2562 | 1303.9443 | 1953.8473
41% | 59% | 1988.618 | 1390.0934 | 2023.7039
43% | 57% | 2056.8877 | 1481.7739 | 2095.4967
45% | 55% | 2115.6059 | 1568.8205 | 2177.2038
47% | 53% | 2177.8981 | 1648.3473 | 2249.788
49% | 51% | 2235.6954 | 1743.6482 | 2321.5895
51% | 49% | 2302.6926 | 1830.9186 | 2398.7509
53% | 47% | 2362.7598 | 1918.3377 | 2474.3233
55% | 45% | 2428.5295 | 2024.364 | 2556.9623
57% | 43% | 2486.4007 | 2117.8524 | 2634.7794
59% | 41% | 2544.1487 | 2227.5205 | 2720.1364
61% | 39% | 2607.8962 | 2334.1367 | 2804.6942
63% | 37% | 2675.3674 | 2447.3622 | 2888.3041
65% | 35% | 2744.5219 | 2560.6974 | 2971.7081
67% | 33% | 2808.6206 | 2671.2568 | 3068.6572
69% | 31% | 2874.9023 | 2802.064 | 3173.2481
71% | 29% | 2948.5372 | 2918.3824 | 3286.2434
73% | 27% | 3026.5877 | 3068.4683 | 3398.6186
75% | 25% | 3115.5341 | 3210.1778 | 3530.7477
77% | 23% | 3203.7906 | 3368.8212 | 3648.8595
79% | 21% | 3301.3483 | 3542.312 | 3788.3587
81% | 19% | 3393.9854 | 3704.4291 | 3927.3673
83% | 17% | 3500.6376 | 3902.7997 | 4071.3696
85% | 15% | 3604.2405 | 4117.2286 | 4268.1936
87% | 13% | 3730.9222 | 4345.0851 | 4470.0536
89% | 11% | 3884.8113 | 4579.6055 | 4676.9561
91% | 9% | 4052.1067 | 4887.227 | 4959.1608
93% | 7% | 4248.3036 | 5305.6652 | 5322.9122
95% | 5% | 4488.6981 | 5845.8505 | 5747.1301
97% | 3% | 4837.9727 | 6554.7997 | 6383.8291
99% | 1% | 5611.5712 | 8019.0699 | 7714.5099
Outcome helper: Best | Below | Cumulative
A Subsea tieback | 1.5 | 62.46%
B Standalone FPSO | 2.5 | 74.85%
Overall mean of NPV_C |  | 2663.9886
Ranked input (chart) |  |  |  | Highest − mean | Lowest − mean
Recoverable volume |  |  |  | 2489.5872 | -1726.0972
Volume estimate at decision |  |  |  | 2328.6506 | -1632.2729
Long-term oil price |  |  |  | 820.3675 | -700.7586
Deliverability |  |  |  | 115.1812 | -139.8055
Capex overrun factor |  |  |  | 140.8892 | -104.2911
Host remaining life |  |  |  | 82.3698 | -80.7407
FPSO delay |  |  |  | 7.1086 | -2.9731

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
419
822
449
204
59
29
11
3
1
3
111
492
623
482
192
73
21
4
0
2
329
759
493
272
99
32
11
4
0
1
349
848
504
202
67
21
8
0
0
1
34
117
233
305
363
376
344
144
66
18
259
693
565
280
108
51
31
7
3
3
271
618
546
313
132
63
38
11
7
1
1225
0
0
0
252
0
0
0
0
523
774
0
0
0
0
0
0
0
0
1226
314
760
534
230
92
42
17
7
2
2
40
132
239
309
350
326
274
179
120
31
56
169
328
380
348
311
215
124
55
14
162
309
419
376
295
230
120
64
22
3
68
197
289
357
354
262
227
155
74
17
1402
0
0
0
0
0
0
0
0
598