## About
Cost Estimate with Contingency |  | ModelRisk example · Projects and construction · PC-01
How much contingency does the warehouse budget need? Three-point estimates turned into a P50 and a P80 budget.
Next: Inputs ▸
Model card
Industry | Projects and construction
Difficulty | ★☆☆☆☆ Twelve cost items with three-point ranges added up by simulation: the simplest useful risk model.
Business question | The cost plan for a new distribution warehouse adds up to US$36.8 million using the most likely cost of each item. How likely is that figure to be enough, and how much contingency is needed for a budget with an 80% chance of not being exceeded?
Who it is for | Cost estimators, quantity surveyors, project managers and the sponsors who approve budgets.
Main outputs | Total cost: P50, P80 and P90, the chance that the base estimate is enough, the contingency needed for a P80 budget, and which items drive the range.
ModelRisk techniques | PERT distributions from low, most likely and high estimates · simulation of the total · P50 / P80 / P90 · contingency from percentiles · one correlation for every pair of items through a Normal copula (VoseCopulaMultiNormal) · conditional-mean tornado to rank the cost items.
File | PC-01 Cost estimate with three-point ranges and contingency · Version 1.0 · October 2026 · built with ModelRisk 10
The business question
The estimator's cost plan for a new 40,000 m² distribution warehouse has twelve items. For each one the team has agreed a lowest plausible cost, a most likely cost and a highest plausible cost. Adding up the most likely costs gives the base estimate of US$36.8 million — but the ranges are not symmetric: most items can overrun by more than they can underrun, so the base estimate is likely to be too low. The model replaces each item by a PERT distribution built from its three estimates, adds them up by simulation, and reads off the budget at the confidence level the sponsor wants. The difference between that budget and the base estimate is the contingency, and the ranking of the items shows where better estimates would narrow the range most.
How the model works
Three sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | For each item, the lowest, most likely and highest plausible cost, with the basis of the estimate. Each becomes a PERT distribution: most likely values carry the most weight, extremes are possible but rare. One correlation says how strongly the items' costs move together: 0, independent, as shipped.
2 Estimate | The base estimate is the sum of the most likely costs. In each iteration a Normal copula draws twelve U values with that correlation between every pair, each item's PERT turns its U into a cost, and the total is their sum.
3 Results | The total cost's percentiles: P80 is the budget with an 80% chance of not being exceeded. The contingency is that budget minus the base estimate. The tornado ranks the items by how much they drive the total.
How to use it
Step 1 | Replace the twelve items and their three estimates with your own on the Inputs sheet (the model holds exactly twelve; ask for the high estimate first, then the low, then the most likely: it reduces anchoring).
Step 2 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set).
Step 3 | Read the P50, P80 and P90 on the Results sheet and choose the confidence level for the budget.
Step 4 | Work on the items at the top of the tornado first: better information there narrows the range most.
Workbook map
Inputs | The twelve cost items with their low, most likely and high estimates.
Estimate | Base estimate, mean and this iteration's value of every item; totals and checks.
Results | Budget percentiles, contingency, S-curve, and the items that drive the range.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Money | US$ million (US$m), at today's prices, excluding inflation and VAT.
P50 / P80 / P90 | The cost with a 50%, 80% and 90% chance of not being exceeded.
Contingency | Budget at the chosen confidence level minus the base estimate (the sum of the most likely costs).
Base estimate | The single-number estimate that adds up most likely values.
Key assumptions and limitations
Independence | Items are independent as shipped (correlation 0). In reality some move together (labour rates, a longer programme); raise the correlation on the Inputs sheet to see how much that widens the range.
Scope | Only estimating uncertainty within the agreed scope: no risk events (see PC-02) and no scope change.
Distributions | PERT from the three estimates; the low and high are treated as true minimum and maximum.
Data | The project and all costs are invented for this example.
ModelRisk functions used
VosePERT | Each item's cost from its low, most likely and high estimates, and its U value.
VoseCopulaMultiNormal | Twelve U values in each iteration, one per item, from the correlation matrix on the Estimate sheet.
VoseInput, VoseOutput | Name the twelve items and the total for the Results Viewer and the sensitivity analysis.
VoseSimMean, VoseSimPercentile, VoseSimProbability | Statistics of the simulation for the tables and charts on the Results sheet.
VoseSimSensitivityMean | The tornado chart: every VoseInput ranked by how far the mean total cost moves across its range.
Further reading
Cost risk | AACE International (2008). Recommended Practice 41R-08: Risk Analysis and Contingency Determination Using Range Estimating.
Expert estimates | Vose, D. (2008). Risk Analysis: A Quantitative Guide, 3rd edition. Wiley — chapter on eliciting expert opinion.
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Cost Estimate with Contingency | [7 empty] | ModelRisk example · Projects and construction · PC-01
INPUTS · Every assumption the model uses, with its uncertainty and its basis. Change only the yellow cells.
◂ About | [7 empty] | Next: Estimate ▸
How to read this sheet: yellow cells are inputs. Orange cells hold ModelRisk distributions and show the current random sample (press F9 to draw again). Low / Most likely / High are the minimum, most likely and maximum for PERT. Mean is the distribution's average (VoseMean); it shows ✗ if a range is out of order.
1 Site and substructure
Below ground and around the building: where ground conditions bring the most uncertainty.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Site preparation and earthworks | US$m | 2.2661 | PERT · correlated | 1.8 | 2.2 | 3.2 | 2.3 | Ground investigation found variable fill on the north side.
Foundations and ground-floor slab | US$m | 4.9803 | PERT · correlated | 4 | 4.6 | 6 | 4.7333 | Piling may be needed under the high-bay area.
Drainage and external works | US$m | 1.7484 | PERT · correlated | 1.2 | 1.5 | 2.1 | 1.55 | Attenuation tank sized by the local authority.
2 Building
The frame and envelope: mostly quoted prices.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Steel frame | US$m | 7.6948 | PERT · correlated | 6.5 | 7.2 | 8.8 | 7.35 | Steel price quoted, valid for 60 days.
Cladding and roofing | US$m | 4.446 | PERT · correlated | 3.8 | 4.3 | 5.4 | 4.4 | Two subcontract quotes; the higher includes rooflights.
Loading docks and doors | US$m | 1.3651 | PERT · correlated | 1.1 | 1.3 | 1.7 | 1.3333 | 24 dock levellers, specification agreed.
3 Services and fit-out
Services design is least advanced, so its ranges are widest.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Mechanical and electrical services | US$m | 6.4064 | PERT · correlated | 4.5 | 5.2 | 7 | 5.3833 | Design at stage 2; the power connection cost is not yet confirmed.
Sprinklers and fire protection | US$m | 1.0707 | PERT · correlated | 1 | 1.2 | 1.6 | 1.2333 | Insurer's requirements still to be confirmed.
Racking and warehouse fit-out | US$m | 3.2291 | PERT · correlated | 2.8 | 3.1 | 3.9 | 3.1833 | Client's layout, supplier's budget price.
Offices and staff amenities | US$m | 1.5425 | PERT · correlated | 1.4 | 1.6 | 2.1 | 1.65 | Two-storey office block, standard finish.
4 Preliminaries and fees
Time-related site costs and fees.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Preliminaries and site management | US$m | 2.9904 | PERT · correlated | 2.5 | 2.8 | 3.6 | 2.8833 | Time-related: a longer build costs more. The programme is not modelled here, so this is a range of its own.
Design and professional fees | US$m | 1.7812 | PERT · correlated | 1.6 | 1.8 | 2.2 | 1.8333 | Percentage fees on the construction cost, entered here as a range of their own.
5 How the costs move together
One correlation for every pair of items.
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Correlation between any two items' costs | 0 – 1 | 0 | Fixed |  |  |  |  | 0 = independent, as most cost plans assume. A shared cause, such as a longer programme or a tight labour market, makes costs move together: try 0.3 and simulate again.

## Estimate
Cost Estimate with Contingency | [12 empty] | ModelRisk example · Projects and construction · PC-01
ESTIMATE · The base estimate, the expected cost and this iteration's cost of every item (US$m); how the items move together.
◂ Inputs | [12 empty] | Next: Results ▸
1 Cost items
Base = most likely cost. Mean = the PERT's mean (Inputs). Copula draw: the U value that item's PERT turns into its cost.
No. | Item | Base | Mean | This iteration | Mean − base | Copula draw
|  | most likely | PERT | sampled | skew | U, 0 – 1
1 | Site preparation and earthworks | 2.2 | 2.3 | 2.2661 | 0.1 | 0.48513
2 | Foundations and ground-floor slab | 4.6 | 4.7333 | 4.9803 | 0.13333 | 0.74548
3 | Drainage and external works | 1.5 | 1.55 | 1.7484 | 0.05 | 0.86586
4 | Steel frame | 7.2 | 7.35 | 7.6948 | 0.15 | 0.78284
5 | Cladding and roofing | 4.3 | 4.4 | 4.446 | 0.1 | 0.58306
6 | Loading docks and doors | 1.3 | 1.3333 | 1.3651 | 0.033333 | 0.62351
7 | Mechanical and electrical services | 5.2 | 5.3833 | 6.4064 | 0.18333 | 0.98308
8 | Sprinklers and fire protection | 1.2 | 1.2333 | 1.0707 | 0.033333 | 0.058379
9 | Racking and warehouse fit-out | 3.1 | 3.1833 | 3.2291 | 0.083333 | 0.61397
10 | Offices and staff amenities | 1.6 | 1.65 | 1.5425 | 0.05 | 0.22611
11 | Preliminaries and site management | 2.8 | 2.8833 | 2.9904 | 0.083333 | 0.70961
12 | Design and professional fees | 1.8 | 1.8333 | 1.7812 | 0.033333 | 0.35514
| Total | 36.8 | 37.8333 | 39.5208 | 1.0333
This iteration: the cost drawn on the Inputs sheet, with the item's copula draw as its U.
Mean − base above 0: the item can overrun by more than it can underrun.
Copula draw: VoseCopulaMultiNormal with the correlation matrix in section 2.
2 How the items move together
The correlation matrix the copula reads: 1 on the diagonal, and the correlation on the Inputs sheet for every pair (0 as shipped: independent).
No. | Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Site preparation and earthworks | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Foundations and ground-floor slab | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Drainage and external works | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Steel frame | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Cladding and roofing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Loading docks and doors | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
7 | Mechanical and electrical services | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
8 | Sprinklers and fire protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
9 | Racking and warehouse fit-out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
10 | Offices and staff amenities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
11 | Preliminaries and site management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
12 | Design and professional fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
3 Value in this iteration
Key outputs, recorded by ModelRisk at every sample (VoseOutput). Their statistics appear on the Results sheet.
| Output | Unit | Value |  | Meaning
| Total cost | US$m | 39.5208 |  | Sum of this iteration's twelve item costs.
| Base estimate | US$m | 36.8 |  | Sum of the most likely costs.
| Expected cost (sum of the PERT means) | US$m | 37.8333 |  | The mean of the total, calculated exactly.
4 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
| Every range on the Inputs sheet is in order (no ✗ under Mean) |  | OK
| The correlation is at least 0 and below 1 |  | OK

## Results
Cost Estimate with Contingency | [6 empty] | ModelRisk example · Projects and construction · PC-01
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Estimate
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 The budget | [5 empty] | Total cost — S-curve
P80 = the cost with an 80% chance of not being exceeded.
Measure | Unit | Value
Base estimate (sum of the most likely costs) | US$m | 36.8
P80 budget | US$m | 38.602
Contingency for a P80 budget | US$m | 1.802
Contingency as a share of the base estimate |  | 4.897%
Chance that the base estimate is enough | probability | 12.47%
Mean total cost | US$m | 37.8303
2 Budget at other confidence levels
Choose the confidence level, then read the budget.
Measure | Unit | P50 | P80 | P90 | Mean
Total cost | US$m | 37.81 | 38.602 | 38.9937 | 37.8303
Expected cost, calculated exactly (check) | US$m |  |  |  | 37.8333
3 Which items drive the range | [5 empty] | Which items drive the total cost (US$m)
Lowest and highest mean total over ten equal groups of each item (VoseSimSensitivityMean): estimate the top items more carefully first.
Input (ranked by influence) | Lowest mean | Highest mean | Rank
Mechanical and electrical services | 37.1247 | 38.6641 | 1
Steel frame | 37.233 | 38.5998 | 2
Foundations and ground-floor slab | 37.3103 | 38.4774 | 3
Cladding and roofing | 37.3878 | 38.3233 | 4
Site preparation and earthworks | 37.4189 | 38.3202 | 5
Preliminaries and site management | 37.5133 | 38.2522 | 6
Racking and warehouse fit-out | 37.5536 | 38.2006 | 7
Drainage and external works | 37.5847 | 38.1626 | 8
Offices and staff amenities | 37.6431 | 38.0085 | 9
Loading docks and doors | 37.6472 | 38.0118 | 10
Design and professional fees | 37.6644 | 38.0066 | 11
Sprinklers and fire protection | 37.6715 | 37.9657 | 12
4 How to read these results
• The base estimate adds up most likely costs. Because most items can overrun by more than they can underrun, the sum of the most likely values sits below the middle of the range, and the chance that it is enough is low.
• The contingency is not a guess or a fixed percentage: it is the difference between the budget at the chosen confidence level and the base estimate. Sponsors often fund the P50 and hold the step to the P80 as a management reserve.
• As shipped the items are independent (correlation 0 on the Inputs sheet), which lets overruns on some items cancel underruns on others. When costs move together — a longer programme, a tight labour market — the range is wider: at a correlation of 0.3 the P80 contingency rises to about 6.7% of the base estimate (US$2.5 million), and the tornado's bars even out, because each item then carries the others that move with it. PC-02 adds risk events such as a delayed power connection.
• The items at the top of the tornado are where the range comes from: a firmer price or more design there narrows the budget more than anywhere else.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | TotalCost
1% | 99% | 35.857
3% | 97% | 36.1767
5% | 95% | 36.3803
7% | 93% | 36.513
9% | 91% | 36.6285
11% | 89% | 36.7384
13% | 87% | 36.8197
15% | 85% | 36.9048
17% | 83% | 36.9686
19% | 81% | 37.0268
21% | 79% | 37.0978
23% | 77% | 37.1518
25% | 75% | 37.2116
27% | 73% | 37.2651
29% | 71% | 37.3207
31% | 69% | 37.3676
33% | 67% | 37.4125
35% | 65% | 37.4574
37% | 63% | 37.5044
39% | 61% | 37.55
41% | 59% | 37.5975
43% | 57% | 37.6467
45% | 55% | 37.6907
47% | 53% | 37.7393
49% | 51% | 37.7866
51% | 49% | 37.8323
53% | 47% | 37.8764
55% | 45% | 37.9241
57% | 43% | 37.9719
59% | 41% | 38.0171
61% | 39% | 38.0728
63% | 37% | 38.1196
65% | 35% | 38.1658
67% | 33% | 38.2218
69% | 31% | 38.276
71% | 29% | 38.3283
73% | 27% | 38.3829
75% | 25% | 38.4444
77% | 23% | 38.5057
79% | 21% | 38.572
81% | 19% | 38.6377
83% | 17% | 38.7051
85% | 15% | 38.7748
87% | 13% | 38.856
89% | 11% | 38.939
91% | 9% | 39.0459
93% | 7% | 39.1706
95% | 5% | 39.335
97% | 3% | 39.549
99% | 1% | 39.9557
Overall mean of TotalCost |  | 37.8303
Ranked input (chart) |  |  |  | Highest − mean | Lowest − mean
Mechanical and electrical services |  |  |  | 0.8338 | -0.70558
Steel frame |  |  |  | 0.76959 | -0.59727
Foundations and ground-floor slab |  |  |  | 0.64718 | -0.51996
Cladding and roofing |  |  |  | 0.49303 | -0.44245
Site preparation and earthworks |  |  |  | 0.48995 | -0.41137
Preliminaries and site management |  |  |  | 0.42199 | -0.31691
Racking and warehouse fit-out |  |  |  | 0.37035 | -0.27666
Drainage and external works |  |  |  | 0.33231 | -0.24555
Offices and staff amenities |  |  |  | 0.17827 | -0.18713
Loading docks and doors |  |  |  | 0.18154 | -0.18304
Design and professional fees |  |  |  | 0.17634 | -0.16589
Sprinklers and fire protection |  |  |  | 0.13542 | -0.15874

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
4
23
132
322
491
485
333
164
39
7
102
240
310
355
307
271
205
115
64
31
126
278
366
368
330
219
176
96
27
14
92
240
374
355
346
239
192
103
46
13
91
280
342
359
328
257
182
92
49
20
103
208
353
390
309
260
184
128
46
19
90
241
329
365
343
267
194
98
52
21
125
304
343
367
286
233
184
96
47
15
91
237
318
353
328
300
197
100
62
14
131
287
371
365
335
219
148
89
44
11
112
308
371
365
341
235
153
80
31
4
125
332
384
380
319
202
145
75
34
4
84
232
282
342
344
285
210
135
65
21