## About
Risk Register: Threats and Opportunities |  | ModelRisk example · Projects and construction · PC-02
How much risk contingency does the hospital extension need? The risk register, quantified in cost and time.
Next: Inputs ▸
Model card
Industry | Projects and construction
Difficulty | ★★☆☆☆ A risk register turned into a simulation: risk events with linked cost and schedule impacts.
Business question | The project's risk register lists twelve threats and three opportunities, each with a probability and a cost and schedule impact. How much contingency is needed to cover them with 80% confidence, how likely is the project to finish within its float, and which risks matter most?
Who it is for | Project managers, risk managers, cost managers and project sponsors.
Main outputs | Risk contingency at the chosen confidence level against the register's expected value · total risk cost including the cost of the delay beyond the float · delay and the chance of finishing within the programme float · the risks that drive the exposure.
ModelRisk techniques | Risk events as two draws: whether the risk happens (VoseBernoulli) and how bad it is (VoseUniform), shared by its cost and its delay (the U argument of VosePERT), so that they happen together and a bad case is bad in both · opportunities as negative impacts · time-related cost beyond the float · tornado ranking of the risks.
File | PC-02 Risk register threats and opportunities · Version 1.0 · October 2026 · built with ModelRisk 10
The business question
The hospital extension has a base estimate of US$85 million and a 104-week programme with eight weeks of float. Like every project, it keeps a risk register: contaminated ground, a gas main to divert, design changes, asbestos, a tight labour market, and a few opportunities such as value engineering the façade. Each entry has a probability and a range of cost and time if it happens. Adding up probability × impact gives the register's expected value, but a contingency equal to that average is not enough most of the time, because in any given project some risks happen in full and others not at all. The model turns each entry into a risk event, links its cost and its delay so that they happen together, adds the cost of delay, and simulates the register to give the contingency at the sponsor's confidence level and the chance of finishing on time.
How the model works
Three sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | The base cost and programme the risks are added to, the float in the programme, what a week of delay costs (site overheads, preliminaries, inflation), and the confidence level at which the contingency is set.
2 Register | Each risk has a probability and three-point ranges for its cost and its delay; opportunities have negative impacts. In every iteration VoseBernoulli decides whether each risk happens and VoseUniform how bad it is: the same draw places both its cost and its delay in their ranges (the U argument of VosePERT), so a large cost goes with a long delay. Delays are added as if each hit the critical path.
3 Results | The total risk cost — direct cost plus the cost of the delay beyond the float — at the chosen confidence level, compared with the register's expected value; the delay against the float; and the tornado of the risks that drive the total.
How to use it
Step 1 | Replace the register on the Register sheet with your own risks: probability, cost range and delay range.
Step 2 | Set the base cost and programme, the float, the cost of a week of delay and the confidence level on the Inputs sheet.
Step 3 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set).
Step 4 | Use the tornado to decide where risk responses pay off, then update the register and simulate again.
Workbook map
Inputs | Base cost and programme, float, cost of delay, contingency confidence level.
Register | The fifteen risks with their ranges and expected values; this iteration's outcome; totals and checks.
Results | Risk contingency, S-curve, schedule outlook and the ranking of the risks.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Money | US$ million (US$m).
Time | Weeks of delay to completion; the programme's float absorbs the first weeks.
Threats and opportunities | Threats have positive impacts (more cost, more time); opportunities negative ones.
Expected value | Probability × mean impact, summed over the register: the average, not a contingency.
Key assumptions and limitations
Critical path | Every delay is added to completion, as if all risks hit the critical path: the schedule results are an upper bound. PC-03 uses network logic instead.
Independence | Risks are independent of each other; within a risk, cost and delay are fully linked.
Cost of delay | Only weeks beyond the float cost money: the float absorbs the first weeks and their time-related cost. Each week beyond it costs the same, whatever causes it.
Data | The project, the register and all figures are invented for this example.
ModelRisk functions used
VoseBernoulli | Whether each risk happens.
VoseUniform, VosePERT | How bad it is: one draw, passed as the U argument of the cost and the delay PERTs so that they move together.
VoseInput, VoseOutput | Name each risk's cost and the totals for the Results Viewer and the sensitivity analysis.
VoseSimMean, VoseSimPercentile | Statistics of the simulation for the tables and charts on the Results sheet.
VoseSimSensitivityMean | The tornado chart: every risk ranked by how far the mean total risk cost moves across the range of its cost.
Further reading
Risk registers | Hillson, D. and Simon, P. (2020). Practical Project Risk Management: The ATOM Methodology, 3rd edition. Berrett-Koehler.
Contingency | AACE International (2011). Recommended Practice 65R-11: Integrated Cost and Schedule Risk Analysis and Contingency Determination Using Expected Value.
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Risk Register: Threats and Opportunities |  |  |  | ModelRisk example · Projects and construction · PC-02
INPUTS · The base estimate, the float, the cost of delay and the confidence level. The risk register itself is on the Register sheet. Change only the yellow cells.
◂ About |  |  |  | Next: Register ▸
How to read this sheet: yellow cells are inputs.
1 Project
The base the risks are added to.
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
Base estimate (without risk contingency) | US$m | 85 | Fixed | Approved cost plan, stage 4.
Float in the programme | weeks | 8 | Fixed | Time contingency already in the 104-week programme.
Cost of a week of delay beyond the float | US$m per week | 0.12 | Fixed | Preliminaries, site overheads and inflation on the remaining work.
2 Contingency policy
The confidence level the sponsor wants for the risk contingency.
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
Confidence level for the contingency | probability | 80% | Fixed | P80 is common for public-sector projects at business-case stage.

## Register
Risk Register: Threats and Opportunities | [11 empty] | ModelRisk example · Projects and construction · PC-02
REGISTER · Fifteen risks with their probabilities and impacts, and what happens to each in this iteration.
◂ Inputs | [11 empty] | Next: Results ▸
1 The risk register
Yellow cells are inputs. Opportunities have negative impacts (savings).
ID | Risk | Probability | Cost if it happens (US$m) |  |  | Delay (weeks) |  |  | Expected | Expected | Kind | Owner · response
|  |  | Low | Most likely | High | Low | Most likely | High | cost | delay
T1 | Contaminated ground found during excavation | 30% | 0.4 | 0.9 | 2.5 | 1 | 3 | 8 | 0.325 | 1.05 | threat | Contractor · extra boreholes before tender
T2 | Gas main diversion takes longer than planned | 40% | 0.2 | 0.5 | 1.2 | 2 | 4 | 10 | 0.22667 | 1.8667 | threat | Client · early engagement with the utility
T3 | Client design changes after stage 4 | 60% | 0.5 | 1.5 | 4 | 1 | 3 | 8 | 1.05 | 2.1 | threat | Client · design freeze and change control
T4 | Asbestos in the existing building | 35% | 0.3 | 0.8 | 2 | 1 | 2 | 6 | 0.32083 | 0.875 | threat | Contractor · refurbishment survey
T5 | Medical equipment prices rise | 50% | 0.4 | 1 | 2.5 | 0 | 0 | 0 | 0.575 | 0 | threat | Client · fix prices with the supplier
T6 | Planning condition adds archaeological works | 20% | 0.1 | 0.3 | 0.8 | 2 | 4 | 12 | 0.07 | 1 | threat | Client · desk study now
T7 | Shortage of mechanical and electrical labour | 45% | 0.3 | 0.9 | 2.2 | 2 | 5 | 12 | 0.4575 | 2.55 | threat | Contractor · early subcontract award
T8 | Wet winter stops groundworks | 35% | 0.1 | 0.3 | 0.7 | 1 | 3 | 6 | 0.11667 | 1.1083 | threat | Contractor · sequence groundworks for summer
T9 | Key subcontractor becomes insolvent | 8% | 1 | 2.5 | 6 | 4 | 8 | 20 | 0.22667 | 0.74667 | threat | Contractor · financial checks, bonds
T10 | Defects found in commissioning the medical gases | 25% | 0.2 | 0.5 | 1.5 | 1 | 2 | 6 | 0.15417 | 0.625 | threat | Contractor · witness testing
T11 | Hospital operations restrict working hours | 50% | 0.2 | 0.6 | 1.5 | 1 | 3 | 8 | 0.34167 | 1.75 | threat | Client · agree working windows
T12 | Fire strategy needs re-approval | 20% | 0.1 | 0.4 | 1 | 1 | 3 | 8 | 0.09 | 0.7 | threat | Designer · early building-control review
O1 | Value engineering of the façade | 50% | -1.2 | -0.8 | -0.3 | 0 | 0 | 0 | -0.39167 | 0 | opportunity | Designer · alternative cladding system
O2 | Early access to the site compound | 30% | -0.4 | -0.2 | -0.1 | -3 | -2 | -1 | -0.065 | -0.6 | opportunity | Client · negotiate with the estates team
O3 | Framework bulk-purchase agreement | 40% | -0.6 | -0.4 | -0.2 | 0 | 0 | 0 | -0.16 | 0 | opportunity | Contractor · use the regional framework
| Expected value of the register | [7 empty] | 3.3375 | 13.7717
2 This iteration
Whether each risk happens, and how bad it is: one draw places both its cost and its delay in their ranges, so a large cost goes with a long delay.
ID | Risk | Happens? | How bad | Cost | Delay | [6 empty] | How it is calculated
|  | 1 = yes | 0 – 1 | US$m | weeks
T1 | Contaminated ground found during excavation | 0 | 0.85192 | 0 | 0 | [6 empty] | Happens?: VoseBernoulli(probability). How bad: VoseUniform(0, 1), the percentile within the ranges
T2 | Gas main diversion takes longer than planned | 0 | 0.94531 | 0 | 0 | [6 empty] | Cost = happens × VosePERT(low, most likely, high, how bad); the delay the same, with the same draws
T3 | Client design changes after stage 4 | 1 | 0.29357 | 1.3339 | 2.6678 | [6 empty] | A range with low = high is a fixed impact: no PERT needed (a risk with no delay has low = high = 0)
T4 | Asbestos in the existing building | 1 | 0.053113 | 0.4636 | 1.3057
T5 | Medical equipment prices rise | 1 | 0.22969 | 0.83146 | 0
T6 | Planning condition adds archaeological works | 0 | 0.46225 | 0 | 0
T7 | Shortage of mechanical and electrical labour | 1 | 0.9434 | 1.6123 | 8.8011
T8 | Wet winter stops groundworks | 0 | 0.9806 | 0 | 0
T9 | Key subcontractor becomes insolvent | 0 | 0.22302 | 0 | 0
T10 | Defects found in commissioning the medical gases | 0 | 0.51886 | 0 | 0
T11 | Hospital operations restrict working hours | 1 | 0.69936 | 0.80648 | 4.1467
T12 | Fire strategy needs re-approval | 0 | 0.89951 | 0 | 0
O1 | Value engineering of the façade | 0 | 0.43512 | 0 | 0
O2 | Early access to the site compound | 0 | 0.079956 | 0 | 0
O3 | Framework bulk-purchase agreement | 0 | 0.37135 | 0 | 0
| Total | 5 |  | 5.0477 | 16.9213
3 Value in this iteration
Key outputs, recorded by ModelRisk at every sample (VoseOutput). Their statistics appear on the Results sheet.
| Output | Unit | Value | [8 empty] | Meaning
| Direct risk cost | US$m | 5.0477 | [8 empty] | Sum of the risks' cost impacts.
| Delay | weeks | 16.9213 | [8 empty] | Sum of the delays, as if each hit the critical path.
| Weeks late (beyond the float) | weeks | 8.9213 | [8 empty] | The float absorbs the first weeks of delay.
| Cost of the delay beyond the float | US$m | 1.0706 | [8 empty] | Weeks late × cost of a week: the float absorbs the rest.
| Total risk cost | US$m | 6.1183 | [8 empty] | What the risk contingency has to cover.
| Finishes within the float? (1 = yes) | 1 / 0 | 0
| Number of threats that happen | risks | 5
4 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
| Probabilities are between 0% and 100% |  | OK

## Results
Risk Register: Threats and Opportunities | [6 empty] | ModelRisk example · Projects and construction · PC-02
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Register
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 Risk contingency | [5 empty] | Total risk cost — S-curve
The total risk cost — direct cost plus the cost of delay — at the confidence level on the Inputs sheet.
Measure | Unit | Value
Register's expected value, with the average delay beyond the float | US$m | 4.0301
Mean total risk cost (simulated) | US$m | 4.1161
Risk contingency at the chosen confidence level | US$m | 6.054
Confidence level (Inputs sheet) |  | 80%
Contingency above the expected value | US$m | 2.0239
Budget: base estimate + contingency | US$m | 91.054
2 Cost and schedule ranges
P50 / P80 / P90: a 50%, 80% and 90% chance of not being exceeded.
Measure | Unit | P50 | P80 | P90 | Mean
Total risk cost | US$m | 3.9391 | 6.054 | 7.3375 | 4.1161
Direct risk cost | US$m | 3.2524 | 4.8205 | 5.755 | 3.3394
Delay | weeks | 13.4379 | 19.3614 | 22.7182 | 13.8357
Weeks late (beyond the float) | weeks | 5.4379 | 11.3614 | 14.7182 | 6.4727
Number of threats that happen | risks | 4 | 5 | 6 | 4.1886
Measure | Unit | Value
Chance of finishing within the float | probability | 20.18%
3 Which risks matter | [5 empty] | Which risks drive the total risk cost (US$m)
Lowest and highest mean total over ten equal groups of each risk's cost (VoseSimSensitivityMean): where a response pays off most.
Input (ranked by influence) | Lowest mean | Highest mean | Rank
T9 Key subcontractor becomes insolvent | 3.8104 | 7.7094 | 1
T3 Client design changes after stage 4 | 2.9146 | 6.1294 | 2
T7 Shortage of mechanical and electrical labour | 3.4233 | 5.727 | 3
T1 Contaminated ground found during excavation | 3.7154 | 5.6028 | 4
T5 Medical equipment prices rise | 3.5853 | 5.2222 | 5
T4 Asbestos in the existing building | 3.7042 | 5.3295 | 6
T2 Gas main diversion takes longer than planned | 3.6782 | 5.1935 | 7
T11 Hospital operations restrict working hours | 3.5839 | 5.0863 | 8
T10 Defects found in commissioning the medical gases | 3.93 | 5.0517 | 9
T12 Fire strategy needs re-approval | 3.9573 | 5.0187 | 10
T6 Planning condition adds archaeological works | 3.9523 | 5.0109 | 11
T8 Wet winter stops groundworks | 3.8842 | 4.8593 | 12
O1 Value engineering of the façade | 3.6111 | 4.4069 | 13
O3 Framework bulk-purchase agreement | 3.8263 | 4.2262 | 14
O2 Early access to the site compound | 3.7989 | 4.1946 | 15
4 How to read these results
• The register's expected value is an average: in a real project some risks happen in full and the others not at all. A contingency set at the expected value would be exceeded about half the time; the confidence level makes that choice explicit.
• Cost and delay of a risk come from the same draws, so they happen together and a large cost comes with a long delay. Delay beyond the float also costs money, which is why the total risk cost exceeds the direct cost of the risks; the float absorbs the first weeks, and their time-related cost with them.
• The schedule results add up every delay as if it hit the critical path, so they are pessimistic: PC-03 calculates the delay through the programme's network, where some delays are absorbed by float.
• The tornado ranks the risks by their effect on the total. It does not always match a probability × impact score: a likely risk with a narrow range matters less than a rarer one with a wide range.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | TotalRisk
1% | 99% | -0.37481
3% | 97% | 0.24402
5% | 95% | 0.59197
7% | 93% | 0.84225
9% | 91% | 1.0423
11% | 89% | 1.2419
13% | 87% | 1.4355
15% | 85% | 1.5926
17% | 83% | 1.7451
19% | 81% | 1.9235
21% | 79% | 2.049
23% | 77% | 2.1718
25% | 75% | 2.3082
27% | 73% | 2.4307
29% | 71% | 2.5629
31% | 69% | 2.7055
33% | 67% | 2.8455
35% | 65% | 2.9779
37% | 63% | 3.0956
39% | 61% | 3.2154
41% | 59% | 3.3491
43% | 57% | 3.4951
45% | 55% | 3.6121
47% | 53% | 3.7445
49% | 51% | 3.8762
51% | 49% | 3.9852
53% | 47% | 4.0955
55% | 45% | 4.227
57% | 43% | 4.3651
59% | 41% | 4.4866
61% | 39% | 4.6125
63% | 37% | 4.7309
65% | 35% | 4.8692
67% | 33% | 5.0084
69% | 31% | 5.1626
71% | 29% | 5.3069
73% | 27% | 5.4467
75% | 25% | 5.6074
77% | 23% | 5.7886
79% | 21% | 5.9665
81% | 19% | 6.1574
83% | 17% | 6.3674
85% | 15% | 6.6166
87% | 13% | 6.891
89% | 11% | 7.1838
91% | 9% | 7.5184
93% | 7% | 7.9049
95% | 5% | 8.4643
97% | 3% | 9.144
99% | 1% | 10.841
Overall mean of TotalRisk |  | 4.1161
Ranked input (chart) |  |  |  | Highest − mean | Lowest − mean
T9 Key subcontractor becomes insolvent |  |  |  | 3.5933 | -0.30568
T3 Client design changes after stage 4 |  |  |  | 2.0133 | -1.2015
T7 Shortage of mechanical and electrical labour |  |  |  | 1.6109 | -0.69279
T1 Contaminated ground found during excavation |  |  |  | 1.4866 | -0.4007
T5 Medical equipment prices rise |  |  |  | 1.1061 | -0.53078
T4 Asbestos in the existing building |  |  |  | 1.2134 | -0.41188
T2 Gas main diversion takes longer than planned |  |  |  | 1.0774 | -0.43796
T11 Hospital operations restrict working hours |  |  |  | 0.97017 | -0.53226
T10 Defects found in commissioning the medical gases |  |  |  | 0.93555 | -0.18614
T12 Fire strategy needs re-approval |  |  |  | 0.90257 | -0.15879
T6 Planning condition adds archaeological works |  |  |  | 0.89481 | -0.16379
T8 Wet winter stops groundworks |  |  |  | 0.74321 | -0.23196
O1 Value engineering of the façade |  |  |  | 0.29078 | -0.50501
O3 Framework bulk-purchase agreement |  |  |  | 0.11012 | -0.28978
O2 Early access to the site compound |  |  |  | 0.078512 | -0.31726

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
1382
4
95
144
127
102
72
49
21
4
1165
3
103
174
185
167
111
62
25
5
782
28
168
256
234
207
159
109
47
10
1324
13
91
135
141
136
90
45
20
5
999
1
94
161
198
200
150
129
49
19
1572
9
42
90
81
71
64
42
21
8
1106
10
84
161
186
173
130
86
45
19
1294
7
64
128
144
132
108
78
34
11
1838
1
14
25
30
37
31
17
4
3
1505
14
85
103
99
80
68
27
15
4
992
10
120
184
170
205
136
102
63
18
1617
13
41
71
67
70
55
38
20
8
47
156
222
226
198
107
31
3
0
1010
18
44
83
128
134
119
60
3
0
1411
41
119
197
214
142
59
7
0
0
1221
25
157
413
485
470
258
125
43
18
6
44
211
414
541
416
228
100
33
8
5
762
404
344
236
126
77
33
11
4
3
53
279
492
468
379
190
87
32
14
6
1606
0
0
0
0
0
0
0
0
394
11
60
192
380
522
423
282
97
31
2