## About
Schedule Risk on a Project Network |  | ModelRisk example · Projects and construction · PC-03
When will the new bridge open? Schedule risk on the activity network: completion date, criticality and merge bias.
Next: Inputs ▸
Model card
Industry | Projects and construction
Difficulty | ★★★☆☆ A 15-activity network with three-point durations and a risk event, scheduled forwards and backwards in every iteration.
Business question | The replacement of a road bridge is planned at 40 weeks with most likely durations, and the contract allows 44. How likely is the project to finish within 44 weeks, what completion date can be promised with 80% confidence, and which activities really control the finish?
Who it is for | Planners, project managers and contractors who prepare or review programmes.
Main outputs | Completion in weeks and as a date: P50 / P80 / P90 · chance of meeting the contract date · the effect of skewed durations and of merge bias · each activity's criticality index and its influence on the finish · a Gantt chart of each iteration.
ModelRisk techniques | PERT durations and a risk event on a finish-to-start network · forward and backward pass inside the spreadsheet in every iteration · float and criticality index · merge bias at a node where paths join · conditional-mean tornado.
File | PC-03 Schedule risk on a project network · Version 1.0 · October 2026 · built with ModelRisk 10
The business question
A council is replacing an old road bridge. The programme has fifteen activities: design, demolition, piling and walls for two abutments, a pier in the river, girders fabricated off site, then the deck, surfacing and opening. With most likely durations the critical path gives 40 weeks, and the contract allows 44. But durations are uncertain and skewed — things are more likely to take longer than shorter — and four paths must all be finished before the girders can be erected. Wherever parallel paths join, the later of them sets the pace, so the project is late if any one of them is. That 'merge bias' is invisible in a deterministic programme. The model draws every duration, schedules the network forwards and backwards in every iteration, and reports the completion date, the chance of meeting the contract, and how often each activity is critical.
How the model works
Three sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | The start date, the contract duration, and a risk event: a flood that stops work on the river pier.
2 Network | Each activity has a PERT duration and finish-to-start predecessors. Each start is the latest finish of its predecessors (forward pass); each latest finish is the earliest latest-start of its successors (backward pass). Float is the difference; an activity with no float is critical in that iteration. The same network is also scheduled with most likely and with mean durations, for comparison.
3 Results | Completion percentiles and dates, the chance of finishing within the contract, the gap between the deterministic and the simulated finish split into skew and merge bias, and for each activity how often it is critical and how strongly its duration drives the finish.
How to use it
Step 1 | Enter your activities' three-point durations on the Network sheet. The logic (predecessors) is built into the Start formulas: each takes the latest finish of the activities listed.
Step 2 | Set the start date, the contract duration and the risk event on the Inputs sheet.
Step 3 | Press F9 to watch the Gantt chart change, then run a simulation from the ModelRisk ribbon (10,000 samples).
Step 4 | Focus schedule recovery on activities with a high criticality index and a strong influence on the finish.
Workbook map
Inputs | Start date, contract duration and the flood risk event.
Network | Activities, the iteration's schedule with float and criticality and its Gantt chart, deterministic schedules, outputs.
Results | Completion, chance of meeting the contract, skew and merge bias, criticality and sensitivity.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Time | Weeks from the start of the project; dates are the start date plus whole weeks.
Critical | An activity is critical in an iteration if it has no float: any delay to it delays the opening.
Criticality index | The share of iterations in which an activity is critical.
P50 / P80 / P90 | A 50%, 80% and 90% chance of finishing by then.
Key assumptions and limitations
Logic | Finish-to-start links only, no lags; resources are not limited; no weather calendar apart from the flood risk.
Independence | Durations are independent of each other; in practice common causes (productivity, weather) can link them.
Flood | A flood adds its delay to the river pier only.
Data | The project and all durations are invented for this example.
ModelRisk functions used
VosePERT | Each activity's duration from its low, most likely and high estimates.
VoseRiskEvent, VosePERTObject | The flood: no delay, or a PERT number of weeks.
VoseInput, VoseOutput | Name the durations and the outputs, including whether each activity is critical.
VoseSimMean, VoseSimPercentile | Statistics of the simulation for the tables and charts on the Results sheet.
VoseSimSensitivityMean | The tornado chart: every VoseInput ranked by how far the mean completion moves across its range.
Further reading
Schedule risk | Hulett, D. T. (2009). Practical Schedule Risk Analysis. Gower.
Merge bias | MacCrimmon, K. R. and Ryavec, C. A. (1964). An analytical study of the PERT assumptions. Operations Research 12(1), 16–37.
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Schedule Risk on a Project Network | [7 empty] | ModelRisk example · Projects and construction · PC-03
INPUTS · Start date, contract duration and the flood risk. The fifteen activities and their three-point durations are on the Network sheet. Change only the yellow cells.
◂ About | [7 empty] | Next: Network ▸
How to read this sheet: yellow cells are inputs. Orange cells hold ModelRisk distributions and show the current random sample (press F9 to draw again). Low / Most likely / High are the minimum, most likely and maximum for PERT. Mean is the distribution's average (VoseMean); it shows ✗ if a range is out of order.
1 Programme
When the work starts and what the contract allows.
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Start date | date | 2027-03-01 | Fixed |  |  |  |  | Notice to proceed (1 March 2027).
Contract duration | weeks | 44 | Fixed |  |  |  |  | Completion date in the contract: 44 weeks after the start.
2 Risk event
A flood stops work in the river until the water level drops.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Chance of a flood during the pier works | probability | 25% | Fixed |  |  |  |  | Gauge records: one flood in four winters over the cofferdam's design level.
Delay to the river pier from a flood | weeks | 0 | Risk event · PERT | 2 | 3 | 6 | 0.83333 | Pumping out, inspection and repair of the cofferdam.

## Network
Schedule Risk on a Project Network | [10 empty] | ModelRisk example · Projects and construction · PC-03
NETWORK · Fifteen activities: durations, forward and backward pass, float and the critical path (weeks).
◂ Inputs | [10 empty] | Next: Results ▸
1 Activities
Yellow cells are inputs. The Predecessors column is a label only: the logic is written into the Start formulas of section 2, so editing the text changes nothing.
ID | Activity | Predecessors | Duration (weeks) |  |  | Mean |  |  |  |  | Note
|  | label only | Low | Most likely | High | PERT
A | Design and approvals | – | 8 | 10 | 16 | 10.6667 |  |  |  |  | Detailed design, approval by the highway authority
B | Site set-up and traffic management | A | 2 | 3 | 5 | 3.1667 |  |  |  |  | Diversion route signed and opened
C | Demolish the old bridge | B | 3 | 4 | 7 | 4.3333 |  |  |  |  | Night possessions of the railway below
D | North abutment piling | C | 5 | 7 | 11 | 7.3333 |  |  |  |  | Bored piles; ground conditions known from boreholes
E | South abutment piling | C | 5 | 7 | 12 | 7.5 |  |  |  |  | Softer ground near the river bank
F | River pier | C | 6 | 9 | 14 | 9.3333 |  |  |  |  | Cofferdam in the river; flood risk added below
G | Fabricate steel girders (off site) | A | 10 | 14 | 20 | 14.3333 |  |  |  |  | Fabricator's slot booked after design approval
H | North abutment walls | D | 3 | 4 | 6 | 4.1667
I | South abutment walls | E | 3 | 4 | 6 | 4.1667
J | Deliver and erect girders | F, G, H, I | 2 | 3 | 5 | 3.1667 |  |  |  |  | Needs both abutments, the pier and the girders
K | Deck slab | J | 4 | 5 | 8 | 5.3333
L | Waterproofing and surfacing | K | 2 | 3 | 5 | 3.1667
M | Parapets and finishes | K | 2 | 2 | 4 | 2.3333
N | Approach road tie-ins | B | 3 | 4 | 6 | 4.1667 |  |  |  |  | Independent of the bridge itself
O | Testing and opening | L, M, N | 1 | 1 | 2 | 1.1667 |  |  |  |  | Load test and safety audit
2 Schedule in this iteration
Start = latest finish of the predecessors. Late finish = earliest late start of the successors.
ID | Activity | Duration | Start | Finish | Late start | Late finish | Float | Critical? |  |  | How it is calculated
|  | sampled | [5 empty] | 1 = yes
A | Design and approvals | 11.5986 | 0 | 11.5986 | 0 | 11.5986 | 0 | 1 |  |  | Start: the finish of the predecessor, or the latest finish if there are several (forward pass)
B | Site set-up and traffic management | 3.3287 | 11.5986 | 14.9273 | 11.5986 | 14.9273 | 0 | 1 |  |  | Late finish: the late start of the successor, or the earliest if there are several (backward pass)
C | Demolish the old bridge | 4.7502 | 14.9273 | 19.6774 | 14.9273 | 19.6774 | 0 | 1 |  |  | Float = late start − start; critical if the float is zero
D | North abutment piling | 7.8088 | 19.6774 | 27.4862 | 21.9174 | 29.7262 | 2.24 | 0
E | South abutment piling | 9.4789 | 19.6774 | 29.1564 | 19.6774 | 29.1564 | 0 | 1
F | River pier | 12.5581 | 19.6774 | 32.2355 | 20.7242 | 33.2823 | 1.0468 | 0 |  |  | River pier: its duration includes the flood delay from the Inputs sheet
G | Fabricate steel girders (off site) | 14.5922 | 11.5986 | 26.1908 | 18.6901 | 33.2823 | 7.0915 | 0
H | North abutment walls | 3.5561 | 27.4862 | 31.0423 | 29.7262 | 33.2823 | 2.24 | 0
I | South abutment walls | 4.1259 | 29.1564 | 33.2823 | 29.1564 | 33.2823 | 0 | 1
J | Deliver and erect girders | 2.3255 | 33.2823 | 35.6078 | 33.2823 | 35.6078 | 0 | 1
K | Deck slab | 5.2868 | 35.6078 | 40.8946 | 35.6078 | 40.8946 | 0 | 1
L | Waterproofing and surfacing | 2.5139 | 40.8946 | 43.4085 | 40.8946 | 43.4085 | 0 | 1
M | Parapets and finishes | 2.0753 | 40.8946 | 42.9699 | 41.3331 | 43.4085 | 0.43855 | 0
N | Approach road tie-ins | 4.2761 | 14.9273 | 19.2034 | 39.1323 | 43.4085 | 24.2051 | 0
O | Testing and opening | 1.2292 | 43.4085 | 44.6377 | 43.4085 | 44.6377 | 0 | 1
3 This iteration as a Gantt chart
The schedule above drawn to scale. Press F9 to see another possible programme.
4 Deterministic schedules
The same network with most likely durations — forward and backward pass, to find its critical path — and with mean durations (the flood at its expected value).
ID | Activity | Most likely | Start | Finish | Late start | Late finish | Critical? | Mean | Start | Finish | How it is calculated
|  | duration |  |  |  |  | most likely | duration
A | Design and approvals | 10 | 0 | 10 | 0 | 10 | 1 | 10.6667 | 0 | 10.6667 | Most likely durations: the usual deterministic programme
B | Site set-up and traffic management | 3 | 10 | 13 | 10 | 13 | 1 | 3.1667 | 10.6667 | 13.8333 | Critical in it: no float between start and late start
C | Demolish the old bridge | 4 | 13 | 17 | 13 | 17 | 1 | 4.3333 | 13.8333 | 18.1667 | Mean durations: removes the skew, but not the merge bias
D | North abutment piling | 7 | 17 | 24 | 17 | 24 | 1 | 7.3333 | 18.1667 | 25.5
E | South abutment piling | 7 | 17 | 24 | 17 | 24 | 1 | 7.5 | 18.1667 | 25.6667
F | River pier | 9 | 17 | 26 | 19 | 28 | 0 | 10.1667 | 18.1667 | 28.3333
G | Fabricate steel girders (off site) | 14 | 10 | 24 | 14 | 28 | 0 | 14.3333 | 10.6667 | 25
H | North abutment walls | 4 | 24 | 28 | 24 | 28 | 1 | 4.1667 | 25.5 | 29.6667
I | South abutment walls | 4 | 24 | 28 | 24 | 28 | 1 | 4.1667 | 25.6667 | 29.8333
J | Deliver and erect girders | 3 | 28 | 31 | 28 | 31 | 1 | 3.1667 | 29.8333 | 33
K | Deck slab | 5 | 31 | 36 | 31 | 36 | 1 | 5.3333 | 33 | 38.3333
L | Waterproofing and surfacing | 3 | 36 | 39 | 36 | 39 | 1 | 3.1667 | 38.3333 | 41.5
M | Parapets and finishes | 2 | 36 | 38 | 37 | 39 | 0 | 2.3333 | 38.3333 | 40.6667
N | Approach road tie-ins | 4 | 13 | 17 | 35 | 39 | 0 | 4.1667 | 13.8333 | 18
O | Testing and opening | 1 | 39 | 40 | 39 | 40 | 1 | 1.1667 | 41.5 | 42.6667
5 Value in this iteration
Key outputs, recorded by ModelRisk at every sample (VoseOutput). Their statistics appear on the Results sheet.
| Output | Unit | Value | [7 empty] | Meaning
| Completion | weeks | 44.6377 | [7 empty] | Finish of the last activity in this iteration.
| Completion date | date | 2028-01-07 | [7 empty] | Start date + weeks × 7 days.
| Within the contract duration? (1 = yes) | 1 / 0 | 0
| Deterministic, most likely durations | weeks | 40 | [7 empty] | The usual programme.
| Deterministic, mean durations | weeks | 42.6667 | [7 empty] | Skew removed; merge bias still missing.
6 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
| Durations: Low ≤ Most likely ≤ High |  | OK
| No negative float (the backward pass is consistent) |  | OK
| The last activity is critical |  | OK

## Results
Schedule Risk on a Project Network | [6 empty] | ModelRisk example · Projects and construction · PC-03
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Network
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 Completion | [5 empty] | Completion — S-curve
Weeks from the start. The contract allows the duration on the Inputs sheet.
Measure | Unit | Value
Contract duration (Inputs sheet) | weeks | 44
Contract completion date | date | 2028-01-03
Chance of finishing within the contract | probability | 57.89%
P80 completion | weeks | 45.5784
P80 completion date | date | 2028-01-14
Mean completion (simulated) | weeks | 43.6384
Deterministic completion, most likely durations | weeks | 40
Deterministic completion, mean durations | weeks | 42.6667
Effect of skewed durations (mean − most likely schedule) | weeks | 2.6667
Merge bias (simulated mean − mean-duration schedule) | weeks | 0.97174
2 Completion percentiles
P50 / P80 / P90: a 50%, 80% and 90% chance of finishing by then.
Measure | Unit | P50 | P80 | P90 | Mean
Completion | weeks | 43.5306 | 45.5784 | 46.7009 | 43.6384
3 Which activities are critical
Criticality index: how often the activity is on the critical path in the simulation.
Activity | Critical, | Criticality
| most likely | index
A Design and approvals | yes | 100%
B Site set-up and traffic management | yes | 99.39%
C Demolish the old bridge | yes | 99.39%
D North abutment piling | yes | 37.22%
E South abutment piling | yes | 43.45%
F River pier |  | 18.72%
G Fabricate steel girders (off site) |  | 0.61%
H North abutment walls | yes | 37.22%
I South abutment walls | yes | 43.45%
J Deliver and erect girders | yes | 100%
K Deck slab | yes | 100%
L Waterproofing and surfacing | yes | 91.62%
M Parapets and finishes |  | 8.38%
N Approach road tie-ins |  | 0%
O Testing and opening | yes | 100%
4 Which durations drive completion | [5 empty] | Influence of each duration on completion (weeks)
Lowest and highest mean completion over ten equal groups of each input (VoseSimSensitivityMean), drawn from the overall mean.
Input (ranked by influence) | Lowest mean | Highest mean | Rank
A Design and approvals | 41.5262 | 46.3775 | 1
K Deck slab | 42.5649 | 45.0001 | 2
C Demolish the old bridge | 42.6478 | 44.9131 | 3
E South abutment piling | 43.0284 | 45.2501 | 4
F River pier | 43.274 | 45.4716 | 5
J Deliver and erect girders | 42.7549 | 44.8086 | 6
B Site set-up and traffic management | 42.7905 | 44.6369 | 7
L Waterproofing and surfacing | 42.8712 | 44.679 | 8
D North abutment piling | 43.1793 | 44.6983 | 9
Flood delay | 43.4078 | 44.8339 | 10
H North abutment walls | 43.312 | 44.0891 | 11
I South abutment walls | 43.3136 | 44.0806 | 12
O Testing and opening | 43.4281 | 43.9043 | 13
G Fabricate steel girders (off site) | 43.5009 | 43.8566 | 14
N Approach road tie-ins | 43.4868 | 43.7919 | 15
M Parapets and finishes | 43.4562 | 43.7604 | 16
5 How to read these results
• The deterministic programme finishes in 40 weeks, but that date is rarely met: most likely durations add up to less than the median, and wherever paths join, the latest of them sets the pace (merge bias). The two effects are shown separately.
• Activities that are critical in the deterministic programme are not always critical in practice, and others become critical when they overrun: the criticality index measures how often each one controls the finish.
• Effort to recover the schedule pays off on activities with a high criticality index and a strong influence: shortening a non-critical activity changes nothing.
• Common causes such as productivity or weather can make durations move together, which widens the range; this model treats them as independent.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | Finish
1% | 99% | 38.6452
3% | 97% | 39.4984
5% | 95% | 39.9692
7% | 93% | 40.2902
9% | 91% | 40.5499
11% | 89% | 40.8415
13% | 87% | 41.0444
15% | 85% | 41.2152
17% | 83% | 41.4147
19% | 81% | 41.5686
21% | 79% | 41.7235
23% | 77% | 41.8778
25% | 75% | 42.0158
27% | 73% | 42.1702
29% | 71% | 42.2914
31% | 69% | 42.3961
33% | 67% | 42.5178
35% | 65% | 42.6295
37% | 63% | 42.767
39% | 61% | 42.8887
41% | 59% | 43.0138
43% | 57% | 43.1231
45% | 55% | 43.2319
47% | 53% | 43.3439
49% | 51% | 43.478
51% | 49% | 43.5872
53% | 47% | 43.7104
55% | 45% | 43.8177
57% | 43% | 43.9383
59% | 41% | 44.0721
61% | 39% | 44.2082
63% | 37% | 44.3519
65% | 35% | 44.4721
67% | 33% | 44.6002
69% | 31% | 44.7327
71% | 29% | 44.8865
73% | 27% | 45.0393
75% | 25% | 45.1935
77% | 23% | 45.3512
79% | 21% | 45.4999
81% | 19% | 45.6759
83% | 17% | 45.8764
85% | 15% | 46.0666
87% | 13% | 46.2957
89% | 11% | 46.5551
91% | 9% | 46.8775
93% | 7% | 47.2228
95% | 5% | 47.6295
97% | 3% | 48.2799
99% | 1% | 49.3421
Overall mean of Finish |  | 43.6384
Ranked input (chart) |  |  |  | Highest − mean | Lowest − mean
A Design and approvals |  |  |  | 2.7391 | -2.1122
K Deck slab |  |  |  | 1.3617 | -1.0735
C Demolish the old bridge |  |  |  | 1.2747 | -0.99057
E South abutment piling |  |  |  | 1.6117 | -0.61005
F River pier |  |  |  | 1.8332 | -0.36441
J Deliver and erect girders |  |  |  | 1.1702 | -0.88355
B Site set-up and traffic management |  |  |  | 0.99848 | -0.8479
L Waterproofing and surfacing |  |  |  | 1.0406 | -0.76722
D North abutment piling |  |  |  | 1.0599 | -0.45906
Flood delay |  |  |  | 1.1955 | -0.23064
H North abutment walls |  |  |  | 0.45069 | -0.32643
I South abutment walls |  |  |  | 0.44216 | -0.32484
O Testing and opening |  |  |  | 0.26592 | -0.21035
G Fabricate steel girders (off site) |  |  |  | 0.21819 | -0.13755
N Approach road tie-ins |  |  |  | 0.15348 | -0.15165
M Parapets and finishes |  |  |  | 0.12195 | -0.18223
Formulas:
Value = IFERROR(StartDate+ROUND(7*[Value, row above],0),"–")

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
1477
0
0
22
121
149
129
76
20
6
145
322
346
354
308
232
176
80
29
8
0
0
0
0
0
2000
0
0
0
0
70
246
340
350
318
289
196
118
53
20
13
0
0
0
0
0
0
0
0
1987
144
317
372
348
293
226
168
85
34
13
13
0
0
0
0
0
0
0
0
1987
117
255
344
365
322
257
181
98
48
13
1277
0
0
0
0
0
0
0
0
723
119
312
383
376
327
221
158
72
29
3
1134
0
0
0
0
0
0
0
0
866
145
302
442
373
306
215
115
69
27
6
1602
0
0
0
0
0
0
0
0
398
57
186
264
311
327
325
251
176
71
32
1987
0
0
0
0
0
0
0
0
13
114
240
349
365
314
261
185
108
51
13
1277
0
0
0
0
0
0
0
0
723
77
233
336
366
354
255
206
115
43
15
1134
0
0
0
0
0
0
0
0
866
63
221
345
330
325
279
217
125
69
26
0
0
0
0
0
2000
0
0
0
0
155
326
423
389
312
213
109
55
15
3
0
0
0
0
0
2000
0
0
0
0
91
219
329
376
349
280
189
109
46
12
171
0
0
0
0
0
0
0
0
1829
633
405
355
235
163
102
59
22
18
8
1829
0
0
0
0
0
0
0
0
171
86
261
306
333
304
285
200
125
83
17
0
0
0
0
0
2000
0
0
0
0
625
448
326
236
171
98
44
23
17
12
0
0
0
0
0
2000
0
0
0
0
30
96
285
442
464
373
183
83
36
8
837
0
0
0
0
0
0
0
0
1163