## About
Integrated Cost and Schedule Risk |  | ModelRisk example · Projects and construction · PC-04
Budget and completion date together: how confident can the sponsor be of both, for the treatment works upgrade?
Next: Inputs ▸
Model card
Industry | Projects and construction
Difficulty | ★★★★★ Network schedule, time-dependent costs, a common productivity factor and linked risk events: cost and time simulated together, with the joint confidence level.
Business question | The wastewater treatment works upgrade has a deterministic plan of US$26.7 million and 62 weeks. Because much of the cost accrues by the week, a late project is also an expensive one. What budget and completion date can be approved with a given confidence of meeting both, and why is a P80 budget plus a P80 date not an 80% plan?
Who it is for | Project directors, project controls and cost engineers, sponsors and boards approving budgets and dates together.
Main outputs | Cost and completion: P50 / P70 / P80 · the correlation between them · the chance of meeting the budget, the deadline and both (joint confidence level, JCL) at the targets · a JCL table for budgets and deadlines around the targets · the drivers.
ModelRisk techniques | Activity network with PERT durations · a common productivity factor that makes site durations move together · time-dependent and fixed costs per activity and site overheads by the week · risk events whose delay and cost come from one shared draw · joint confidence level with VoseSimJointProb, at the targets, at the P80s and for a table of budgets and deadlines · S-curves and tornado.
File | PC-04 Integrated cost and schedule risk · Version 1.0 · October 2026 · built with ModelRisk 10
The business question
A water company is upgrading a wastewater treatment works: new tanks, new process equipment, and the old works decommissioned. The deterministic plan says US$26.7 million and 62 weeks. Two things make that plan optimistic. First, much of the cost depends on time: crews, plant and site management are paid by the week, so a longer project costs more — cost and schedule are linked. Second, durations do not vary independently: site productivity affects every site activity at once. The model schedules the network in every iteration, prices each activity's time-dependent and fixed cost, adds risk events that bring both delay and cost, and records whether the project meets the budget, the deadline and both. The joint confidence level (JCL) — the chance of meeting both — is what a sponsor approving a budget and a date together really needs, and it is lower than either confidence on its own.
How the model works
Three sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | The budget and deadline to test, the site productivity factor (Lognormal around 1, applied to every site activity), the weekly site overheads, and three risk events. Ground conditions and commissioning problems bring both delay and cost, drawn from one shared uniform so that a bad case is bad in both.
2 Plan | Each activity has a PERT duration (× productivity for site work, + any risk delay), a time-dependent rate and a PERT fixed cost (+ any risk cost). A small risk table holds this iteration's risk delays and costs, and each activity picks up its own with SUMIF. Starts follow the network; activity cost = fixed cost + risk cost + rate × duration; the project adds overheads × finish.
3 Results | Percentiles of cost and finish, their correlation, the chance of meeting the budget, the deadline and both (VoseSimJointProb), the chance of meeting both P80s, the JCL table, and what drives the cost.
How to use it
Step 1 | Review the activities, durations, rates and fixed costs on the Plan sheet, and the risks on the Inputs sheet.
Step 2 | Set the budget and deadline you want to test on the Inputs sheet.
Step 3 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set).
Step 4 | Use the JCL table to choose a budget-and-date pair with the confidence the sponsor requires.
Step 5 | Do not approve the P80 budget and the P80 date as an '80% plan': Results shows how much less likely it is to meet both.
Workbook map
Inputs | Targets and the JCL table's steps, productivity factor, overheads, risk events.
Plan | Activities and their costs, this iteration's risks, schedule and cost, the deterministic plan, outputs and checks.
Results | Cost and finish ranges, joint confidence, JCL table, S-curves and drivers.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Money | US$ million (US$m); rates in US$ thousand per week (US$k/wk).
Time | Weeks from the start.
JCL | Joint confidence level: the chance that the project meets the budget AND the deadline.
P50 / P70 / P80 | A 50%, 70% and 80% chance of not being exceeded. Agencies often require a JCL of 70%.
Key assumptions and limitations
Logic | Finish-to-start links; no resource limits; overheads run until the last activity finishes.
Productivity | One factor scales all site durations together; design and procurement are not affected.
Risks | Three risk events; each happens at most once; the delay applies to its activity's duration.
Data | The project and all figures are invented for this example.
ModelRisk functions used
VosePERT | Durations and fixed costs from three-point estimates.
VoseLognormalAlt | The site productivity factor, from its 10th and 90th percentiles.
VoseRiskEvent, VosePERTObject, VoseUniform | Risk events; one shared uniform per risk drives both its delay and its cost.
VoseInput, VoseOutput | Name the uncertain quantities and the outputs.
VoseSimJointProb | The share of iterations that meet a budget AND a deadline: the joint confidence level.
VoseSimMean, VoseSimPercentile, VoseSimProbability, VoseSimCorrelation | Statistics of the simulation for the tables and charts on the Results sheet.
VoseSimSensitivityMean | The tornado chart: the thirteen VoseInputs that move the mean total cost most across their range, ranked.
Further reading
Integrated analysis | AACE International (2012). Recommended Practice 57R-09: Integrated Cost and Schedule Risk Analysis using Monte Carlo Simulation of a CPM Model.
Joint confidence | NASA (2015). NASA Cost Estimating Handbook, version 4.0 — Joint Cost and Schedule Confidence Level (JCL).
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Integrated Cost and Schedule Risk | [7 empty] | ModelRisk example · Projects and construction · PC-04
INPUTS · Targets, common factors and risk events. The nine activities, with their durations, rates and fixed costs, are on the Plan sheet. Change only the yellow cells.
◂ About | [7 empty] | Next: Plan ▸
How to read this sheet: yellow cells are inputs. Orange cells hold ModelRisk distributions and show the current random sample (press F9 to draw again). Low / Most likely / High are the minimum, most likely and maximum for PERT; the low (10th percentile) and high (90th percentile) estimates for Lognormal. Mean is the distribution's average (VoseMean); it shows ✗ if a range is out of order.
1 Targets
The budget and the completion deadline to test, and the steps between the budgets and deadlines of the JCL table.
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Budget | US$m | 29.5 | Fixed |  |  |  |  | Proposed budget including contingency.
Deadline | weeks | 70 | Fixed |  |  |  |  | Completion required by the regulator's permit.
Step between the budgets in the JCL table | US$m | 1 | Fixed |  |  |  |  | Two budgets either side of the target.
Step between the deadlines in the JCL table | weeks | 3 | Fixed |  |  |  |  | Two deadlines either side of the target.
2 Common factors
Things that affect many activities at once.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Site productivity factor (× site durations) | × | 0.88019 | Lognormal · P10, P90 | 0.9 | – | 1.1 | 0.99804 | Labour market and site conditions: 1.10 means every site activity takes 10% longer.
Site overheads | US$k per week | 35 | Fixed |  |  |  |  | Site management, welfare, security: paid until completion.
3 Risk events
The chance of each risk, and its delay and cost if it happens. They are drawn on the Plan sheet; ground conditions and commissioning take their delay and cost from one shared draw.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Chance of poor ground conditions | probability | 30% | Fixed |  |  |  |  | Boreholes found soft clay on the east side.
Ground: delay to excavation and piling, if it happens | weeks | – | PERT · drawn elsewhere | 2 | 3 | 6 | 3.3333 | Extra piling and dewatering.
Ground: extra cost, if it happens | US$m | – | PERT · drawn elsewhere | 0.5 | 0.8 | 1.5 | 0.86667 | Longer piles, dewatering plant.
Chance that the process equipment is late | probability | 25% | Fixed |  |  |  |  | Single supplier for the membranes, busy order book.
Equipment: delay, if it is late | weeks | – | PERT · drawn elsewhere | 3 | 5 | 8 | 5.1667 | Delivery slip.
Chance of process problems in commissioning | probability | 20% | Fixed |  |  |  |  | Biological process needs time to stabilise.
Commissioning: delay, if it happens | weeks | – | PERT · drawn elsewhere | 2 | 3 | 5 | 3.1667 | Re-seeding, retesting.
Commissioning: extra cost, if it happens | US$m | – | PERT · drawn elsewhere | 0.3 | 0.5 | 0.8 | 0.51667 | Specialists, chemicals, temporary treatment.

## Plan
Integrated Cost and Schedule Risk | [10 empty] | ModelRisk example · Projects and construction · PC-04
PLAN · Nine activities: network, durations and costs; this iteration's risk events, schedule and cost.
◂ Inputs | [10 empty] | Next: Results ▸
1 Activities
Yellow cells are inputs. Site work = 1: the productivity factor applies. Rate: cost per week of the activity.
ID | Activity | Predecessors | Duration (weeks) |  |  | Site | Rate | Fixed cost (US$m) |  |  | Note
|  | label only | Low | Most likely | High | work | US$k/wk | Low | Most likely | High
A | Design and permits | – | 12 | 14 | 20 | 0 | 40 | 0.7 | 0.8 | 1 | Design team and permitting
B | Enabling works | A | 4 | 5 | 8 | 1 | 60 | 0.5 | 0.6 | 0.8 | Access roads, temporary works
C | Excavation and piling for the new tanks | B | 8 | 10 | 16 | 1 | 120 | 1.5 | 1.8 | 2.4 | Ground risk event adds time and cost
D | Concrete tanks | C | 12 | 14 | 20 | 1 | 150 | 3 | 3.5 | 4.4 | The largest civil package
E | Process equipment procurement | A | 16 | 20 | 30 | 0 | 10 | 5.4 | 6 | 7.2 | Membranes and blowers; supplier risk event
F | Mechanical installation and pipework | D, E | 8 | 10 | 14 | 1 | 140 | 1.7 | 2 | 2.6
G | Electrical installation and controls | D, E | 6 | 8 | 12 | 1 | 110 | 1.4 | 1.6 | 2
H | Commissioning | F, G | 4 | 5 | 9 | 1 | 90 | 0.3 | 0.4 | 0.6 | Process performance risk event
I | Decommission the old works, landscaping | H | 3 | 4 | 6 | 1 | 60 | 0.4 | 0.5 | 0.7
The Predecessors column is a label only: the logic is written into the Start formulas of section 3.
2 Risk events in this iteration
Each risk is 0, or a PERT delay and cost, with the chance on the Inputs sheet. One shared draw gives a risk's delay and cost, so that a bad case is bad in both.
| Risk | Activity | Shared | Delay | Extra cost | [5 empty] | How it is calculated
|  | ID | draw (U) | weeks | US$m
| Poor ground conditions | C | 0.33596 | 0 | 0 | [5 empty] | VoseRiskEvent(chance, PERT of the delay or cost, the shared draw)
| Process equipment late | E | – | 5.6191 | – | [5 empty] | The supplier risk has no cost: it only delays the equipment
| Process problems in commissioning | H | 0.70057 | 0 | 0
3 This iteration
Work = PERT × productivity (site work). Duration = work + risk delay. Cost = fixed + risk cost + rate × duration.
ID | Activity | Work | Risk delay | Duration | Start | Finish | Fixed | Risk cost | Time-dep. | Cost | How it is calculated
|  | weeks | weeks | weeks | week | week | US$m | US$m | US$m | US$m
A | Design and permits | 14.5129 | 0 | 14.5129 | 0 | 14.5129 | 0.73547 | 0 | 0.58052 | 1.316 | Start: the predecessor's finish, or the latest of several
B | Enabling works | 4.899 | 0 | 4.899 | 14.5129 | 19.4119 | 0.62654 | 0 | 0.29394 | 0.92048 | Risk delay and risk cost: SUMIF over the risk table (section 2)
C | Excavation and piling for the new tanks | 8.6462 | 0 | 8.6462 | 19.4119 | 28.058 | 2.1059 | 0 | 1.0375 | 3.1434 | Time-dependent cost = rate × duration ÷ 1000 (US$k to US$m)
D | Concrete tanks | 14.0337 | 0 | 14.0337 | 28.058 | 42.0918 | 4.0117 | 0 | 2.1051 | 6.1167
E | Process equipment procurement | 18.0957 | 5.6191 | 23.7149 | 14.5129 | 38.2278 | 6.0241 | 0 | 0.23715 | 6.2613
F | Mechanical installation and pipework | 8.3447 | 0 | 8.3447 | 42.0918 | 50.4365 | 1.8891 | 0 | 1.1683 | 3.0573
G | Electrical installation and controls | 8.4909 | 0 | 8.4909 | 42.0918 | 50.5827 | 1.5692 | 0 | 0.934 | 2.5032
H | Commissioning | 4.7097 | 0 | 4.7097 | 50.5827 | 55.2924 | 0.33748 | 0 | 0.42387 | 0.76136
I | Decommission the old works, landscaping | 3.6642 | 0 | 3.6642 | 55.2924 | 58.9566 | 0.55357 | 0 | 0.21985 | 0.77342
| Total | [5 empty] | 17.8529 | 0 | 7.0002 | 24.8531
4 Deterministic plan
Most likely durations and costs, no productivity effect, no risk events.
ID | Activity | Duration | Start | Finish |  |  |  | Cost
|  | weeks | week | week |  |  |  | US$m
A | Design and permits | 14 | 0 | 14 |  |  |  | 1.36
B | Enabling works | 5 | 14 | 19 |  |  |  | 0.9
C | Excavation and piling for the new tanks | 10 | 19 | 29 |  |  |  | 3
D | Concrete tanks | 14 | 29 | 43 |  |  |  | 5.6
E | Process equipment procurement | 20 | 14 | 34 |  |  |  | 6.2
F | Mechanical installation and pipework | 10 | 43 | 53 |  |  |  | 3.4
G | Electrical installation and controls | 8 | 43 | 51 |  |  |  | 2.48
H | Commissioning | 5 | 53 | 58 |  |  |  | 0.85
I | Decommission the old works, landscaping | 4 | 58 | 62 |  |  |  | 0.74
5 Value in this iteration
Key outputs, recorded by ModelRisk at every sample (VoseOutput). Their statistics appear on the Results sheet.
| Output | Unit | Value | [7 empty] | Meaning
| Completion | weeks | 58.9566 | [7 empty] | Finish of the last activity.
| Total cost | US$m | 26.9166 | [7 empty] | Activity costs + overheads × weeks.
| Deterministic completion | weeks | 62 | [7 empty] | Most likely plan.
| Deterministic cost | US$m | 26.7
6 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
| Durations and fixed costs: Low ≤ Most likely ≤ High |  | OK
| Site-work flags are 0 or 1 |  | OK
| Every risk names an activity of the plan |  | OK

## Results
Integrated Cost and Schedule Risk | [6 empty] | ModelRisk example · Projects and construction · PC-04
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Plan
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 Cost and completion | [5 empty] | Total cost — S-curve
The deterministic plan against the simulation.
Measure | Unit | Value
Deterministic cost (most likely, no risk) | US$m | 26.7
Mean cost (simulated) | US$m | 28.1506
Deterministic completion | weeks | 62
Mean completion (simulated) | weeks | 66.9905
Rank correlation between cost and completion |  | 0.81392
Measure | Unit | P50 | P70 | P80 | Mean
Total cost | US$m | 28.0699 | 28.7356 | 29.1622 | 28.1506
Completion | weeks | 66.7415 | 69.5272 | 71.3999 | 66.9905
2 Joint confidence at the targets
Budget and deadline from the Inputs sheet. VoseSimJointProb: the share of iterations that meet both.
Measure | Unit | Value
Budget · deadline |  | 29.5 US$m · 70 weeks |  |  |  | Completion — S-curve
Chance of meeting the budget | probability | 86.02%
Chance of meeting the deadline | probability | 72.79%
Chance of meeting both (joint confidence level) | probability | 71.06%
If cost and time were independent (budget × deadline) | probability | 62.62%
3 A P80 budget and a P80 date are not an 80% plan
Each is met with an 80% chance on its own; both together less often.
Measure | Unit | Value
P80 cost | US$m | 29.1622
P80 completion | weeks | 71.3999
Chance of meeting both the P80 cost and the P80 date | probability | 73.63%
4 Joint confidence level table
Chance of meeting both, for budgets (rows) and deadlines (columns) around the targets: VoseSimJointProb for each pair.
Budget (US$m) | 64 | 67 | 70 | 73 | 76
27.5 | 22.01% | 28.92% | 30.83% | 31.08% | 31.08%
28.5 | 28.69% | 46.81% | 58.7% | 62.39% | 63.05%
29.5 | 29.74% | 51.63% | 71.06% | 81.52% | 85.25%
30.5 | 29.75% | 51.9% | 72.74% | 86.64% | 93.54%
31.5 | 29.75% | 51.9% | 72.79% | 86.98% | 94.77%
The centre cell is the target pair. Green: a high chance of meeting both; red: low. The steps between rows and columns are on the Inputs sheet.
5 What drives the cost | [5 empty] | What drives the total cost (US$m)
Lowest and highest mean total cost over ten equal groups of each input (VoseSimSensitivityMean), drawn from the overall mean.
Input (ranked by influence) | Lowest mean | Highest mean | Rank
Site productivity factor | 26.993 | 29.3881 | 1
Duration: concrete tanks | 27.0681 | 29.3129 | 2
Duration: excavation and piling | 27.2046 | 29.1776 | 3
Duration: mechanical installation | 27.1848 | 29.1539 | 4
Ground risk (delay and cost) | 27.6431 | 29.4549 | 5
Duration: electrical installation | 27.33 | 28.9677 | 6
Duration: commissioning | 27.3871 | 28.866 | 7
Duration: enabling works | 27.423 | 28.8646 | 8
Duration: old works and landscaping | 27.4553 | 28.8816 | 9
Fixed cost: process equipment | 27.5999 | 28.7445 | 10
Commissioning risk (delay and cost) | 27.9357 | 28.9841 | 11
Fixed cost: concrete tanks | 27.7416 | 28.6795 | 12
Fixed cost: excavation and piling | 27.8628 | 28.4914 | 13
6 How to read these results
• Cost and completion are strongly correlated: weeks cost money, and the same events delay the work and add cost. A late project is an expensive one.
• The chance of meeting both the budget and the deadline is lower than either chance on its own. Approving a P80 budget and a P80 date separately gives about a 74% chance of meeting both, not 80%; the JCL table shows which pairs do reach 80%.
• Because cost and time move together, the joint chance is higher than it would be if they were independent — but it is still limited by the harder of the two targets.
• Site productivity affects every site activity at once, so it drives both the cost and the completion; durations that move together widen the range compared with independent estimates.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | TotalCost | Finish
1% | 99% | 25.6445 | 55.6467
3% | 97% | 26.0534 | 57.7363
5% | 95% | 26.2764 | 58.7893
7% | 93% | 26.4431 | 59.5886
9% | 91% | 26.5713 | 60.2448
11% | 89% | 26.6976 | 60.7371
13% | 87% | 26.7973 | 61.1885
15% | 85% | 26.8918 | 61.5595
17% | 83% | 26.9778 | 61.9603
19% | 81% | 27.0581 | 62.2996
21% | 79% | 27.1385 | 62.6574
23% | 77% | 27.2057 | 62.9702
25% | 75% | 27.2785 | 63.2954
27% | 73% | 27.3518 | 63.6099
29% | 71% | 27.4227 | 63.9191
31% | 69% | 27.4985 | 64.1634
33% | 67% | 27.5608 | 64.4199
35% | 65% | 27.6161 | 64.7061
37% | 63% | 27.6799 | 64.9765
39% | 61% | 27.7402 | 65.2658
41% | 59% | 27.7972 | 65.5805
43% | 57% | 27.8597 | 65.8646
45% | 55% | 27.919 | 66.1206
47% | 53% | 27.974 | 66.3698
49% | 51% | 28.0394 | 66.6127
51% | 49% | 28.1026 | 66.8805
53% | 47% | 28.164 | 67.1429
55% | 45% | 28.2236 | 67.4069
57% | 43% | 28.292 | 67.6823
59% | 41% | 28.3607 | 67.9541
61% | 39% | 28.4239 | 68.2175
63% | 37% | 28.4986 | 68.4838
65% | 35% | 28.565 | 68.7626
67% | 33% | 28.631 | 69.0505
69% | 31% | 28.7021 | 69.3657
71% | 29% | 28.7752 | 69.6889
73% | 27% | 28.855 | 70.0352
75% | 25% | 28.9409 | 70.3773
77% | 23% | 29.0168 | 70.7977
79% | 21% | 29.1091 | 71.1936
81% | 19% | 29.2198 | 71.6387
83% | 17% | 29.3293 | 72.0605
85% | 15% | 29.443 | 72.4814
87% | 13% | 29.5714 | 73.0002
89% | 11% | 29.6969 | 73.5454
91% | 9% | 29.8676 | 74.1763
93% | 7% | 30.0464 | 74.9984
95% | 5% | 30.2635 | 76.1219
97% | 3% | 30.6116 | 77.5129
99% | 1% | 31.2433 | 80.2939
Overall mean of TotalCost |  | 28.1506
Ranked input (chart) |  |  |  | Highest − mean | Lowest − mean
Site productivity factor |  |  |  | 1.2375 | -1.1576
Duration: concrete tanks |  |  |  | 1.1623 | -1.0825
Duration: excavation and piling |  |  |  | 1.0271 | -0.94595
Duration: mechanical installation |  |  |  | 1.0033 | -0.96578
Ground risk (delay and cost) |  |  |  | 1.3044 | -0.5075
Duration: electrical installation |  |  |  | 0.81711 | -0.82058
Duration: commissioning |  |  |  | 0.71536 | -0.76347
Duration: enabling works |  |  |  | 0.71405 | -0.72758
Duration: old works and landscaping |  |  |  | 0.73098 | -0.69525
Fixed cost: process equipment |  |  |  | 0.59388 | -0.55073
Commissioning risk (delay and cost) |  |  |  | 0.83351 | -0.2149
Fixed cost: concrete tanks |  |  |  | 0.52887 | -0.40898
Fixed cost: excavation and piling |  |  |  | 0.34084 | -0.28781

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
7
72
245
504
579
389
160
37
5
2
202
205
191
205
209
184
206
197
199
202
1466
0
0
0
37
113
161
125
78
20
199
210
212
187
198
205
191
199
200
199
160
319
388
359
286
236
128
83
38
3
75
243
342
396
307
276
179
104
63
15
40
249
418
441
368
242
150
60
26
6
86
228
324
338
346
282
212
120
56
8
51
232
414
468
378
250
125
56
20
6
70
246
340
350
318
289
196
118
53
20
41
197
471
514
402
237
97
33
5
3
64
201
333
319
348
285
221
157
50
22
134
260
338
369
293
236
191
102
58
19
117
255
344
365
322
257
181
98
48
13
36
189
425
505
438
231
126
40
9
1
91
264
347
382
340
257
181
92
42
4
36
229
429
462
423
224
133
52
10
2
114
236
310
372
333
257
194
113
57
14
24
218
495
452
387
224
109
66
18
7
83
246
287
336
331
279
217
146
53
22
53
240
391
484
388
252
116
55
20
1
114
240
349
365
314
261
185
108
51
13
11
76
241
448
512
380
222
73
32
5
19
141
356
528
468
291
139
44
10
4