## About
Bid Pricing: Margin versus Chance of Winning |  | ModelRisk example · Projects and construction · PC-05
What markup should we bid? The trade-off between the chance of winning and the profit if we win.
Next: Inputs ▸
Model card
Industry | Projects and construction
Difficulty | ★★★☆☆ Eleven bid prices evaluated on the same simulated costs and competitor bids, with a winner's-curse effect.
Business question | A contractor is pricing a US$20 million tender against four competitors. A higher markup earns more if the job is won but wins less often, and the jobs won cheaply are the ones most likely to lose money. Which markup maximises expected profit, and how likely is a loss on a job that is won?
Who it is for | Estimating and bid managers, commercial directors and business-development teams.
Main outputs | For each markup from 0% to 20%: the chance of winning, the expected profit, the profit if the job is won and the chance of a loss on a won job · the markup with the highest expected profit · profit distributions at three markups · drivers.
ModelRisk techniques | Every bid follows the job's true cost: competitors bid their own estimate plus a markup, so winning tells us something about our estimate (the winner's curse) · several decision options evaluated on the same simulated futures · conditional statistics from indicator outputs · a combined chart of expected profit and chance of winning.
File | PC-05 Bid pricing margin versus chance of winning · Version 1.0 · October 2026 · built with ModelRisk 10
The business question
A contractor is preparing a price for a US$20 million building contract, awarded on price alone. Four competitors are bidding. Everyone is estimating the same job, and everyone's estimate is wrong by a few per cent — but not by the same amount. The contractor wins most easily when its own estimate is the one that missed costs the others saw: a won job is then too often one whose cost was underestimated, and it loses money — the winner's curse. A high markup is profitable when it wins, but rarely wins. The model draws the job's true cost and the four competitors' bids from it, and evaluates eleven markups on the same simulated tenders, so that the best markup can be read off and its risk understood.
How the model works
Three sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | The base estimate, a factor for how far the real cost can differ from it, a market factor for prices that affect everyone, the pattern of competitors' bids relative to our estimate, and the cost of preparing the bid.
2 Bids | The job's true cost = our estimate × our estimating error × the market factor. Each competitor bids the true cost × its own ratio (its estimating error and its markup). For each markup our bid is our estimate × (1 + markup); we win if it is below the lowest competitor bid; profit = bid − true cost if we win, minus the bid cost in any case.
3 Results | For each markup: the chance of winning, the expected profit, the profit if we win, and the chance of a loss on a won job; the markup with the highest expected profit; and the profit range at three markups.
How to use it
Step 1 | Enter your estimate and the cost uncertainty on the Inputs sheet.
Step 2 | Calibrate the competitors' bid ratios from your tender history (their bid ÷ your estimate).
Step 3 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set).
Step 4 | Read the best markup, then decide whether its chance of a loss on a won job is acceptable.
Workbook map
Inputs | Estimate, cost factor, market factor, competitor bid ratios, bid cost.
Bids | This tender's cost and competitor bids, and the outcome at each markup; outputs and checks.
Results | Markup table, chart of expected profit and chance of winning, profit S-curves and drivers.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Money | US$ million (US$m).
Markup | Bid = base estimate × (1 + markup).
Bid ratio | A competitor's bid divided by the job's true cost, from past tenders whose final cost became known.
Winner's curse | We win most easily when our estimate is too low: the chance of a loss on a won job is higher than on any tender.
Key assumptions and limitations
Award | Lowest price wins; no negotiation, no quality score, no tie.
Competitors | Four competitors with the same bid pattern; their errors are independent of ours and of each other's, and they do not react to our price.
Costs | Every bid is linked to the job's true cost; the market factor moves it for everyone.
Data | The tender and the bid history are invented for this example.
ModelRisk functions used
VosePERT | Our estimating error, the market factor and each competitor's bid ratio.
VoseInput, VoseOutput | Name the uncertain inputs and the outputs: win, profit and loss-on-win at every markup.
VoseSimMean | Statistics of the simulation for the tables and charts on the Results sheet.
VoseSimSensitivityMean | The tornado chart: every VoseInput ranked by how far the mean profit at the markup in detail moves across its range.
Further reading
Bidding | Friedman, L. (1956). A competitive-bidding strategy. Operations Research 4(1), 104–112.
Winner's curse | Thaler, R. H. (1988). Anomalies: the winner's curse. Journal of Economic Perspectives 2(1), 191–202.
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Bid Pricing: Margin versus Chance of Winning | [7 empty] | ModelRisk example · Projects and construction · PC-05
INPUTS · Every assumption the model uses, with its uncertainty and its basis. Change only the yellow cells.
◂ About | [7 empty] | Next: Bids ▸
How to read this sheet: yellow cells are inputs. Orange cells hold ModelRisk distributions and show the current random sample (press F9 to draw again). Low / Most likely / High are the minimum, most likely and maximum for PERT. Mean is the distribution's average (VoseMean); it shows ✗ if a range is out of order.
1 The job and our estimate
What the job will really cost, against our estimate of it.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Base estimate of our cost | US$m | 20 | Fixed |  |  |  |  | Estimator's most likely cost at tender.
Our estimating error (true cost ÷ estimate) | × | 1.003 | PERT | 0.93 | 1 | 1.12 | 1.0083 | Past jobs: final cost between 7% under and 12% over the tender estimate.
Market price factor | × | 1.0166 | PERT | 0.95 | 1 | 1.07 | 1.0033 | Materials and labour prices over the bid period: they move the job's true cost, and so every bid.
Cost of preparing the bid | US$m | 0.15 | Fixed |  |  |  |  | Estimating and design time; paid whatever the outcome.
2 Competitors
4 competitors. Each estimates the same job, with its own error, and adds its markup: its bid ÷ the job's true cost.
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Competitor bid ratio: low | × true cost | 1 | Fixed |  |  |  |  | From past tenders whose final cost became known.
Competitor bid ratio: most likely | × true cost | 1.12 | Fixed |  |  |  |  | Most common ratio.
Competitor bid ratio: high | × true cost | 1.28 | Fixed |  |  |  |  | Highest ratio seen.
3 Detail
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Markup analysed in detail | markup | 8% | Fixed |  |  |  |  | One of the eleven markups (0% to 20% in steps of 2%): the tornado chart on the Results sheet.

## Bids
Bid Pricing: Margin versus Chance of Winning | [5 empty] | ModelRisk example · Projects and construction · PC-05
BIDS · This tender: the job's true cost, the competitors' bids, and the outcome at each markup (US$m).
◂ Inputs | [5 empty] | Next: Results ▸
1 The job's true cost and the competitors' bids in this iteration
Every bid follows the same true cost: the winner's curse is built in.
Quantity | Unit | Value |  |  |  | How it is calculated
The job's true cost (what it costs us if we win) | US$m | 20.3914 |  |  |  | Our estimate × our estimating error × the market factor
Competitor 1: bid ÷ true cost | × | 1.0847 |  |  |  | Its estimating error and its markup together (PERT)
Competitor 1: bid | US$m | 22.1182 |  |  |  | The job's true cost × its ratio: when the job costs more, every competitor bids more
Competitor 2: bid ÷ true cost | × | 1.0543
Competitor 2: bid | US$m | 21.4983
Competitor 3: bid ÷ true cost | × | 1.1055
Competitor 3: bid | US$m | 22.5427
Competitor 4: bid ÷ true cost | × | 1.0937
Competitor 4: bid | US$m | 22.3017
Lowest competitor bid | US$m | 21.4983 |  |  |  | The price to beat
2 Outcome at each markup
All markups are evaluated on the same simulated tender, so their differences are real.
Markup | Our bid | Win? | Profit | Loss on | Cost above | How it is calculated
| US$m | 1 = yes | US$m | a won job | our bid
0% | 20 | 1 | -0.54143 | 1 | 1 | Win if our bid is below the lowest competitor bid
2% | 20.4 | 1 | -0.14143 | 0 | 0 | Profit = (bid − true cost) if we win, minus the bid cost
4% | 20.8 | 1 | 0.25857 | 0 | 0 | Loss on a won job: we win and the true cost is above our bid
6% | 21.2 | 1 | 0.65857 | 0 | 0 | Cost above our bid: the same, won or not — the comparison that shows the winner's curse
8% | 21.6 | 0 | -0.15 | 0 | 0
10% | 22 | 0 | -0.15 | 0 | 0
12% | 22.4 | 0 | -0.15 | 0 | 0
14% | 22.8 | 0 | -0.15 | 0 | 0
16% | 23.2 | 0 | -0.15 | 0 | 0
18% | 23.6 | 0 | -0.15 | 0 | 0
20% | 24 | 0 | -0.15 | 0 | 0
Profit at the markup analysed in detail | US$m |  | -0.15 |  |  | The markup on the Inputs sheet: for the tornado chart
3 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
Competitor bid ratios: low ≤ most likely ≤ high |  | OK
The markup analysed in detail is one of the eleven |  | OK

## Results
Bid Pricing: Margin versus Chance of Winning | [6 empty] | ModelRisk example · Projects and construction · PC-05
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Bids
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 Which markup? | [5 empty] | Expected profit and chance of winning by markup
Chance of winning, expected profit (all tenders, won or lost), the margin on a won job, and the chance of a loss: on a won job, and on any tender.
Markup | Chance of | Expected | Margin if | Loss if | Cost above
| winning | profit, US$m | we win, US$m | we win | bid, any tender
0% | 94.88% | -0.44167 | -0.30741 | 62% | 58.83%
2% | 88.49% | -0.13446 | 0.017566 | 46.57% | 41.21%
4% | 78.08% | 0.088614 | 0.3056 | 33.27% | 25.98%
6% | 65.78% | 0.22767 | 0.57414 | 20.74% | 13.64%
8% | 51.66% | 0.27368 | 0.82013 | 11.83% | 6.11%
10% | 38.47% | 0.25699 | 1.0579 | 5.433% | 2.09%
12% | 26.09% | 0.18495 | 1.2838 | 2.146% | 0.56%
14% | 15.99% | 0.090991 | 1.5071 | 0.5003% | 0.08%
16% | 9.32% | 0.01179 | 1.7359 | 0.1074% | 0.01%
18% | 4.79% | -0.056647 | 1.9489 | 0% | 0%
20% | 2.29% | -0.10033 | 2.1689 | 0% | 0%
Markup with the highest expected profit |  | 8%
Margin if we win: before the bid cost. Loss if we win against cost above the bid on any tender: the gap is the winner's curse.
2 Profit at three markups
The range of profit over all tenders, won or lost. | [5 empty] | Profit at three markups — cumulative probability
Measure | Unit | Value
4% markup: 10th percentile of profit | US$m | -0.71219
8% markup: 10th percentile of profit | US$m | -0.15
12% markup: 10th percentile of profit | US$m | -0.15
4% markup: 90th percentile of profit | US$m | 0.99443
8% markup: 90th percentile of profit | US$m | 1.2729
12% markup: 90th percentile of profit | US$m | 1.3325
3 What drives the profit at the markup in detail | [5 empty] | What drives the profit at the markup in detail (US$m)
Lowest and highest mean profit at the markup on the Inputs sheet over ten equal groups of each input (VoseSimSensitivityMean).
Input (ranked by influence) | Lowest mean | Highest mean | Rank
Our cost factor | -0.098474 | 0.48977 | 1
Competitor 2 bid ratio | -0.076449 | 0.39546 | 2
Competitor 4 bid ratio | -0.061411 | 0.39841 | 3
Competitor 1 bid ratio | -0.063253 | 0.37927 | 4
Competitor 3 bid ratio | -0.055635 | 0.37876 | 5
Market factor | 0.15006 | 0.34343 | 6
4 How to read these results
• Expected profit counts every tender, won or lost: a low markup wins often but earns little or loses money, a high markup earns well but rarely wins. The best markup balances the two.
• Every competitor bids off the same true cost. When our estimate is too low, theirs mostly are not, so our bid looks cheap exactly when the job will cost us more: the chance of a loss on a won job is well above the chance that the cost exceeds our bid on any tender. That gap, in the last two columns, is the winner's curse.
• The market factor moves the true cost and every bid together, so it matters less to the decision than our own estimating error: the tornado chart shows where better estimating would pay off.
• Bid costs are paid on every tender, so a markup that almost never wins still has a small negative expected profit.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | Profit_2 | Profit_4 | Profit_6
1% | 99% | -1.592 | -0.79202 | -0.15
3% | 97% | -1.2366 | -0.43657 | -0.15
5% | 95% | -1.0301 | -0.23013 | -0.15
7% | 93% | -0.88452 | -0.15 | -0.15
9% | 91% | -0.76808 | -0.15 | -0.15
11% | 89% | -0.66053 | -0.15 | -0.15
13% | 87% | -0.57282 | -0.15 | -0.15
15% | 85% | -0.49447 | -0.15 | -0.15
17% | 83% | -0.4213 | -0.15 | -0.15
19% | 81% | -0.35233 | -0.15 | -0.15
21% | 79% | -0.28919 | -0.15 | -0.15
23% | 77% | -0.22946 | -0.15 | -0.15
25% | 75% | -0.17268 | -0.15 | -0.15
27% | 73% | -0.15 | -0.15 | -0.15
29% | 71% | -0.15 | -0.15 | -0.15
31% | 69% | -0.15 | -0.15 | -0.15
33% | 67% | -0.15 | -0.15 | -0.15
35% | 65% | -0.15 | -0.15 | -0.15
37% | 63% | -0.15 | -0.15 | -0.15
39% | 61% | -0.15 | -0.15 | -0.15
41% | 59% | -0.15 | -0.15 | -0.15
43% | 57% | -0.15 | -0.15 | -0.15
45% | 55% | -0.15 | -0.15 | -0.15
47% | 53% | -0.15 | -0.15 | -0.15
49% | 51% | -0.11744 | -0.15 | -0.15
51% | 49% | -0.067155 | -0.15 | -0.15
53% | 47% | -0.013772 | -0.15 | -0.15
55% | 45% | 0.031003 | -0.11138 | -0.15
57% | 43% | 0.084218 | 0.016237 | -0.15
59% | 41% | 0.14104 | 0.12162 | -0.15
61% | 39% | 0.19375 | 0.21543 | -0.15
63% | 37% | 0.24964 | 0.29675 | -0.15
65% | 35% | 0.29194 | 0.37389 | -0.15
67% | 33% | 0.34423 | 0.44805 | -0.15
69% | 31% | 0.39542 | 0.51488 | -0.15
71% | 29% | 0.44355 | 0.58414 | -0.15
73% | 27% | 0.49751 | 0.64506 | -0.15
75% | 25% | 0.54348 | 0.71006 | 0.031112
77% | 23% | 0.59308 | 0.77348 | 0.37418
79% | 21% | 0.64895 | 0.83506 | 0.59147
81% | 19% | 0.70344 | 0.90746 | 0.75824
83% | 17% | 0.75779 | 0.98445 | 0.89557
85% | 15% | 0.81987 | 1.0636 | 1.0282
87% | 13% | 0.89332 | 1.1339 | 1.147
89% | 11% | 0.95955 | 1.2274 | 1.2682
91% | 9% | 1.033 | 1.3191 | 1.3968
93% | 7% | 1.1377 | 1.4151 | 1.5252
95% | 5% | 1.2465 | 1.5533 | 1.6728
97% | 3% | 1.3877 | 1.7187 | 1.8809
99% | 1% | 1.6076 | 2.019 | 2.2342
Overall mean of ProfitDetail |  | 0.27368
Ranked input (chart) |  |  |  | Highest − mean | Lowest − mean
Our cost factor |  |  |  | 0.2161 | -0.37215
Competitor 2 bid ratio |  |  |  | 0.12178 | -0.35013
Competitor 4 bid ratio |  |  |  | 0.12473 | -0.33509
Competitor 1 bid ratio |  |  |  | 0.10559 | -0.33693
Competitor 3 bid ratio |  |  |  | 0.10508 | -0.32931
Market factor |  |  |  | 0.069754 | -0.12361

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
51
133
269
336
371
315
261
171
81
12
45
152
272
329
370
274
263
189
81
25
40
173
252
351
345
319
268
151
82
19
30
156
263
316
323
344
259
186
96
27
103
0
0
0
0
0
0
0
0
1897
1
21
67
173
354
457
553
290
75
9
822
0
0
0
0
0
0
0
0
1178
822
0
0
0
0
0
0
0
0
1178
235
0
0
0
0
0
0
0
0
1765
1
18
49
146
305
639
443
289
96
14
1175
0
0
0
0
0
0
0
0
825
1175
0
0
0
0
0
0
0
0
825
439
0
0
0
0
0
0
0
0
1561
1
15
42
125
255
818
400
248
87
9
1468
0
0
0
0
0
0
0
0
532
1468
0
0
0
0
0
0
0
0
532
681
0
0
0
0
0
0
0
0
1319
1
15
42
125
935
358
320
155
46
3
1723
0
0
0
0
0
0
0
0
277
1723
0
0
0
0
0
0
0
0
277
977
0
0
0
0
0
0
0
0
1023
1
15
42
1101
244
301
200
76
19
1
1872
0
0
0
0
0
0
0
0
128
1872
0
0
0
0
0
0
0
0
128
1228
0
0
0
0
0
0
0
0
772
1
8
23
1294
118
191
199
113
40
13
1956
0
0
0
0
0
0
0
0
44
1956
0
0
0
0
0
0
0
0
44
1470
0
0
0
0
0
0
0
0
530
1
8
1493
64
101
131
122
61
16
3
1984
0
0
0
0
0
0
0
0
16
1984
0
0
0
0
0
0
0
0
16
1668
0
0
0
0
0
0
0
0
332
1
1673
17
33
64
77
66
43
20
6
1999
0
0
0
0
0
0
0
0
1
1999
0
0
0
0
0
0
0
0
1
1803
0
0
0
0
0
0
0
0
197
1804
4
11
17
41
44
41
30
6
2
1999
0
0
0
0
0
0
0
0
1
1999
0
0
0
0
0
0
0
0
1
1903
0
0
0
0
0
0
0
0
97
1904
0
3
10
9
23
17
21
9
4
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
1959
0
0
0
0
0
0
0
0
41
1959
1
0
2
4
7
12
6
7
2
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
1
15
42
1101
244
301
200
76
19
1
72
200
301
359
326
303
230
132
56
21
63
177
279
375
353
304
216
156
60
17