## About
Rework and Change Orders |  | ModelRisk example · Projects and construction · PC-06
Is a 5% change allowance enough? Change orders and rework as a random number of events of random size.
Next: Inputs ▸
Model card
Industry | Projects and construction
Difficulty | ★★☆☆☆ Three classes of change, each a random number of events with random costs, added up with VoseAggregateMC.
Business question | Over a 24-month building contract worth US$60 million, client changes, design errors and rework will add cost. How much, how likely is the 5% change allowance to be exceeded, and what allowance would give 80% confidence?
Who it is for | Cost managers, quantity surveyors, contract administrators and clients setting change allowances.
Main outputs | Total cost of changes and rework: mean, P50 / P80 / P90 · the chance of exceeding the allowance · the allowance needed for 80% confidence · the number of change orders and its range · the contribution of each class.
ModelRisk techniques | Frequency × severity: a Poisson number of events per class, each with a Lognormal cost, summed by VoseAggregateMC · an uncertain event rate (Gamma), which makes the count more variable than Poisson (a Poisson–Gamma mixture) · P80 allowance.
File | PC-06 Rework and change orders · Version 1.0 · October 2026 · built with ModelRisk 10
The business question
A US$60 million school building will take 24 months. The cost plan carries a 5% allowance for changes, the usual figure. Changes come from three sources. The client will instruct changes — a few a month, but nobody knows the rate for this client, so the rate itself is uncertain. The design will have errors and omissions that the contractor is entitled to be paid for. And defective work will have to be redone. Each change is small on its own, but a few are expensive, and their number is uncertain. The model counts the events in each class, gives each one a cost, adds them up, and asks whether the 5% allowance is enough — and what allowance would be.
How the model works
Three sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | The contract sum, its duration and the allowance; for each class, the expected number of events per month and the mean and spread of an event's cost. The client's change rate has its own uncertainty.
2 Changes | The number of events in each class is Poisson with mean = rate × months (for client changes, the rate is first drawn from a Gamma). VoseAggregateMC then adds up that many Lognormal costs.
3 Results | The total change cost against the allowance, the allowance that would cover it with 80% confidence, the number of client change orders, and how each class contributes.
How to use it
Step 1 | Calibrate the rates and costs from the change logs of similar projects (number per month, average and spread of cost).
Step 2 | Set the contract sum, duration and allowance on the Inputs sheet.
Step 3 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set).
Step 4 | Compare the allowance with the P80 change cost; the drivers show which class to manage.
Workbook map
Inputs | Contract, duration and allowance; rates and costs of the three classes.
Changes | This iteration's counts and costs; outputs and checks.
Results | Change cost and the allowance, ranges by class, number of change orders, drivers.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Money | US$ million (US$m); event costs entered in US$m (0.045 = US$45,000).
Rates | Expected number of events per month of the contract.
Allowance | A percentage of the contract sum reserved for changes.
P80 | The cost with an 80% chance of not being exceeded.
Key assumptions and limitations
Events | Events occur at random through the contract (Poisson); costs are independent of each other and of their number.
Client rate | The client's average rate is uncertain (Gamma, 30% coefficient of variation): some clients change much more.
Scope | Only change and rework costs; their effect on time is not modelled (see PC-02 and PC-04).
Data | The project, rates and costs are invented for this example.
ModelRisk functions used
VosePoisson, VoseGamma | The number of events per class; the client's uncertain change rate.
VoseAggregateMC, VoseLognormalObject | The total cost of a random number of Lognormal events.
VoseInput, VoseOutput | Name the uncertain quantities and the outputs.
VoseSimMean, VoseSimPercentile, VoseSimProbability | Statistics of the simulation for the tables and charts on the Results sheet.
VoseSimSensitivityMean | The tornado chart: every VoseInput ranked by how far the mean total moves across its range.
Further reading
Change orders | Hanna, A. S. et al. (2002). Impact of change orders on labor efficiency for mechanical construction. Journal of Construction Engineering and Management 128(1), 57–64.
Aggregate distributions | Vose, D. (2008). Risk Analysis: A Quantitative Guide, 3rd edition. Wiley — chapter on aggregate distributions.
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Rework and Change Orders |  |  |  | ModelRisk example · Projects and construction · PC-06
INPUTS · Every assumption the model uses, with its uncertainty and its basis. Change only the yellow cells.
◂ About |  |  |  | Next: Changes ▸
How to read this sheet: yellow cells are inputs.
1 Contract
The contract the changes are measured against.
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
Contract sum | US$m | 60 | Fixed | Lump-sum building contract.
Contract duration | months | 24 | Fixed | Start on site to practical completion.
Change allowance | of the contract sum | 5% | Fixed | The usual allowance in the client's cost plan.
2 Client-instructed changes
Variations the client asks for. The client's rate is itself uncertain.
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
Expected changes per month | per month | 1.6 | Fixed | Similar school projects: 30 to 45 changes over two years.
Uncertainty of that rate | coefficient of variation | 30% | Fixed | Some clients change far more than others: the rate is drawn from a Gamma with this spread.
Mean cost of a change | US$m | 0.045 | Fixed | Change logs: US$45,000 on average.
Standard deviation of the cost | US$m | 0.08 | Fixed | Most are small, a few are large.
3 Design errors and omissions
Changes the design team causes and the client pays for.
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
Expected events per month | per month | 0.6 | Fixed | Design 85% complete at tender.
Mean cost of an event | US$m | 0.08 | Fixed
Standard deviation of the cost | US$m | 0.12 | Fixed
4 Rework of defects
Work that has to be redone; recovered from nobody.
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
Expected events per month | per month | 1.2 | Fixed | Quality records of the main contractor.
Mean cost of an event | US$m | 0.02 | Fixed
Standard deviation of the cost | US$m | 0.025 | Fixed

## Changes
Rework and Change Orders |  |  | ModelRisk example · Projects and construction · PC-06
CHANGES · This iteration: how many events of each class, and what they cost in total.
◂ Inputs |  |  | Next: Results ▸
1 Number and cost of events in this iteration
Count: Poisson(rate × months). Cost: VoseAggregateMC of that many Lognormal costs.
Quantity | Unit | Value | How it is calculated
Gamma shape of the client's rate |  | 11.1111 | 1 ÷ CV²: a Gamma's coefficient of variation is 1 ÷ √shape
Gamma scale of the client's rate | per month | 0.144 | Expected rate ÷ shape, so that shape × scale = the expected rate
Client's change rate in this iteration | per month | 1.8743 | VoseGamma(shape, scale): mean = the expected rate, spread = the coefficient of variation on Inputs
Client-instructed changes: number | events | 46 | Poisson with mean Client_RateDrawn × months. Not marked as an input: the class total below carries it
Client-instructed changes: total cost | US$m | 1.9201 | VoseAggregateMC: the sum of that many Lognormal event costs
Design errors and omissions: number | events | 18 | Poisson with mean Design_Rate × months. Not marked as an input: the class total below carries it
Design errors and omissions: total cost | US$m | 1.2657 | VoseAggregateMC: the sum of that many Lognormal event costs
Rework of defects: number | events | 25 | Poisson with mean Rework_Rate × months. Not marked as an input: the class total below carries it
Rework of defects: total cost | US$m | 0.45728 | VoseAggregateMC: the sum of that many Lognormal event costs
2 Value in this iteration
Key outputs, recorded by ModelRisk at every sample (VoseOutput). Their statistics appear on the Results sheet.
Output | Unit | Value | Meaning
Total cost of changes and rework | US$m | 3.6431 | Sum of the three classes.
Change allowance | US$m | 3 | From the Inputs sheet.
Exceeds the allowance? (1 = yes) | 1 / 0 | 1
Expected cost, calculated exactly | US$m | 3.456 | Rate × months × mean cost, summed: what the simulation's mean should match.
3 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
Rates, costs and spreads are positive |  | OK
The coefficient of variation of the client rate is above zero |  | OK

## Results
Rework and Change Orders | [6 empty] | ModelRisk example · Projects and construction · PC-06
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Changes
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 Is the allowance enough? | [5 empty] | Total cost of changes and rework — S-curve
The total cost of changes and rework against the allowance in the cost plan.
Measure | Unit | Value
Change allowance (Inputs sheet) | US$m | 3
Chance of exceeding the allowance | probability | 66.37%
P80 cost of changes and rework | US$m | 4.1757
Allowance needed for 80% confidence | of contract | 6.959%
Expected cost of changes and rework | US$m | 3.464
Expected cost, calculated exactly (check) | US$m | 3.456
2 Cost by class
P50 / P80 / P90: a 50%, 80% and 90% chance of not being exceeded.
Measure | Unit | P50 | P80 | P90 | Mean
Client-instructed changes | US$m | 1.6228 | 2.3143 | 2.7414 | 1.7313
Design errors and omissions | US$m | 1.0646 | 1.5509 | 1.8361 | 1.1544
Rework of defects | US$m | 0.55791 | 0.7142 | 0.80681 | 0.57823
Total | US$m | 3.3577 | 4.1757 | 4.6963 | 3.464
3 Number of events
10th percentile, median and 90th percentile.
Measure | Unit | 10th pct | Median | 90th pct | Mean
Client change orders | orders | 23 | 37 | 56 | 38.2937
Design errors and omissions | events | 10 | 14 | 20 | 14.4173
Rework items | events | 22 | 29 | 36 | 28.8837
4 What drives the total | [5 empty] | What drives the total change cost (US$m)
Lowest and highest mean total over ten equal groups of each input (VoseSimSensitivityMean), drawn from the overall mean.
Input (ranked by influence) | Lowest mean | Highest mean | Rank
Client-instructed changes: cost | 2.3936 | 5.0149 | 1
Design errors and omissions: cost | 2.7546 | 4.5806 | 2
Client change rate | 2.6765 | 4.435 | 3
Rework of defects: cost | 3.1752 | 3.7781 | 4
5 How to read these results
• The expected cost of changes is above the 5% allowance, so the allowance is more likely than not to be exceeded; the P80 shows what allowance would give 80% confidence.
• The client's change rate is uncertain, so the number of change orders varies much more than a Poisson count with a known rate would: a demanding client can double the count. The client's changes lead the tornado chart: their total cost has the longest bar, and the uncertain rate behind it one of the next. The tornado ranks only the rate and the class totals: the counts in between are part of the same chain, not separate causes.
• Rework items are frequent but small and similar in size, so their total is much more predictable than the cost of client changes, where a few large changes dominate.
• Change control that reduces the client's rate, or a more complete design at tender, attacks the drivers at the top of the ranking.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | TotalChange
1% | 99% | 1.7238
3% | 97% | 1.9502
5% | 95% | 2.0858
7% | 93% | 2.1976
9% | 91% | 2.285
11% | 89% | 2.362
13% | 87% | 2.4438
15% | 85% | 2.5141
17% | 83% | 2.578
19% | 81% | 2.6358
21% | 79% | 2.699
23% | 77% | 2.7526
25% | 75% | 2.802
27% | 73% | 2.8506
29% | 71% | 2.8963
31% | 69% | 2.9445
33% | 67% | 2.9868
35% | 65% | 3.03
37% | 63% | 3.0712
39% | 61% | 3.1178
41% | 59% | 3.1645
43% | 57% | 3.2075
45% | 55% | 3.2532
47% | 53% | 3.2965
49% | 51% | 3.3347
51% | 49% | 3.3785
53% | 47% | 3.4306
55% | 45% | 3.4742
57% | 43% | 3.5266
59% | 41% | 3.5797
61% | 39% | 3.6225
63% | 37% | 3.6726
65% | 35% | 3.7276
67% | 33% | 3.7839
69% | 31% | 3.8412
71% | 29% | 3.8922
73% | 27% | 3.9501
75% | 25% | 4.0134
77% | 23% | 4.0782
79% | 21% | 4.1428
81% | 19% | 4.2133
83% | 17% | 4.3036
85% | 15% | 4.4064
87% | 13% | 4.5193
89% | 11% | 4.6391
91% | 9% | 4.7863
93% | 7% | 4.9534
95% | 5% | 5.147
97% | 3% | 5.4838
99% | 1% | 6.2363
Overall mean of TotalChange |  | 3.464
Ranked input (chart) |  |  |  | Highest − mean | Lowest − mean
Client-instructed changes: cost |  |  |  | 1.5509 | -1.0704
Design errors and omissions: cost |  |  |  | 1.1166 | -0.70945
Client change rate |  |  |  | 0.971 | -0.78753
Rework of defects: cost |  |  |  | 0.31415 | -0.28879

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
39
273
555
571
354
145
51
8
2
2
401
882
522
147
36
7
4
0
0
1
374
824
512
202
59
13
6
8
1
1
34
244
514
559
359
183
65
23
14
5
108
594
753
379
129
22
10
3
1
1
665
0
0
0
0
0
0
0
0
1335