## About
Material Price Escalation and Procurement Strategy |  | ModelRisk example · Projects and construction · PC-07
Buy the steel now, as needed, or with a price cap? Material escalation on a fixed-price contract.
Next: Inputs ▸
Model card
Industry | Projects and construction
Difficulty | ★★★☆☆ Monthly steel and concrete price paths over 18 months and four ways of buying the steel, on the same paths.
Business question | A contractor has agreed a fixed price for a building that needs 12,000 tonnes of steel and 40,000 m³ of concrete over the next 18 months. Prices can rise. Should it buy all the steel forward now, half of it, cap the price, or buy as needed — and how much material risk remains in each case?
Who it is for | Contractors' commercial and procurement managers, estimators, and finance directors on fixed-price work.
Main outputs | Material cost under four steel strategies: mean, P90 and P99, the chance of staying within the tender allowance for all the materials and for the steel alone, and the cost of protection · the range of the steel price over the 18 months.
ModelRisk techniques | Monthly geometric Brownian motion with escalation (VoseTimeGBM) for steel and concrete · purchase profiles over time · forward contract, partial forward and price cap applied to the same price paths · fan chart of the price.
File | PC-07 Material price escalation and procurement strategy · Version 1.0 · October 2026 · built with ModelRisk 10
The business question
The contractor has signed a fixed-price contract for a commercial building. The tender allowed US$900 a tonne for structural steel and a 3% escalation allowance on concrete. Steel is bought from month 4 to month 12, concrete from month 2 to month 17, and both prices can move a long way in that time — steel especially. The steel supplier offers a forward contract at US$890 a tonne for the whole quantity; the bank offers a price cap at US$950 for a premium; or the contractor can buy as it goes and take the market price. Every option costs something: the forward price includes the supplier's carrying costs, the cap has a premium, and buying as needed carries the risk. The model simulates monthly prices and applies the four strategies to the same price paths.
How the model works
Three sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | Quantities and the months in which they are bought; for steel and concrete, today's price, the expected annual escalation and the volatility; the forward price, the share bought forward in the partial option, the cap and its premium; the tender allowances.
2 Purchases | VoseTimeGBM draws a monthly price path for each material, with drift set so that the expected price rises at the escalation rate. Steel bought in a month costs the month's price, the forward price, a blend, or the lower of the price and the cap plus the premium.
3 Results | Total material cost under each strategy: its mean, high percentiles, how much more or less it costs on average than buying at market prices, and the chance of staying within the tender allowance — for all the materials, and for the steel alone, which is what the strategies change.
How to use it
Step 1 | Enter your quantities, purchase months and the supplier's and bank's offers on the Inputs sheet.
Step 2 | Set the escalation and volatility from price indices and the futures market.
Step 3 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set).
Step 4 | Choose the strategy whose P90 (or P99) the business can live with, at an acceptable cost of protection.
Workbook map
Inputs | Quantities, timing, price models, offers and allowances.
Purchases | Monthly prices, quantities and costs; outputs and checks.
Results | Strategy comparison, S-curves, and the steel price fan chart.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Money | US$ million (US$m); prices in US$ per tonne of steel and per m³ of concrete.
Escalation | Expected annual price increase: the price model's drift is set so that the mean price grows at this rate.
Forward contract | A fixed price agreed now for delivery later.
Price cap | Pays the market price up to the cap, never more; costs a premium per tonne.
Key assumptions and limitations
Prices | Geometric Brownian motion with constant volatility; steel and concrete prices are independent.
Quantities | Quantities and purchase months are certain; no programme slippage (see PC-04).
Offers | No credit or delivery risk on the forward contract; storage is the supplier's.
Data | Prices, quantities and offers are invented for this example.
ModelRisk functions used
VoseTimeGBM | Monthly steel and concrete price paths with escalation, as array formulas.
VoseOutput | Name the strategy totals and the monthly steel prices for the Results Viewer.
VoseSimMean, VoseSimPercentile, VoseSimProbability | Statistics of the simulation for the tables and charts on the Results sheet.
Further reading
Escalation | AACE International (2008). Recommended Practice 58R-10: Escalation Estimating Principles and Methods Using Indices.
Hedging | Hull, J. C. (2022). Options, Futures, and Other Derivatives, 11th edition. Pearson.
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Material Price Escalation and Procurement Strategy |  |  |  | ModelRisk example · Projects and construction · PC-07
INPUTS · Every assumption the model uses, with its uncertainty and its basis. Change only the yellow cells.
◂ About |  |  |  | Next: Purchases ▸
How to read this sheet: yellow cells are inputs.
1 Quantities and timing
What is bought, and in which months (evenly between the first and last month).
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
Structural steel | tonnes | 12000 | Fixed | From the bill of quantities.
Steel: first month | month | 4 | Fixed | Frame erection starts in month 5.
Steel: last month | month | 12 | Fixed
Concrete | m³ | 40000 | Fixed | Foundations, slabs and cores.
Concrete: first month | month | 2 | Fixed
Concrete: last month | month | 17 | Fixed
2 Steel price
Monthly geometric Brownian motion; the expected price grows at the escalation rate.
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
Steel price today | US$/t | 850 | Fixed | Supplier's current list price for sections.
Expected escalation | per year | 4% | Fixed | Consensus forecast of construction-steel prices.
Volatility | per year | 25% | Fixed | Steel prices have moved this much in a typical year.
3 Concrete price
Less volatile, but escalates with labour and cement costs.
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
Concrete price today | US$/m³ | 120 | Fixed | Ready-mix supply agreement, indexed.
Expected escalation | per year | 5% | Fixed | Cement and haulage indices.
Volatility | per year | 6% | Fixed
4 Steel procurement offers
Ways to buy the steel other than at market prices.
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
Forward contract price | US$/t | 890 | Fixed | Supplier's offer for all deliveries; includes carrying costs.
Share bought forward in the partial option |  | 50% | Fixed | The rest is bought at market prices.
Price cap | US$/t | 950 | Fixed | The bank pays any excess of the market price over the cap.
Cap premium | US$/t | 45 | Fixed | Paid on every tonne, whatever happens to the price.
5 Tender allowances
What the fixed price assumed.
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
Steel allowance | US$/t | 900 | Fixed
Concrete: escalation allowed in the tender |  | 3% | Fixed | On today's price.
Concrete allowance | US$/m³ | 123.6 | Calculated | Today's price plus the escalation allowed.

## Purchases
Material Price Escalation and Procurement Strategy | [20 empty] | ModelRisk example · Projects and construction · PC-07
PURCHASES · 18 months of prices and purchases, and the steel cost under each strategy (US$m).
◂ Inputs | [20 empty] | Next: Results ▸
Month |  | Total | Open | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 Price model
Monthly drift and volatility from the annual figures.
Quantity | Unit | Value |  | How it is calculated
Steel: monthly volatility |  | 7.217% |  | Annual volatility ÷ √12
Steel: monthly drift of the log price |  | 0.06642% |  | Set so that the expected price grows at the escalation rate
Concrete: monthly volatility |  | 1.732%
Concrete: monthly drift of the log price |  | 0.3916%
2 Prices and quantities
Price paths from VoseTimeGBM. Quantities spread evenly over the purchase months.
Steel price | US$/t |  |  | 793.8573 | 768.698 | 767.7972 | 801.9948 | 804.725 | 824.9277 | 775.2038 | 788.7542 | 782.3953 | 861.2503 | 925.6434 | 850.4355 | 837.3913 | 827.6823 | 898.0452 | 903.9655 | 879.9311 | 785.6165
Concrete price | US$/m³ |  |  | 124.1439 | 124.8234 | 123.7406 | 124.3058 | 126.0489 | 124.4231 | 122.672 | 121.0822 | 122.9481 | 123.442 | 123.9803 | 125.2922 | 129.5916 | 132.6527 | 132.5699 | 127.7096 | 123.0518 | 117.2733
Steel bought | tonnes | 12000 |  | 0 | 0 | 0 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 0 | 0 | 0 | 0 | 0 | 0
Concrete bought | m³ | 40000 |  | 0 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 0
3 Cost of the steel under each strategy
Same tonnes, same price path, different terms.
Buy at market prices | US$m | 9.8871 |  | 0 | 0 | 0 | 1.0693 | 1.073 | 1.0999 | 1.0336 | 1.0517 | 1.0432 | 1.1483 | 1.2342 | 1.1339 | 0 | 0 | 0 | 0 | 0 | 0
Forward contract for all | US$m | 10.68 |  | 0 | 0 | 0 | 1.1867 | 1.1867 | 1.1867 | 1.1867 | 1.1867 | 1.1867 | 1.1867 | 1.1867 | 1.1867 | 0 | 0 | 0 | 0 | 0 | 0
Forward contract for part | US$m | 10.2836 |  | 0 | 0 | 0 | 1.128 | 1.1298 | 1.1433 | 1.1101 | 1.1192 | 1.1149 | 1.1675 | 1.2104 | 1.1603 | 0 | 0 | 0 | 0 | 0 | 0
Price cap | US$m | 10.4271 |  | 0 | 0 | 0 | 1.1293 | 1.133 | 1.1599 | 1.0936 | 1.1117 | 1.1032 | 1.2083 | 1.2942 | 1.1939 | 0 | 0 | 0 | 0 | 0 | 0
Concrete (same for all strategies) | US$m | 5.0208 |  | 0 | 0.31206 | 0.30935 | 0.31076 | 0.31512 | 0.31106 | 0.30668 | 0.30271 | 0.30737 | 0.3086 | 0.30995 | 0.31323 | 0.32398 | 0.33163 | 0.33142 | 0.31927 | 0.30763 | 0
4 Steel price outputs
Each month's steel price is an output, for the fan chart on the Results sheet.
Steel price (output) | US$/t |  |  | 793.8573 | 768.698 | 767.7972 | 801.9948 | 804.725 | 824.9277 | 775.2038 | 788.7542 | 782.3953 | 861.2503 | 925.6434 | 850.4355 | 837.3913 | 827.6823 | 898.0452 | 903.9655 | 879.9311 | 785.6165
5 Value in this iteration
Key outputs, recorded by ModelRisk at every sample (VoseOutput). Their statistics appear on the Results sheet.
Output | Unit | Value |  | Meaning
Material cost: buy at market prices as needed | US$m | 14.9079 |  | Steel under this strategy plus concrete.
Material cost: forward contract for all the steel | US$m | 15.7008
Material cost: partial forward contract | US$m | 15.3044
Material cost: price cap on the steel | US$m | 15.4479
Steel cost: buy at market prices as needed | US$m | 9.8871 |  | The steel alone: what the strategies change.
Steel cost: forward contract for all the steel | US$m | 10.68
Steel cost: partial forward contract | US$m | 10.2836
Steel cost: price cap on the steel | US$m | 10.4271
Tender allowance for materials | US$m | 15.744 |  | Steel and concrete at the allowances.
Tender allowance for the steel | US$m | 10.8
Average steel price paid at market | US$/t | 823.9255 |  | Weighted by the tonnes bought each month.
6 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
Purchase months are within the 18 months and in order |  | OK
All the steel and concrete is bought |  | OK

## Results
Material Price Escalation and Procurement Strategy | [6 empty] | ModelRisk example · Projects and construction · PC-07
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Purchases
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 Which steel strategy? | [5 empty] | Material cost — cumulative probability
Total material cost (steel and concrete) under each strategy, on the same simulated prices (US$m).
Strategy | Mean | P90 | P99 | Mean vs
| US$m | US$m | US$m | market, US$m
Buy at market prices as needed | 15.4569 | 18.0696 | 20.8626 | 0
Forward contract for all the steel | 15.6734 | 15.9725 | 16.2196 | 0.21653
Forward contract for 50% of the steel | 15.5652 | 16.9015 | 18.3178 | 0.10826
Price cap on the steel | 15.5004 | 16.9321 | 17.2928 | 0.043466
2 Within the allowances?
Concrete costs the same under every strategy, so the steel column shows what the choice of strategy changes.
Strategy | All materials | Steel alone
| within allowance | within allowance
Buy at market prices as needed | 58.86% | 60.3%
Forward contract for all the steel | 62.74% | 99.99%
Forward contract for 50% of the steel | 60.15% | 62.56%
Price cap on the steel | 49.26% | 50.43%
Measure | Unit | Value
Tender allowance for materials | US$m | 15.744
…of which steel | US$m | 10.8
3 The steel price
The average price paid at market, and the monthly price range.
Measure | Unit | 10th pct | Median | 90th pct | Mean
Average steel price paid at market | US$/t | 676.9442 | 857.355 | 1087.4224 | 871.9559
4 How to read these results | [5 empty] | Steel price by month — 10th to 90th percentile
• Buying at market prices is cheapest on average when the offers include a margin, but it leaves the whole steel price risk: its P90 and P99 are the highest. A forward contract removes the steel risk at a small expected cost.
• The cap protects against high prices and keeps the benefit of low ones. Its premium is paid on every tonne, so its mean is close to buying at market and its chance of staying within the allowance is the lowest — but steel can never cost more than the cap plus the premium, so its worst cases are bounded.
• Even with all the steel bought forward, some risk remains: concrete escalation, which limits the chance for all the materials. The steel-alone column isolates the decision: as shipped, the forward contract keeps the steel within its allowance every time, the partial forward about 63% of the time, buying at market about 60% and the cap about 50%.
• The fan chart shows why timing matters: the later the steel is bought, the wider the range of its price.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | Total_Spot | Total_Fwd | Total_Half | Total_Cap
1% | 99% | 11.5901 | 15.172 | 13.5756 | 12.1301
3% | 97% | 12.2275 | 15.2653 | 13.9171 | 12.7675
5% | 95% | 12.5421 | 15.3108 | 14.0786 | 13.0821
7% | 93% | 12.7887 | 15.3438 | 14.2012 | 13.3287
9% | 91% | 13.0002 | 15.3717 | 14.3084 | 13.5402
11% | 89% | 13.1621 | 15.3963 | 14.3969 | 13.7019
13% | 87% | 13.3171 | 15.4175 | 14.4675 | 13.8571
15% | 85% | 13.4611 | 15.4366 | 14.5436 | 14.0011
17% | 83% | 13.5973 | 15.4541 | 14.6081 | 14.1373
19% | 81% | 13.7085 | 15.4705 | 14.6686 | 14.2485
21% | 79% | 13.8282 | 15.4863 | 14.7339 | 14.3682
23% | 77% | 13.9406 | 15.5009 | 14.7905 | 14.4801
25% | 75% | 14.0504 | 15.516 | 14.8462 | 14.5888
27% | 73% | 14.1577 | 15.5293 | 14.9013 | 14.6921
29% | 71% | 14.2612 | 15.5414 | 14.9479 | 14.7986
31% | 69% | 14.3625 | 15.553 | 15.0071 | 14.8957
33% | 67% | 14.4589 | 15.5655 | 15.055 | 14.9919
35% | 65% | 14.5538 | 15.5783 | 15.1073 | 15.0853
37% | 63% | 14.6497 | 15.59 | 15.1549 | 15.1786
39% | 61% | 14.7392 | 15.6012 | 15.2086 | 15.2635
41% | 59% | 14.8254 | 15.6146 | 15.2578 | 15.3492
43% | 57% | 14.9417 | 15.6258 | 15.3057 | 15.4534
45% | 55% | 15.0362 | 15.6375 | 15.3538 | 15.5458
47% | 53% | 15.1354 | 15.6488 | 15.4054 | 15.6418
49% | 51% | 15.2365 | 15.662 | 15.4572 | 15.7286
51% | 49% | 15.3361 | 15.673 | 15.51 | 15.8163
53% | 47% | 15.4352 | 15.6855 | 15.561 | 15.8924
55% | 45% | 15.5376 | 15.6979 | 15.6111 | 15.9711
57% | 43% | 15.6429 | 15.7082 | 15.6619 | 16.0615
59% | 41% | 15.7459 | 15.7207 | 15.7154 | 16.139
61% | 39% | 15.8436 | 15.7318 | 15.7696 | 16.2082
63% | 37% | 15.9499 | 15.7452 | 15.8239 | 16.2751
65% | 35% | 16.0508 | 15.7581 | 15.8773 | 16.3304
67% | 33% | 16.1594 | 15.7709 | 15.9302 | 16.392
69% | 31% | 16.2639 | 15.7837 | 15.98 | 16.4479
71% | 29% | 16.3698 | 15.7967 | 16.0507 | 16.5028
73% | 27% | 16.4956 | 15.8115 | 16.1103 | 16.5523
75% | 25% | 16.6445 | 15.8263 | 16.1755 | 16.6036
77% | 23% | 16.783 | 15.8413 | 16.2417 | 16.6518
79% | 21% | 16.92 | 15.8573 | 16.3246 | 16.6946
81% | 19% | 17.0863 | 15.8738 | 16.4004 | 16.7403
83% | 17% | 17.2833 | 15.8916 | 16.4992 | 16.7816
85% | 15% | 17.5161 | 15.9117 | 16.5993 | 16.8242
87% | 13% | 17.719 | 15.9359 | 16.7124 | 16.8642
89% | 11% | 17.9289 | 15.9604 | 16.8318 | 16.9082
91% | 9% | 18.205 | 15.984 | 16.9742 | 16.9554
93% | 7% | 18.5336 | 16.0162 | 17.1298 | 17.0173
95% | 5% | 18.9568 | 16.0605 | 17.3604 | 17.0838
97% | 3% | 19.6306 | 16.1139 | 17.6949 | 17.1619
99% | 1% | 20.8626 | 16.2196 | 18.3178 | 17.2928
Period | 10th percentile | Median | 90th percentile | Mean
1 | 775.5598 | 850.6214 | 933.2767 | 853.1751
2 | 746.2561 | 850.3302 | 970.1699 | 855.3511
3 | 725.0353 | 853.3435 | 1003.6811 | 859.837
4 | 704.3234 | 853.4454 | 1031.3615 | 861.8331
5 | 690.2672 | 852.4985 | 1050.928 | 863.2432
6 | 680.5827 | 852.4269 | 1068.9003 | 866.0446
7 | 667.6959 | 854.7537 | 1089.6298 | 868.6787
8 | 655.2943 | 853.9649 | 1107.9588 | 870.2932
9 | 646.7552 | 853.2041 | 1127.0238 | 874.0718
10 | 638.5623 | 853.6926 | 1149.3297 | 877.3423
11 | 629.5811 | 853.8887 | 1168.0681 | 880.996
12 | 621.7693 | 856.3728 | 1185.2411 | 885.0264
13 | 613.1828 | 856.465 | 1197.9751 | 887.8218
14 | 604.7342 | 858.8101 | 1219.2204 | 891.039
15 | 599.9134 | 858.4105 | 1229.7092 | 894.2502
16 | 592.7773 | 860.2865 | 1252.748 | 896.8756
17 | 586.7911 | 859.1905 | 1264.8638 | 900.2557
18 | 579.2326 | 859.908 | 1280.8512 | 903.4654

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
7
40
183
432
552
451
224
79
24
8
35
155
334
499
467
278
157
48
21
6
23
133
350
545
486
290
121
40
11
1
10
67
273
444
510
365
189
100
28
14
27
169
412
528
435
238
124
46
15
6
17
162
469
577
455
206
75
27
10
2
49
247
545
598
327
156
56
15
6
1
49
257
562
533
358
151
59
20
5
6
20
220
608
599
334
144
57
11
5
2
24
236
634
572
336
131
49
14
3
1
31
346
693
524
267
99
31
7
1
1
36
268
541
548
295
194
70
28
13
7
66
366
616
497
270
112
41
23
6
3
116
496
649
430
191
79
24
12
2
1
78
471
718
440
175
79
28
10
0
1
60
505
731
437
165
65
27
8
1
1
83
564
745
384
142
50
27
2
2
1
147
758
678
286
88
28
13
0
1
1
40
243
569
557
342
163
62
14
7
3
7
25
113
317
528
488
329
151
37
5
34
189
508
575
381
198
87
16
9
3
12
22
61
122
220
260
295
346
541
121
31
246
572
574
335
171
51
11
6
3
0
0
0
0
0
2000
0
0
0
0
31
246
572
574
335
171
51
11
6
3
7
14
38
84
144
195
270
273
290
685
31
246
572
574
335
171
51
11
6
3