## About
Construction Cash Flow and Peak Funding |  | ModelRisk example · Projects and construction · PC-08
Is a US$40 million facility enough? A developer's monthly cash flow, peak funding and profit.
Next: Inputs ▸
Model card
Industry | Projects and construction
Difficulty | ★★★★☆ A 48-month cash flow with S-curve spend, off-plan sales and a revolving facility with monthly interest.
Business question | A developer is building 120 apartments with US$15 million of equity and a US$40 million bank facility. The construction cost and duration are uncertain, and so are the pace and the price of off-plan sales. How large will the peak funding need be, how likely is it to exceed the facility, and what profit will the scheme make?
Who it is for | Developers, development and project finance teams, lenders, and development managers.
Main outputs | Peak funding: mean, P80, P90 and the month it occurs · the chance of exceeding the facility · the drawn balance by month with its range · profit and profit on cost · what drives the peak and the profit.
ModelRisk techniques | S-curve of construction spend (cumulative Beta) over an uncertain duration · off-plan sales with deposits and balances at completion · a revolving facility drawn and repaid month by month with interest · fan chart of the drawn balance · two tornado charts.
File | PC-08 Construction cash flow and peak funding · Version 1.0 · October 2026 · built with ModelRisk 10
The business question
A developer has bought a site for US$8 million and will build 120 apartments over about 30 months: a construction contract of about US$45 million, plus its own fees, site costs and sales office at US$120,000 a month while building. It puts in US$15 million of equity, and the bank offers a US$40 million revolving facility at 7%. Construction spend follows the familiar S-curve: slow at first, fastest a little before mid-way, slow at the end. Off-plan buyers pay a 10% deposit when they sign and the balance at completion; apartments still unsold at completion are sold afterwards at a discount. The funding need peaks at completion, when the money has been spent and only the deposits have come in. The model simulates the monthly cash flow and the facility, and asks whether US$40 million is enough.
How the model works
Three sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | The land cost and the equity; the facility limit and its interest rate; the construction cost and duration (PERT), the shape of the S-curve and the monthly overheads; the number of apartments, today's price and a market factor, the off-plan sales pace, the deposit, and the sales after completion.
2 Cash flow | Each month, construction spend = cost × the increase in the S-curve (the cumulative Beta distribution of the month ÷ the duration), plus the overheads while building. Receipts are deposits on new contracts, the balances the month after completion, and later sales. Cash is used first; the facility is drawn when cash runs out and repaid from receipts, and interest is charged on the drawn balance.
3 Results | Peak funding and when it occurs, the chance that it exceeds the facility, the drawn balance by month, profit after interest, and what drives the peak and the profit.
How to use it
Step 1 | Enter your scheme's land, equity, facility, cost, duration and sales assumptions on the Inputs sheet.
Step 2 | Press F9 on the Cash flow sheet to see other monthly profiles; the chart beside the outputs shows each one.
Step 3 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set).
Step 4 | Size the facility at the confidence the lender requires, or use the drivers to bring the peak down.
Workbook map
Inputs | Site and finance, construction, and sales.
Cash flow | This iteration's single values, then 48 months of spend, sales, funding and interest; outputs, checks and a chart.
Results | Peak funding against the facility, drawn balance fan chart, profit, and the drivers of each.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Money | US$ million (US$m); apartment prices in US$ thousand.
Months | Month 1 is the first month of construction. The Open column is the position at the start: equity paid in, land bought.
Facility | A revolving loan: drawn when cash runs out, repaid from receipts, interest charged monthly on the drawn balance.
Peak funding | The largest drawn balance at any month-end.
Key assumptions and limitations
Spend | Construction cost follows a cumulative Beta S-curve over the duration; overheads are paid monthly while building; no retention or payment delays.
Sales | Off-plan sales at a steady average pace until completion, balances paid the month after; the rest sold later at a fixed pace and discount.
Finance | One interest rate, no fees, covenants or tax; the equity is used before the facility.
Independence | Cost, duration, sales pace and prices are independent of each other (PC-04 links cost and schedule through shared risks).
Data | The scheme and all figures are invented for this example.
ModelRisk functions used
VosePERT | Construction cost and duration, the market price factor and the off-plan sales pace.
VoseBetaProb | The S-curve: the cumulative share of the construction cost spent by each month.
VoseInput, VoseOutput | Name the uncertain inputs and the outputs, including the drawn balance in every month.
VoseSimMean, VoseSimPercentile, VoseSimProbability | Statistics of the simulation for the tables and charts on the Results sheet.
VoseSimSensitivityMean | The two tornado charts: every VoseInput ranked by how far the mean peak funding, and the mean profit, move across its range.
Further reading
Cash flow | Kenley, R. (2003). Financing Construction: Cash Flows and Cash Farming. Spon Press.
Development appraisal | Havard, T. (2014). Financial Feasibility Studies for Property Development: Theory and Practice. Routledge.
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Construction Cash Flow and Peak Funding | [7 empty] | ModelRisk example · Projects and construction · PC-08
INPUTS · Every assumption the model uses, with its uncertainty and its basis. Change only the yellow cells.
◂ About | [7 empty] | Next: Cash flow ▸
How to read this sheet: yellow cells are inputs. Orange cells hold ModelRisk distributions and show the current random sample (press F9 to draw again). Low / Most likely / High are the minimum, most likely and maximum for PERT. Mean is the distribution's average (VoseMean); it shows ✗ if a range is out of order.
1 Site, equity and finance
Money in at the start, and the bank facility.
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Land (paid at the start) | US$m | 8 | Fixed |  |  |  |  | Site bought with planning consent.
Developer's equity | US$m | 15 | Fixed |  |  |  |  | Paid in at the start; used before the facility.
Facility limit | US$m | 40 | Fixed |  |  |  |  | Revolving construction loan offered by the bank.
Interest rate | per year | 7% | Fixed |  |  |  |  | Charged monthly on the drawn balance.
Confidence the bank requires | probability | 90% | Fixed |  |  |  |  | The Results sheet tests the facility against the peak funding at this confidence.
2 Construction
Cost and duration, the shape of the spend profile, and the developer's own monthly costs.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Construction cost | US$m | 47.1905 | PERT | 42 | 45 | 52 | 45.6667 | Contract sum with design, ground and market risk.
Construction duration | months | 30.9998 | PERT | 26 | 30 | 36 | 30.3333 | Rounded to whole months in the model.
S-curve shape: α |  | 2.2 | Fixed |  |  |  |  | With β: a typical S-curve, steepest a little before mid-way.
S-curve shape: β |  | 2.6 | Fixed
Developer's overheads while building | US$m per month | 0.12 | Fixed |  |  |  |  | Fees, site costs, insurance and the sales office.
3 Sales
Off-plan sales during construction, the rest after completion.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Apartments | units | 120 | Fixed
Average price per apartment today | US$ thousand | 580 | Fixed |  |  |  |  | Agent's appraisal at today's values.
Market price factor at completion | × today | 1.0198 | PERT | 0.9 | 1 | 1.1 | 1 | Prices at completion relative to today.
Off-plan sales pace | units per month | 4.4594 | PERT | 3 | 5 | 8 | 5.1667 | An average, so the Cash flow sheet shows fractions of an apartment.
Off-plan sales start | month | 4 | Fixed |  |  |  |  | When the sales office opens.
Deposit on signing | of the price | 10% | Fixed |  |  |  |  | The balance is paid the month after completion.
Sales after completion | units per month | 6 | Fixed |  |  |  |  | Finished apartments sell faster.
Discount on sales after completion | of the price | 5% | Fixed |  |  |  |  | Incentives to clear the stock.

## Cash flow
Construction Cash Flow and Peak Funding | [50 empty] | ModelRisk example · Projects and construction · PC-08
CASH FLOW · Monthly spend, receipts, funding and interest (US$m).
◂ Inputs | [50 empty] | Next: Results ▸
Month |  | Total | Open | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
1 This iteration's single values
Quantity | Unit | Value |  | How it is calculated
Construction duration in whole months | months | 31 |  | The duration on the Inputs sheet, rounded
Average price per apartment at completion | US$m | 0.5915 |  | Today's price × market factor, in US$ million
Apartments sold off-plan by completion | units | 120 |  | Sales pace × months of off-plan selling, at most all the apartments
Monthly interest rate |  | 0.5833% |  | Annual rate ÷ 12
2 Spend
Cumulative share spent = VoseBetaProb(month ÷ duration, α, β, TRUE); overheads while building.
Cumulative share of the construction cost |  |  | 0% | 0.26% | 1.152% | 2.707% | 4.907% | 7.709% | 11.06% | 14.91% | 19.17% | 23.8% | 28.72% | 33.86% | 39.15% | 44.52% | 49.92% | 55.27% | 60.51% | 65.59% | 70.45% | 75.05% | 79.33% | 83.26% | 86.81% | 89.95% | 92.65% | 94.91% | 96.73% | 98.11% | 99.08% | 99.67% | 99.94% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Construction spend | US$m | 47.1905 |  | 0.12271 | 0.42084 | 0.73404 | 1.0379 | 1.3225 | 1.5822 | 1.8137 | 2.0146 | 2.1839 | 2.3207 | 2.4249 | 2.4967 | 2.5365 | 2.5453 | 2.5241 | 2.4742 | 2.397 | 2.2945 | 2.1686 | 2.0216 | 1.8559 | 1.6743 | 1.48 | 1.2764 | 1.0674 | 0.85746 | 0.65165 | 0.45615 | 0.27863 | 0.12953 | 0.02649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Developer's overheads | US$m | 3.72 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total spend | US$m | 50.9105 |  | 0.24271 | 0.54084 | 0.85404 | 1.1579 | 1.4425 | 1.7022 | 1.9337 | 2.1346 | 2.3039 | 2.4407 | 2.5449 | 2.6167 | 2.6565 | 2.6653 | 2.6441 | 2.5942 | 2.517 | 2.4145 | 2.2886 | 2.1416 | 1.9759 | 1.7943 | 1.6 | 1.3964 | 1.1874 | 0.97746 | 0.77165 | 0.57615 | 0.39863 | 0.24953 | 0.14649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 Sales receipts
Deposits on signing, balances the month after completion, then later sales.
Months of off-plan selling so far | months |  |  | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
Off-plan contracts, cumulative | units |  | 0 | 0 | 0 | 0 | 4.4594 | 8.9188 | 13.3783 | 17.8377 | 22.2971 | 26.7565 | 31.216 | 35.6754 | 40.1348 | 44.5942 | 49.0537 | 53.5131 | 57.9725 | 62.4319 | 66.8914 | 71.3508 | 75.8102 | 80.2696 | 84.7291 | 89.1885 | 93.6479 | 98.1073 | 102.5668 | 107.0262 | 111.4856 | 115.945 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
Months since completion | months |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Sales after completion, cumulative | units |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Deposits | US$m | 7.098 |  | 0 | 0 | 0 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.23985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balances at completion | US$m | 63.8823 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.8823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales after completion | US$m | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total receipts | US$m | 70.9803 |  | 0 | 0 | 0 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.26378 | 0.23985 | 0 | 63.8823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 Funding
One running balance: cash in hand when positive, the facility drawn when negative. Interest is charged on what was drawn at the end of the month before.
Interest on the drawn balance | US$m | 3.5509 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0098565 | 0.021814 | 0.03464 | 0.048149 | 0.062155 | 0.076475 | 0.09093 | 0.10535 | 0.11955 | 0.1334 | 0.14672 | 0.15939 | 0.17127 | 0.18226 | 0.19225 | 0.20117 | 0.20895 | 0.21555 | 0.22097 | 0.22522 | 0.22836 | 0.23048 | 0.23188 | 0.23409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance: cash in hand − facility drawn | US$m |  | 7 | 6.7573 | 6.2164 | 5.3624 | 4.4683 | 3.2895 | 1.851 | 0.18116 | -1.6897 | -3.7396 | -5.9383 | -8.2541 | -10.6551 | -13.11 | -15.588 | -18.0593 | -20.495 | -22.8679 | -25.152 | -27.3236 | -29.3607 | -31.2441 | -32.9569 | -34.4854 | -35.8193 | -36.9519 | -37.8811 | -38.61 | -39.1476 | -39.5108 | -39.7509 | -40.1293 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189
Facility drawn at month-end | US$m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6897 | 3.7396 | 5.9383 | 8.2541 | 10.6551 | 13.11 | 15.588 | 18.0593 | 20.495 | 22.8679 | 25.152 | 27.3236 | 29.3607 | 31.2441 | 32.9569 | 34.4854 | 35.8193 | 36.9519 | 37.8811 | 38.61 | 39.1476 | 39.5108 | 39.7509 | 40.1293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash in hand at month-end | US$m |  |  | 6.7573 | 6.2164 | 5.3624 | 4.4683 | 3.2895 | 1.851 | 0.18116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189 | 23.5189
Facility drawn (output, for the fan chart) | US$m |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6897 | 3.7396 | 5.9383 | 8.2541 | 10.6551 | 13.11 | 15.588 | 18.0593 | 20.495 | 22.8679 | 25.152 | 27.3236 | 29.3607 | 31.2441 | 32.9569 | 34.4854 | 35.8193 | 36.9519 | 37.8811 | 38.61 | 39.1476 | 39.5108 | 39.7509 | 40.1293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 Value in this iteration | [13 empty] | This iteration: spend and facility drawn by month (F9 for another)
Key outputs, recorded at every sample (VoseOutput); statistics on the Results sheet.
Output | Unit | Value |  | Meaning
Peak funding (largest drawn balance) | US$m | 40.1293 |  | The facility this iteration needs.
Month of the peak | month | 31
Peak above the facility? (1 = yes) | 1 / 0 | 1
Interest paid | US$m | 3.5509
Profit after interest | US$m | 8.5189 |  | Receipts less the land, the spend and the interest.
Profit on cost |  | 13.64% |  | Profit ÷ (land + spend + interest).
6 Model checks
Should all read OK. A CHECK means an input is outside the range the model is built for.
All the construction cost is spent within the 48 months |  | OK
All the apartments are sold within the 48 months |  | OK
The facility is repaid by month 48 |  | OK

## Results
Construction Cash Flow and Peak Funding | [6 empty] | ModelRisk example · Projects and construction · PC-08
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Cash flow
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 Peak funding | [5 empty] | Peak funding — cumulative probability
The largest drawn balance, against the facility the bank offers.
Measure | Unit | Value
Facility limit (Inputs sheet) | US$m | 40
Mean peak funding | US$m | 38.5821
Chance that the peak exceeds the facility | probability | 25.16%
Median month of the peak | month | 30
2 Sizing the facility
The facility needed for each chance of it being enough: percentiles of the peak funding.
Measure | Unit | Value
For a 50% chance of being enough | US$m | 38.4078
For an 80% chance | US$m | 40.4085
For a 90% chance | US$m | 41.5126
For a 95% chance | US$m | 42.295
For a 99% chance | US$m | 43.6668
For the 90% the bank requires (Inputs sheet) | US$m | 41.5126 |  |  |  | Facility drawn by month — 10th to 90th percentile
Is the facility enough at 90% confidence? |  | No: that peak is above it
3 Profit
After interest and the return of the equity.
Measure | Unit | 10th pct | Median | 90th pct | Mean
Profit after interest | US$m | 4.5107 | 8.9754 | 13.3887 | 8.9526
Profit on cost |  | 7.212% | 14.83% | 22.67% | 14.91%
Interest paid | US$m | 2.9161 | 3.2608 | 3.6603 | 3.2773
Chance of a loss | probability |  |  |  | 0.25%
4 What drives the peak funding | [5 empty] | What drives the peak funding (US$m)
Lowest and highest mean peak funding over ten equal groups of each input (VoseSimSensitivityMean), drawn from the overall mean.
Input (ranked by influence) | Lowest mean | Highest mean | Rank
Construction cost | 35.553 | 42.3409 | 1
Off-plan sales pace | 38.1805 | 39.7939 | 2
Construction duration | 38.0426 | 39.2199 | 3
Market price factor | 37.9731 | 39.0809 | 4
5 What drives the profit | [5 empty] | What drives the profit (US$m)
Lowest and highest mean profit over ten equal groups of each input (VoseSimSensitivityMean), drawn from the overall mean.
Input (ranked by influence) | Lowest mean | Highest mean | Rank
Market price factor | 4.3968 | 13.5926 | 1
Construction cost | 5.1653 | 12.0559 | 2
Construction duration | 8.2369 | 9.688 | 3
Off-plan sales pace | 8.1869 | 9.3015 | 4
6 How to read these results
• The funding need peaks at completion: the construction cost has been spent, but only the deposits have come in. The balances paid the month after completion repay the facility in one go.
• A facility sized on the average peak leaves a real chance of running out of money at the worst moment, just before completion. Sizing it at the P90, or agreeing headroom with the bank, removes most of that risk.
• The construction cost drives the peak almost on its own. Faster off-plan sales and higher prices lower it a little through larger deposits; a longer programme raises it a little, with more interest and overheads partly offset by more deposits.
• The profit depends on the market as much as on the cost. Prices hardly move the peak, because only the deposits arrive before it, but they move the profit almost one for one.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | PeakFunding
1% | 99% | 34.6417
3% | 97% | 35.1042
5% | 95% | 35.3958
7% | 93% | 35.6298
9% | 91% | 35.8383
11% | 89% | 36.0186
13% | 87% | 36.1787
15% | 85% | 36.329
17% | 83% | 36.472
19% | 81% | 36.609
21% | 79% | 36.7362
23% | 77% | 36.8773
25% | 75% | 36.9957
27% | 73% | 37.1279
29% | 71% | 37.2489
31% | 69% | 37.364
33% | 67% | 37.4857
35% | 65% | 37.5972
37% | 63% | 37.7134
39% | 61% | 37.8215
41% | 59% | 37.9256
43% | 57% | 38.0265
45% | 55% | 38.1372
47% | 53% | 38.2436
49% | 51% | 38.3467
51% | 49% | 38.4684
53% | 47% | 38.5981
55% | 45% | 38.7014
57% | 43% | 38.8181
59% | 41% | 38.9286
61% | 39% | 39.0666
63% | 37% | 39.1829
65% | 35% | 39.3252
67% | 33% | 39.4669
69% | 31% | 39.605
71% | 29% | 39.7315
73% | 27% | 39.8702
75% | 25% | 40.0092
77% | 23% | 40.1793
79% | 21% | 40.3241
81% | 19% | 40.4851
83% | 17% | 40.67
85% | 15% | 40.8981
87% | 13% | 41.103
89% | 11% | 41.3557
91% | 9% | 41.6372
93% | 7% | 41.9143
95% | 5% | 42.295
97% | 3% | 42.8134
99% | 1% | 43.6668
Overall mean of PeakFunding |  | 38.5821
Ranked input (chart) |  |  |  | Highest − mean | Lowest − mean
Construction cost |  |  |  | 3.7588 | -3.0291
Off-plan sales pace |  |  |  | 1.2118 | -0.40156
Construction duration |  |  |  | 0.63783 | -0.5395
Market price factor |  |  |  | 0.4988 | -0.60894
Overall mean of Profit |  | 8.9526
Ranked input (chart) |  |  |  | Highest − mean | Lowest − mean
Market price factor |  |  |  | 4.64 | -4.5558
Construction cost |  |  |  | 3.1033 | -3.7873
Construction duration |  |  |  | 0.73539 | -0.71566
Off-plan sales pace |  |  |  | 0.34896 | -0.76569
Period | 10th percentile | Median | 90th percentile | Mean
1 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0.0004873
7 | 0 | 0 | 1.0256 | 0.28845
8 | 0.19475 | 1.6296 | 3.1948 | 1.6901
9 | 1.9138 | 3.659 | 5.5444 | 3.6972
10 | 3.7687 | 5.8294 | 8.0309 | 5.8695
11 | 5.7371 | 8.1082 | 10.6244 | 8.1499
12 | 7.7981 | 10.4653 | 13.2802 | 10.505
13 | 9.9168 | 12.8712 | 15.9417 | 12.9018
14 | 12.0815 | 15.2896 | 18.5822 | 15.3083
15 | 14.2543 | 17.6735 | 21.1699 | 17.6936
16 | 16.4143 | 20.0019 | 23.6528 | 20.0282
17 | 18.5188 | 22.2714 | 26.0463 | 22.2842
18 | 20.5647 | 24.4343 | 28.2847 | 24.4358
19 | 22.5539 | 26.4741 | 30.363 | 26.4597
20 | 24.4242 | 28.3459 | 32.2326 | 28.339
21 | 26.2215 | 30.0707 | 33.8946 | 30.064
22 | 27.8926 | 31.6331 | 35.4032 | 31.6273
23 | 29.4331 | 33.0283 | 36.6477 | 33.0235
24 | 30.8359 | 34.2209 | 37.7313 | 34.2483
25 | 32.0669 | 35.2454 | 38.6275 | 35.3005
26 | 33.1642 | 36.0956 | 39.3545 | 36.1828
27 | 34.0102 | 36.7786 | 39.9357 | 36.7552
28 | 33.9876 | 37.1518 | 40.3141 | 35.2566
29 | 0 | 37.0419 | 40.4493 | 30.7524
30 | 0 | 36.4124 | 40.404 | 24.4667
31 | 0 | 0 | 40.1462 | 17.4912
32 | 0 | 0 | 39.4688 | 10.9158
33 | 0 | 0 | 37.714 | 5.5578
34 | 0 | 0 | 0 | 2.0456
35 | 0 | 0 | 0 | 0.47709
36 | 0 | 0 | 0 | 0.01661
37 | 0 | 0 | 0 | 0
38 | 0 | 0 | 0 | 0
39 | 0 | 0 | 0 | 0
40 | 0 | 0 | 0 | 0
41 | 0 | 0 | 0 | 0
42 | 0 | 0 | 0 | 0
43 | 0 | 0 | 0 | 0
44 | 0 | 0 | 0 | 0
45 | 0 | 0 | 0 | 0
46 | 0 | 0 | 0 | 0
47 | 0 | 0 | 0 | 0
48 | 0 | 0 | 0 | 0

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
1997
1
0
0
0
1
0
0
0
1
1379
175
171
116
77
42
25
13
1
1
356
349
337
315
269
206
109
43
14
2
43
173
349
419
380
319
198
90
27
2
45
166
346
418
385
316
204
90
28
2
43
165
342
420
374
327
207
91
29
2
42
160
327
415
389
326
220
89
30
2
41
152
329
404
397
326
225
93
31
2
38
148
318
407
394
335
230
95
32
3
38
138
306
411
399
335
236
99
35
3
37
131
293
410
400
346
239
105
36
3
35
124
276
415
400
346
255
109
36
4
34
114
272
408
391
358
266
113
39
5
33
109
272
407
394
373
261
112
34
5
30
107
267
406
406
371
269
106
32
6
28
107
251
411
429
360
273
106
28
7
25
100
244
416
432
374
266
105
30
8
27
93
241
423
450
370
262
100
27
7
19
90
244
433
473
365
247
97
26
6
23
93
253
455
472
364
218
95
22
5
26
101
295
470
453
337
211
81
20
6
14
0
0
0
0
0
7
766
1084
129
124
0
0
0
0
0
1
602
1123
150
381
0
0
0
0
0
0
442
1023
154
718
0
0
0
0
0
0
324
826
132
1074
0
0
0
0
0
0
208
619
99
1430
0
0
0
0
0
0
67
397
106
1710
0
0
0
0
0
0
3
185
102
1893
0
0
0
0
0
0
1
64
42
1973
0
0
0
0
0
0
0
19
8
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
41
239
357
445
369
275
161
84
25
4
14
110
257
337
356
356
280
183
80
27
1469
0
0
0
0
0
0
0
0
531
13
110
301
418
454
349
207
96
44
8
16
40
136
278
356
422
378
244
98
32
19
62
171
292
404
403
341
194
88
26
107
288
336
378
308
248
179
99
40
17
70
186
271
333
354
294
248
155
62
27
39
117
225
301
336
330
292
206
122
32
67
210
303
330
361
296
213
146
60
14