## About
Schedule Acceleration Chosen by the Optimizer |  | ModelRisk example · Projects and construction · PC-10
Which activities should be accelerated, at least cost, for an 80% chance of opening the bridge within the contract?
Next: Inputs ▸
Model card
Industry | Projects and construction
Difficulty | ★★★★☆ A 15-activity network scheduled forwards and backwards for two plans in every iteration; six yes-or-no accelerations chosen by the ModelRisk Optimizer, at least cost, for a required chance of finishing on time.
Business question | The replacement of a road bridge is planned at 40 weeks with most likely durations, and the contract allows 44, but the chance of finishing within 44 weeks is under 60%. Six activities can be accelerated, each at a price. Which ones should be, at the lowest cost, to give at least an 80% chance of finishing within the contract?
Who it is for | Planners, project managers and contractors who prepare, review or recover programmes.
Main outputs | The Optimizer's choice of accelerations against a starting plan with none (PC-03's programme) · for both plans: the cost of the accelerations, the chance of finishing within the contract, P50 and P80 completion and the programme with most likely durations · each activity's criticality index under both plans · the completion S-curves.
ModelRisk techniques | The ModelRisk Optimizer: six yes-or-no decisions, the cost of the accelerations minimised (a value that does not vary between samples), a probability constraint (the chance of finishing within the contract) · PERT durations and a flood risk event · forward and backward pass of both plans on the same draws · criticality index.
File | PC-10 Schedule acceleration chosen by the Optimizer · Version 1.0 · October 2026 · built with ModelRisk 10
The business question
A council's road bridge replacement takes 40 weeks with most likely durations, and the contract allows 44. But durations run long and parallel paths merge, so the chance of finishing on time is under 60% (PC-03). Six activities can be accelerated at a price: more designers, extra railway possessions, a second piling rig at either abutment, pre-cast pier units or pre-cast deck units. Which are worth buying?
How the model works
Four sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | The start date, the contract duration and the chance of meeting it that is required; the flood risk to the river pier; and for each of six activities, the share of its duration that accelerating it saves and what that costs.
2 Decisions | The six cells the Optimizer changes, one per activity that can be accelerated: 1 to accelerate it, 0 not to. The starting plan accelerates nothing. The goal is the least cost of the accelerations; the limit is the chance of finishing within the contract.
3 Network | Each iteration draws every duration once. Both plans use the same draws, shortened by their own accelerations, and each is scheduled forwards and backwards: its completion, whether it meets the contract and which activities are critical are outputs. Both plans' programmes with most likely durations are calculated too.
4 Results | Both plans on the same simulated projects: the cost, the chance of finishing within the contract, P50 and P80 completion, the S-curves, and how often each activity is critical under each plan.
How to use it
Step 1 | Enter your durations on the Network sheet, and your contract, the chance required, the flood risk and your acceleration options on the Inputs sheet.
Step 2 | On the ModelRisk ribbon, open the Optimizer: the task is saved in this workbook. Press Start. When it finishes, apply the best solution: the 1s and 0s on the Decisions sheet change.
Step 3 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set) to compare the new plan with the starting plan on the Results sheet.
Step 4 | To watch the search from the beginning, copy the starting plan onto the plan in use first. To see why the 40-week critical path misleads, accelerate only the two pilings and simulate.
Workbook map
Inputs | Start date, contract, chance required, flood risk; the time saved and cost of each acceleration.
Decisions | The plan in use, the starting plan, the goal and the limit, and the Optimizer's last run.
Network | Activities; both plans' durations and schedules in this iteration; Gantt chart; the programmes with most likely durations; outputs and checks.
Results | The plan in use against the starting plan; completion S-curves; the criticality index of both plans.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Decision | A cell the ModelRisk Optimizer changes: it tries values within the bounds and keeps the best plan found.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Time | Weeks from the start of the project; dates are the start date plus whole weeks.
Money | US$ thousand (US$k): the extra cost of each acceleration over the normal method.
Accelerate | 1 = the activity is accelerated, 0 = it is done the normal way. Accelerating saves a fixed share of the activity's duration, whatever that duration turns out to be.
Critical | An activity is critical in an iteration if it has no float; its criticality index is the share of iterations in which it is critical.
Programme | The schedule with most likely durations and no flood: the deterministic programme a planner would draw.
Key assumptions and limitations
Logic | Finish-to-start links only, no lags; resources are not limited; accelerating one activity does not slow another.
Acceleration | Each saves a fixed share of its activity's duration for a fixed cost, paid whether or not it turns out to be needed. It does not shorten the flood delay.
Independence | Durations are independent of each other; in practice common causes (productivity, weather) can link them.
Optimizer | Each plan the Optimizer tries is judged on the same 10,000 simulated projects (common random numbers, seed 1) as the simulation on the Results sheet, so plans are compared fairly and the limit the Optimizer met holds on the Results sheet too.
Data | The project, the durations and the acceleration options are invented for this example.
ModelRisk functions used
ModelRisk Optimizer | Chooses which activities to accelerate: least cost of the accelerations, with the chance of finishing within the contract at least the chance required.
VosePERT | Each activity's duration from its low, most likely and high estimates.
VoseRiskEvent, VosePERTObject | The flood: no delay, or a PERT number of weeks.
VoseInput, VoseOutput | Name the durations and the outputs of both plans, including whether each activity is critical.
VoseSimProbability, VoseSimPercentile | The chance of finishing on time and the completion percentiles of both plans.
VoseSimMean | The mean completion and each activity's criticality index under both plans.
Further reading
Schedule risk | Hulett, D. T. (2009). Practical Schedule Risk Analysis. Gower.
Time–cost trade-off | Kelley, J. E. (1961). Critical-path planning and scheduling: mathematical basis. Operations Research 9(3), 296–320.
Companion model | PC-03 Schedule risk on a project network: the same bridge and network, with the criticality index and merge bias explained.
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Schedule Acceleration Chosen by the Optimizer | [7 empty] | ModelRisk example · Projects and construction · PC-10
INPUTS · Start date, contract and the chance of meeting it required; the flood risk; the acceleration options. The activities' durations are on the Network sheet. Change only the yellow cells.
◂ About | [7 empty] | Next: Decisions ▸
How to read this sheet: yellow cells are inputs. Orange cells hold ModelRisk distributions and show the current random sample (press F9 to draw again). Low / Most likely / High are the minimum, most likely and maximum for PERT. Mean is the distribution's average (VoseMean); it shows ✗ if a range is out of order.
1 Programme and target
When the work starts, what the contract allows, and how sure the council wants to be.
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Start date | date | 2027-03-01 | Fixed |  |  |  |  | Notice to proceed (1 March 2027).
Contract duration | weeks | 44 | Fixed |  |  |  |  | Completion date in the contract: 44 weeks after the start.
On-time chance required | chance | 80% | Fixed |  |  |  |  | The chance of finishing within the contract that the Optimizer must reach: the council wants P80 or better.
2 Risk event
A flood stops work in the river until the water level drops.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Chance of a flood during the pier works | chance | 25% | Fixed |  |  |  |  | Gauge records: one flood in four winters over the cofferdam's design level.
Delay to the river pier from a flood | weeks | 2.9065 | Risk event · PERT | 2 | 3 | 6 | 0.83333 | Pumping out, inspection and repair of the cofferdam.
3 Acceleration: time saved
The share of the activity's duration saved if it is accelerated, whatever the duration turns out to be.
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Design: a second design team | of its duration | 10% | Fixed |  |  |  |  | More designers, and fortnightly reviews with the highway authority instead of one at the end.
Demolition: extra railway possessions | of its duration | 25% | Fixed |  |  |  |  | Two more night possessions a week; the railway charges for each one.
North abutment piling: a second piling rig | of its duration | 20% | Fixed |  |  |  |  | Two rigs share the piles; mobilisation and pile testing take as long as before.
South abutment piling: a second piling rig | of its duration | 20% | Fixed |  |  |  |  | A heavier second rig for the softer ground near the river bank.
River pier: pre-cast pier units | of its duration | 25% | Fixed |  |  |  |  | Pier shafts cast off site and lifted into the cofferdam. A flood delays the work as much as before.
Deck slab: pre-cast deck units | of its duration | 20% | Fixed |  |  |  |  | Pre-cast planks as permanent formwork: less concrete poured and cured on site.
4 Acceleration: cost
The extra cost of each acceleration, paid if it is chosen.
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Design: a second design team | US$ thousand | 160 | Fixed |  |  |  |  | Two more designers through the design period, and the extra reviews.
Demolition: extra railway possessions | US$ thousand | 150 | Fixed |  |  |  |  | Possession fees and night-time rates.
North abutment piling: a second piling rig | US$ thousand | 65 | Fixed |  |  |  |  | Second rig and crew: mobilisation, hire and operators.
South abutment piling: a second piling rig | US$ thousand | 70 | Fixed |  |  |  |  | A heavier rig: higher mobilisation and hire.
River pier: pre-cast pier units | US$ thousand | 55 | Fixed |  |  |  |  | Casting yard, transport and a larger crane, less the work saved in the river.
Deck slab: pre-cast deck units | US$ thousand | 140 | Fixed |  |  |  |  | Planks, transport and a larger crane, less the formwork saved.

## Decisions
Schedule Acceleration Chosen by the Optimizer | [6 empty] | ModelRisk example · Projects and construction · PC-10
DECISIONS · The cells the ModelRisk Optimizer changes, the plan they are compared with, and what the Optimizer is asked to do.
◂ Inputs | [6 empty] | Next: Network ▸
How to read this sheet: the blue cells are the plan in use — the cells the Optimizer changes. The yellow Starting plan is the plan it is compared with on the Results sheet; Lowest and Highest bound the search. To watch the Optimizer search from the starting plan, copy the Starting plan column onto Plan in use (Paste Values), then ModelRisk ▸ Optimizer ▸ Start.
1 Activities to accelerate
The Optimizer changes the blue cells: 1 accelerates the activity, 0 does it the normal way. The starting plan accelerates nothing: PC-03's programme.
Decision | Unit | Plan in use | Starting plan | Lowest | Highest | Kind | Notes
A Design: second design team | 1 = yes | 0 | 0 | 0 | 1 | Yes (1) / no (0) | Saves 10% of the design time, for US$160k (Inputs sheet)
C Demolition: extra possessions | 1 = yes | 0 | 0 | 0 | 1 | Yes (1) / no (0) | Saves 25% of the demolition time, for US$150k (Inputs sheet)
D North piling: second piling rig | 1 = yes | 1 | 0 | 0 | 1 | Yes (1) / no (0) | Saves 20% of the piling time, for US$65k (Inputs sheet)
E South piling: second piling rig | 1 = yes | 1 | 0 | 0 | 1 | Yes (1) / no (0) | Saves 20% of the piling time, for US$70k (Inputs sheet)
F River pier: pre-cast pier units | 1 = yes | 1 | 0 | 0 | 1 | Yes (1) / no (0) | Saves 25% of the pier work, for US$55k (Inputs sheet)
K Deck slab: pre-cast deck units | 1 = yes | 0 | 0 | 0 | 1 | Yes (1) / no (0) | Saves 20% of the deck work, for US$140k (Inputs sheet)
2 Goal and limits
What the Optimizer is asked to do. It judges every plan it tries by these statistics of a simulation of that plan.
| Statistic |  |  |  | Limit |  | Output cell
Minimise: Cost of the accelerations | the value | [5 empty] | Network!E134
Keep: Chance of finishing on time at least | the chance of finishing on time · the input On-time chance required |  |  |  | 80% |  | Network!E132
3 The Optimizer's run
Recorded when this workbook was built: the run that chose the plan in use. A run of your own shows its results in the Optimizer window instead.
Run on |  | 2026-10-13
Method the Optimizer chose |  | Vertex Detector
Plans tried (one simulation each) |  | 64
Samples in each trial |  | 10000
Run time, seconds |  | 8
Why it stopped |  | trial budget used
Every limit met by the best plan |  | Yes
Goal at the best plan, during the run |  | 190

## Network
Schedule Acceleration Chosen by the Optimizer | [10 empty] | ModelRisk example · Projects and construction · PC-10
NETWORK · Fifteen activities: durations of both plans, forward and backward pass, float and the critical path (weeks).
◂ Decisions | [10 empty] | Next: Results ▸
1 Activities
Yellow cells are inputs. Predecessors is a label only: the logic is written into the Start formulas of sections 3 and 4. Option: the share of the duration an acceleration saves (Inputs sheet).
ID | Activity | Predecessors | Duration (weeks) |  |  | Mean | Option |  |  |  | Note
|  | label only | Low | Most likely | High | PERT | saves
A | Design and approvals | – | 8 | 10 | 16 | 10.6667 | 10% |  |  |  | Detailed design, approval by the highway authority
B | Site set-up and traffic management | A | 2 | 3 | 5 | 3.1667 | – |  |  |  | Diversion route signed and opened
C | Demolish the old bridge | B | 3 | 4 | 7 | 4.3333 | 25% |  |  |  | Night possessions of the railway below
D | North abutment piling | C | 5 | 7 | 11 | 7.3333 | 20% |  |  |  | Bored piles; ground conditions known from boreholes
E | South abutment piling | C | 5 | 7 | 12 | 7.5 | 20% |  |  |  | Softer ground near the river bank
F | River pier | C | 6 | 9 | 14 | 9.3333 | 25% |  |  |  | Cofferdam in the river; the flood risk is added in section 2
G | Fabricate steel girders (off site) | A | 10 | 14 | 20 | 14.3333 | – |  |  |  | Fabricator's slot booked after design approval
H | North abutment walls | D | 3 | 4 | 6 | 4.1667 | –
I | South abutment walls | E | 3 | 4 | 6 | 4.1667 | –
J | Deliver and erect girders | F, G, H, I | 2 | 3 | 5 | 3.1667 | – |  |  |  | Needs both abutments, the pier and the girders
K | Deck slab | J | 4 | 5 | 8 | 5.3333 | 20%
L | Waterproofing and surfacing | K | 2 | 3 | 5 | 3.1667 | –
M | Parapets and finishes | K | 2 | 2 | 4 | 2.3333 | –
N | Approach road tie-ins | B | 3 | 4 | 6 | 4.1667 | – |  |  |  | Independent of the bridge itself
O | Testing and opening | L, M, N | 1 | 1 | 2 | 1.1667 | – |  |  |  | Load test and safety audit
2 Durations in this iteration
One draw of each duration, shared by both plans; each plan shortens the activities it accelerates. Press F9 for another iteration.
ID | Activity | Sampled | Flood | Saved | Saved | Duration | Duration |  |  |  | How it is calculated
|  | PERT | delay | starting | in use | starting | in use
A | Design and approvals | 12.3264 | – | 0% | 0% | 12.3264 | 12.3264 |  |  |  | Sampled: this iteration's PERT duration (a VoseInput)
B | Site set-up and traffic management | 2.7896 | – | – | – | 2.7896 | 2.7896 |  |  |  | Saved: the option's share if the plan accelerates it
C | Demolish the old bridge | 4.5761 | – | 0% | 0% | 4.5761 | 4.5761 |  |  |  | Duration = sampled × (1 − saved), + flood for the pier
D | North abutment piling | 8.0437 | – | 0% | 20% | 8.0437 | 6.4349
E | South abutment piling | 6.5114 | – | 0% | 20% | 6.5114 | 5.2091
F | River pier | 8.0763 | 2.9065 | 0% | 25% | 10.9828 | 8.9638 |  |  |  | A flood delays the pier work whichever way it is built
G | Fabricate steel girders (off site) | 13.0957 | – | – | – | 13.0957 | 13.0957
H | North abutment walls | 3.4825 | – | – | – | 3.4825 | 3.4825
I | South abutment walls | 5.5674 | – | – | – | 5.5674 | 5.5674
J | Deliver and erect girders | 2.7406 | – | – | – | 2.7406 | 2.7406
K | Deck slab | 5.7478 | – | 0% | 0% | 5.7478 | 5.7478
L | Waterproofing and surfacing | 4.5415 | – | – | – | 4.5415 | 4.5415
M | Parapets and finishes | 2.314 | – | – | – | 2.314 | 2.314
N | Approach road tie-ins | 4.2095 | – | – | – | 4.2095 | 4.2095
O | Testing and opening | 1.3646 | – | – | – | 1.3646 | 1.3646
3 Schedule of the starting plan in this iteration
Start = latest finish of the predecessors. Late finish = earliest late start of the successors.
ID | Activity | Duration | Start | Finish | Late start | Late finish | Float | Critical? |  |  | How it is calculated
|  | section 2 | [5 empty] | 1 = yes
A | Design and approvals | 12.3264 | 0 | 12.3264 | 0 | 12.3264 | 0 | 1 |  |  | Start: the finish of the predecessor, or the latest finish if there are several (forward pass)
B | Site set-up and traffic management | 2.7896 | 12.3264 | 15.1159 | 12.3264 | 15.1159 | 0 | 1 |  |  | Late finish: the late start of the successor, or the earliest if there are several (backward pass)
C | Demolish the old bridge | 4.5761 | 15.1159 | 19.692 | 15.1159 | 19.692 | 0 | 1 |  |  | Float = late start − start; critical if the float is zero
D | North abutment piling | 8.0437 | 19.692 | 27.7357 | 20.2446 | 28.2883 | 0.55261 | 0
E | South abutment piling | 6.5114 | 19.692 | 26.2034 | 19.692 | 26.2034 | 0 | 1
F | River pier | 10.9828 | 19.692 | 30.6748 | 20.7879 | 31.7707 | 1.0959 | 0
G | Fabricate steel girders (off site) | 13.0957 | 12.3264 | 25.4221 | 18.675 | 31.7707 | 6.3487 | 0
H | North abutment walls | 3.4825 | 27.7357 | 31.2181 | 28.2883 | 31.7707 | 0.55261 | 0
I | South abutment walls | 5.5674 | 26.2034 | 31.7707 | 26.2034 | 31.7707 | 0 | 1
J | Deliver and erect girders | 2.7406 | 31.7707 | 34.5114 | 31.7707 | 34.5114 | 0 | 1
K | Deck slab | 5.7478 | 34.5114 | 40.2592 | 34.5114 | 40.2592 | 0 | 1
L | Waterproofing and surfacing | 4.5415 | 40.2592 | 44.8007 | 40.2592 | 44.8007 | 0 | 1
M | Parapets and finishes | 2.314 | 40.2592 | 42.5732 | 42.4867 | 44.8007 | 2.2275 | 0
N | Approach road tie-ins | 4.2095 | 15.1159 | 19.3254 | 40.5912 | 44.8007 | 25.4753 | 0
O | Testing and opening | 1.3646 | 44.8007 | 46.1654 | 44.8007 | 46.1654 | 0 | 1
4 Schedule of the plan in use in this iteration
Start = latest finish of the predecessors. Late finish = earliest late start of the successors.
ID | Activity | Duration | Start | Finish | Late start | Late finish | Float | Critical? |  |  | How it is calculated
|  | section 2 | [5 empty] | 1 = yes
A | Design and approvals | 12.3264 | 0 | 12.3264 | 0 | 12.3264 | 0 | 1 |  |  | The same network and logic, with the plan in use's durations
B | Site set-up and traffic management | 2.7896 | 12.3264 | 15.1159 | 12.3264 | 15.1159 | 0 | 1
C | Demolish the old bridge | 4.5761 | 15.1159 | 19.692 | 15.1159 | 19.692 | 0 | 1
D | North abutment piling | 6.4349 | 19.692 | 26.1269 | 20.5511 | 26.986 | 0.85907 | 0
E | South abutment piling | 5.2091 | 19.692 | 24.9011 | 19.692 | 24.9011 | 0 | 1
F | River pier | 8.9638 | 19.692 | 28.6558 | 21.5047 | 30.4685 | 1.8127 | 0
G | Fabricate steel girders (off site) | 13.0957 | 12.3264 | 25.4221 | 17.3728 | 30.4685 | 5.0464 | 0
H | North abutment walls | 3.4825 | 26.1269 | 29.6094 | 26.986 | 30.4685 | 0.85907 | 0
I | South abutment walls | 5.5674 | 24.9011 | 30.4685 | 24.9011 | 30.4685 | 0 | 1
J | Deliver and erect girders | 2.7406 | 30.4685 | 33.2091 | 30.4685 | 33.2091 | 0 | 1
K | Deck slab | 5.7478 | 33.2091 | 38.9569 | 33.2091 | 38.9569 | 0 | 1
L | Waterproofing and surfacing | 4.5415 | 38.9569 | 43.4984 | 38.9569 | 43.4984 | 0 | 1
M | Parapets and finishes | 2.314 | 38.9569 | 41.271 | 41.1844 | 43.4984 | 2.2275 | 0
N | Approach road tie-ins | 4.2095 | 15.1159 | 19.3254 | 39.289 | 43.4984 | 24.173 | 0
O | Testing and opening | 1.3646 | 43.4984 | 44.8631 | 43.4984 | 44.8631 | 0 | 1
5 The plan in use in this iteration, as a Gantt chart
Section 4 drawn to scale. Press F9 to see another possible programme.
6 Programmes with most likely durations
The deterministic programme of each plan: most likely durations, no flood. Critical in the starting plan's programme: no float.
ID | Activity | Duration | Start | Finish | Late start | Late finish | Critical? | Duration | Start | Finish | How it is calculated
|  | starting plan |  |  |  |  | 1 = yes | plan in use
A | Design and approvals | 10 | 0 | 10 | 0 | 10 | 1 | 10 | 0 | 10 | Duration = most likely × (1 − the plan's saved share)
B | Site set-up and traffic management | 3 | 10 | 13 | 10 | 13 | 1 | 3 | 10 | 13 | Starting plan: forward and backward pass; critical if no float
C | Demolish the old bridge | 4 | 13 | 17 | 13 | 17 | 1 | 4 | 13 | 17 | Plan in use: forward pass only, for its finish
D | North abutment piling | 7 | 17 | 24 | 17 | 24 | 1 | 5.6 | 17 | 22.6
E | South abutment piling | 7 | 17 | 24 | 17 | 24 | 1 | 5.6 | 17 | 22.6
F | River pier | 9 | 17 | 26 | 19 | 28 | 0 | 6.75 | 17 | 23.75
G | Fabricate steel girders (off site) | 14 | 10 | 24 | 14 | 28 | 0 | 14 | 10 | 24
H | North abutment walls | 4 | 24 | 28 | 24 | 28 | 1 | 4 | 22.6 | 26.6
I | South abutment walls | 4 | 24 | 28 | 24 | 28 | 1 | 4 | 22.6 | 26.6
J | Deliver and erect girders | 3 | 28 | 31 | 28 | 31 | 1 | 3 | 26.6 | 29.6
K | Deck slab | 5 | 31 | 36 | 31 | 36 | 1 | 5 | 29.6 | 34.6
L | Waterproofing and surfacing | 3 | 36 | 39 | 36 | 39 | 1 | 3 | 34.6 | 37.6
M | Parapets and finishes | 2 | 36 | 38 | 37 | 39 | 0 | 2 | 34.6 | 36.6
N | Approach road tie-ins | 4 | 13 | 17 | 35 | 39 | 0 | 4 | 13 | 17
O | Testing and opening | 1 | 39 | 40 | 39 | 40 | 1 | 1 | 37.6 | 38.6
7 Value in this iteration
Key outputs, recorded by ModelRisk at every sample (VoseOutput). Their statistics appear on the Results sheet.
| Output | Unit | Value | [7 empty] | Meaning
| Completion, starting plan | weeks | 46.1654 | [7 empty] | Finish of the last activity in this iteration.
| Completion, plan in use | weeks | 44.8631 | [7 empty] | Finish of the last activity in this iteration.
| On time, starting plan (1 = yes) | 1 / 0 | 0 | [7 empty] | Its share of the iterations is the chance of finishing on time.
| On time, plan in use (1 = yes) | 1 / 0 | 0 | [7 empty] | Its share of the iterations is the chance of finishing on time.
| Acceleration cost, starting plan | US$ thousand | 0 | [7 empty] | The cost of each option chosen: the same in every iteration.
| Acceleration cost, plan in use | US$ thousand | 190 | [7 empty] | The cost of each option chosen: the same in every iteration.
| Completion date, plan in use | date | 2028-01-09 | [7 empty] | Start date + weeks × 7 days.
| Programme, starting plan | weeks | 40 | [7 empty] | Most likely durations, no flood (section 6).
| Programme, plan in use | weeks | 38.6 | [7 empty] | The same with the plan in use's accelerations.
8 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
| Durations: Low ≤ Most likely ≤ High |  | OK
| No negative float in either plan |  | OK
| The last activity is critical in both plans |  | OK
| Every decision is 1 or 0 in both plans |  | OK

## Results
Schedule Acceleration Chosen by the Optimizer | [6 empty] | ModelRisk example · Projects and construction · PC-10
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Network
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 The plan in use against the starting plan | [5 empty] | Completion — S-curves
The accelerations of the two plans, and how each performs on the same simulated projects.
Decision | Unit | Starting plan | Plan in use | Change
A Design: second design team | 1 = yes | 0 | 0 | 0
C Demolition: extra possessions | 1 = yes | 0 | 0 | 0
D North piling: second piling rig | 1 = yes | 0 | 1 | 1
E South piling: second piling rig | 1 = yes | 0 | 1 | 1
F River pier: pre-cast pier units | 1 = yes | 0 | 1 | 1
K Deck slab: pre-cast deck units | 1 = yes | 0 | 0 | 0
Measure | Unit | Starting plan | Plan in use | Change
Cost of the accelerations | US$k | 0 | 190 | 190
Chance of finishing within the contract | chance | 57.76% | 82.74% | 24.98% | ✔ better
Completion, P50 | weeks | 43.5543 | 41.8 | -1.7543 | ✔ better
Completion, P80 | weeks | 45.5904 | 43.7617 | -1.8287 | ✔ better
Completion, mean | weeks | 43.6245 | 41.8911 | -1.7334 | ✔ better
Programme with most likely durations | weeks | 40 | 38.6 | -1.4 | ✔ better
P80 completion date | date | 2028-01-14 | 2028-01-01
Contract duration | weeks | 44 | 44
On-time chance required (Inputs sheet) | chance | 80% | 80%
Programme: most likely durations and no flood, the deterministic schedule (Network sheet, section 6).
2 Which activities are critical | [5 empty] | Criticality index — starting plan and plan in use
Criticality index: how often the activity is on the critical path in the simulation, under each plan.
Activity | Programme | Starting plan | Plan in use | Accelerated
| critical | criticality | criticality | in the plan
A Design and approvals | yes | 100% | 100% | no
B Site set-up and traffic management | yes | 99.31% | 95.65% | –
C Demolish the old bridge | yes | 99.31% | 95.65% | no
D North abutment piling | yes | 37.91% | 40.38% | yes
E South abutment piling | yes | 42.74% | 44.92% | yes
F River pier |  | 18.67% | 10.35% | yes
G Fabricate steel girders (off site) |  | 0.69% | 4.35% | –
H North abutment walls | yes | 37.91% | 40.38% | –
I South abutment walls | yes | 42.74% | 44.92% | –
J Deliver and erect girders | yes | 100% | 100% | –
K Deck slab | yes | 100% | 100% | no
L Waterproofing and surfacing | yes | 91.71% | 91.71% | –
M Parapets and finishes |  | 8.29% | 8.29% | –
N Approach road tie-ins |  | 0% | 0% | –
O Testing and opening | yes | 100% | 100% | –
Programme: critical in the starting plan's programme. Accelerated: in the plan in use (– = not an option).
3 How to read these results
• The starting plan — PC-03's programme, with nothing accelerated — finishes within the 44-week contract in under 60% of the simulated projects, well short of the 80% required.
• The Optimizer buys a second piling rig at each abutment and pre-cast units for the river pier, for about US$190k. The chance of finishing on time rises to a little over 80%, and P80 completion falls by about two weeks, to within the contract.
• The pier is not on the 40-week critical path, and on paper its pre-cast units save nothing: the programme is the same with or without them. Accelerate only the pilings and the chance stalls at about three in four, because the pier, with its flood risk, then sets the pace in over a third of the projects. With all three accelerated, it does so in about one in ten.
• Design, demolition and the deck lie on every path, so time saved there counts in full; but each saves only about a week, for US$140k–160k, and no plan that uses them reaches 80% for less.
• Try a 90% requirement on the Inputs sheet and run the Optimizer again: it adds the pre-cast deck units as well, and the cost rises by about three-quarters.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | Out_Finish_Start | Out_Finish_Plan | line at ContractWeeks
1% | 99% | 38.6332 | 37.2942 | 44
3% | 97% | 39.4962 | 38.0008 | 44
5% | 95% | 39.9095 | 38.3862 | 44
7% | 93% | 40.2657 | 38.7134 | 44
9% | 91% | 40.5283 | 38.9897 | 44
11% | 89% | 40.7608 | 39.2109 | 44
13% | 87% | 40.9759 | 39.3966 | 44
15% | 85% | 41.1677 | 39.5836 | 44
17% | 83% | 41.3381 | 39.7361 | 44
19% | 81% | 41.5101 | 39.8868 | 44
21% | 79% | 41.6773 | 40.0451 | 44
23% | 77% | 41.8172 | 40.191 | 44
25% | 75% | 41.9656 | 40.3286 | 44
27% | 73% | 42.115 | 40.4653 | 44
29% | 71% | 42.2573 | 40.5978 | 44
31% | 69% | 42.4024 | 40.7243 | 44
33% | 67% | 42.529 | 40.8398 | 44
35% | 65% | 42.6436 | 40.9482 | 44
37% | 63% | 42.7771 | 41.0664 | 44
39% | 61% | 42.8889 | 41.1864 | 44
41% | 59% | 43.0115 | 41.3071 | 44
43% | 57% | 43.1264 | 41.4252 | 44
45% | 55% | 43.2501 | 41.5318 | 44
47% | 53% | 43.3717 | 41.6382 | 44
49% | 51% | 43.4937 | 41.7491 | 44
51% | 49% | 43.6019 | 41.8547 | 44
53% | 47% | 43.704 | 41.9783 | 44
55% | 45% | 43.836 | 42.0929 | 44
57% | 43% | 43.9555 | 42.2054 | 44
59% | 41% | 44.0748 | 42.3259 | 44
61% | 39% | 44.2067 | 42.4353 | 44
63% | 37% | 44.3336 | 42.5457 | 44
65% | 35% | 44.4706 | 42.6609 | 44
67% | 33% | 44.6104 | 42.8051 | 44
69% | 31% | 44.7586 | 42.9437 | 44
71% | 29% | 44.8957 | 43.0874 | 44
73% | 27% | 45.0254 | 43.2263 | 44
75% | 25% | 45.178 | 43.3723 | 44
77% | 23% | 45.3429 | 43.5182 | 44
79% | 21% | 45.5009 | 43.6753 | 44
81% | 19% | 45.6722 | 43.8511 | 44
83% | 17% | 45.8566 | 44.0197 | 44
85% | 15% | 46.0786 | 44.208 | 44
87% | 13% | 46.3215 | 44.4252 | 44
89% | 11% | 46.5815 | 44.6693 | 44
91% | 9% | 46.8231 | 44.9218 | 44
93% | 7% | 47.1442 | 45.2502 | 44
95% | 5% | 47.5645 | 45.631 | 44
97% | 3% | 48.2629 | 46.2395 | 44
99% | 1% | 49.3302 | 47.2989 | 44

## ModelRiskOptimizer (hidden)
MROPTREPO/2.0 | 0 | 1 | 1 | {"format_version":"1.0","model":"Schedule acceleration: which activities to accelerate","settings":{"engineKind":0,"optimizationType":0,"useTurboSimulation":true,"gaPopulation":0,"gaProbCrossover":0.8,"gaProbMutation":0.1,"gaSelection":0,"gaTournamentSize":3,"gaElitism":2,"cmaSigma":0.3,"cmaPopulation":0,"cmaUseIPOP":true,"cmaPolishDampStart":0.7,"cmaPolishDampGrowth":0.15,"nelderMeadTol":1e-06,"nelderMeadInitStep":0.05,"bfgsGradH":1e-06,"bfgsStepConvergence":true,"brentTol":1e-13,"projGradConvergenceTol":0.0001,"projGradConvergenceWindow":5,"useCRN":true,"crnSeed":1,"useRandomSeed":false,"useFixedTwister":false,"finalFullMcConfirm":false,"gaProjectLinearConstraints":false,"pathfinderRobust":false,"pathfinderSurrogate":true,"pathfinderGradient":true,"pathfinderCheapExplore":false,"pathfinderFeasGate":true,"pathfinderLeanDescent":true,"pathfinderSoftConstraint":false,"adaptScheme":2,"repMin":200,"repMax":5000,"repFinalTopN":5,"varianceTrancheEpsPct":0.02,"varianceTrancheThreshold":0.8,"varianceTrancheMinK":5,"preFlightEnabled":true,"deterministicSamples":1,"samplingType":3,"userSamples":10000,"conDefType":0,"conDefPenaltyKind":0,"conDefWeight":1.0,"conDefEvalTime":0,"conDefPrecision":0.0,"macroAtOptStart":"","macroBeforeTrial":"","macroAfterTrial":"","macroAtOptEnd":"","useMacroAtOptStart":false,"useMacroBeforeTrial":false,"useMacroAfterTrial":false,"useMacroAtOptEnd":false},"stop":{"maxIterations":150,"maxTimeSeconds":900.0,"parameterTolerance":1.0,"toleranceUnit":1,"stagnationTrials":70,"stagnationDeviation":1e-06,"stagnationUnit":0,"stopOnError":false,"stopFormulaEnabled":false,"stopFormulaRef":""},"adj":{"variables":[{"cell":{"sheet":"Decisions","row":10,"col":3},"type":3,"min":0.0,"max":1.0,"groupIndex":-1,"label":"A Design: second design team","discreteSet":[]},{"cell":{"sheet":"Decisions","row":11,"col":3},"type":3,"min":0.0,"max":1.0,"groupIndex":-1,"label":"C Demolition: extra possessions","discreteSet":[]},{"cell":{"sheet":"Decisions","row":12,"col":3},"type":3,"min":0.0,"max":1.0,"groupIndex":-1,"label":"D North piling: second piling rig","discreteSet":[]},{"cell":{"sheet":"Decisions","row":13,"col":3},"type":3,"min":0.0,"max":1.0,"groupIndex":-1,"label":"E South piling: second piling rig","discreteSet":[]},{"cell":{"sheet":"Decisions","row":14,"col":3},"type":3,"min":0.0,"max":1.0,"groupIndex":-1,"label":"F River pier: pre-cast pier units","discreteSet":[]},{"cell":{"sheet":"Decisions","row":15,"col":3},"type":3,"min":0.0,"max":1.0,"groupIndex":-1,"label":"K Deck slab: pre-cast deck units","discreteSet":[]}],"groups":[]},"objectives":[{"name":"Cost of the accelerations","cell":{"sheet":"Network","row":133,"col":4},"stat":{"kind":22,"param1":0.0,"param2":0.0},"mode":1,"targetValue":0.0}],"constraints":[{"name":"Chance of finishing on time","cell":{"sheet":"Network","row":131,"col":4},"type":0,"softWeight":1.0,"penaltyKind":0,"sixSigma":0,"precision":0.0,"stat":{"kind":23,"param1":0.5,"param2":0.0},"op":1,"rhsA":0.8,"rhsB":0.0,"formulaCellRef":"","evalTime":2,"rhsACell":{"sheet":"Inputs","row":12,"col":3}}],"frontier":{"sweptIndex":-1,"lo":0.0,"hi":0.0,"nPoints":5}}
1 | Base scenario | 1

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
1477
0
0
22
121
149
129
76
20
6
145
322
346
354
308
232
176
80
29
8
79
237
368
354
351
272
176
113
40
10
146
321
374
345
310
223
153
80
33
15
85
228
292
361
317
279
224
124
71
19
108
273
361
358
297
258
178
117
36
14
76
196
271
346
354
265
235
144
80
33
81
207
287
354
349
275
234
129
68
16
65
213
347
361
322
291
183
133
63
22
91
264
347
382
340
257
181
92
42
4
94
233
316
355
340
258
201
121
63
19
172
297
373
383
282
227
129
87
41
9
96
223
357
378
328
290
178
98
40
12
628
437
347
227
161
109
45
24
18
4
85
251
305
371
354
260
176
126
49
23
704
475
331
205
125
82
48
19
5
6
0
0
0
0
0
2000
0
0
0
0
8
0
0
0
0
0
0
0
0
1992
8
0
0
0
0
0
0
0
0
1992
1217
0
0
0
0
0
0
0
0
783
1171
0
0
0
0
0
0
0
0
829
1620
0
0
0
0
0
0
0
0
380
1992
0
0
0
0
0
0
0
0
8
1217
0
0
0
0
0
0
0
0
783
1171
0
0
0
0
0
0
0
0
829
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
142
0
0
0
0
0
0
0
0
1858
1858
0
0
0
0
0
0
0
0
142
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
80
0
0
0
0
0
0
0
0
1920
80
0
0
0
0
0
0
0
0
1920
1177
0
0
0
0
0
0
0
0
823
1128
0
0
0
0
0
0
0
0
872
1775
0
0
0
0
0
0
0
0
225
1920
0
0
0
0
0
0
0
0
80
1177
0
0
0
0
0
0
0
0
823
1128
0
0
0
0
0
0
0
0
872
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
142
0
0
0
0
0
0
0
0
1858
1858
0
0
0
0
0
0
0
0
142
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
25
101
273
387
460
380
236
94
32
12
28
133
275
405
434
368
224
92
34
7
849
0
0
0
0
0
0
0
0
1151
338
0
0
0
0
0
0
0
0
1662