## About
Clinical Trial Cost and Duration |  | ModelRisk example · Pharmaceuticals and biotech · PH-01
What budget and what date for the top-line results? A Phase II trial's cost and timeline with contingency.
Next: Inputs ▸
Model card
Industry | Pharmaceuticals and biotech
Difficulty | ★☆☆☆☆ Three-point estimates and three risk events added up; patients grossed up for dropouts and screen failures; a monthly running cost that turns every delay into money.
Business question | A biotech company is planning a Phase II trial of its lead compound: 180 patients must complete it. The board wants a budget and a date for the top-line results that it can rely on. What will the trial cost, how long will it take, and how much contingency should the budget and the timeline hold?
Who it is for | Clinical operations and project managers, R&D finance, biotech management and boards.
Main outputs | Total cost and duration: mean, P50, P80, P90 · the base estimate's chance of being enough · contingency for a P80 budget and a P80 timeline · top-line results date at 50% and 80% confidence · what drives the cost.
ModelRisk techniques | Three-point estimates as PERT distributions · risk events that delay the trial (VoseRiskEvent) · patients enrolled and screened grossed up for uncertain dropout and screen-failure rates · a time-dependent running cost · P50 / P80 budgets and contingency · S-curve, histogram and tornado.
File | PH-01 Clinical trial cost and duration · Version 1.0 · October 2026 · built with ModelRisk 10
The business question
A biotech company is planning a Phase II trial of its lead compound at about 30 hospitals in Europe and the US. 180 patients must complete the 24 weeks of treatment; some will drop out, and about a third of the patients screened will not meet the entry criteria. The clinical team has given low, most likely and high estimates for each phase of the trial and each cost, and has listed three risks that would delay it: a protocol amendment, enrolment slow enough to need new sites, and a clinical hold by a regulator. Every month of delay costs the trial's running cost: the CRO's project management, monitoring and data management. The protocol is approved in January 2027; the board wants a budget and a date for the top-line results.
How the model works
Three sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | The patients who must complete the trial, the dropout and screen-failure rates; low, most likely and high estimates for each phase and each cost; the chance and the delay of each risk.
2 Trial | The patients to enrol and to screen; the duration, phase by phase plus the risk delays, and the dates of first site open, last patient in and top-line results; the costs, including the running cost over the months the trial runs. The Base column repeats every row with the most likely values and no risks.
3 Results | The cost and the duration at each confidence level; the chance that the base estimate is enough; the contingency for a P80 budget and a P80 timeline; the top-line results date; the inputs that drive the cost.
How to use it
Step 1 | Enter your trial's size and the low, most likely and high estimates of your clinical team on the Inputs sheet.
Step 2 | List the risks that would delay the trial, with their chance and their delay.
Step 3 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set).
Step 4 | Set the budget and the timeline at the confidence level the board wants, and work on the top drivers.
Workbook map
Inputs | Trial size and rates, durations, costs, risks.
Trial | Patients, duration and dates, and costs, each in this iteration and in the base estimate; outputs and checks.
Results | Budget, contingency, timeline, drivers.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Money | US$ million (US$m); costs per patient in US$ thousand (US$k); today's prices.
Time | Months from the protocol's approval; dates at an average month of 30.4 days.
P80 | The value with an 80% chance of not being exceeded.
Base estimate | Every estimate at its most likely value, and no risks.
Key assumptions and limitations
Phases | Back to back: start-up, enrolment, treatment of the last patient, close-out.
Risks | Independent; each adds its delay to the enrolment period, and the running cost continues while it lasts.
Estimates | Independent of each other; enrolment time does not depend on the number of patients (see PH-02 for a recruitment model).
Data | The company, the compound and all figures are invented for this example.
ModelRisk functions used
VosePERT | Three-point estimates of the phases, the costs and the dropout and screen-failure rates.
VoseRiskEvent, VosePERTObject | Each risk's delay: zero, or a PERT delay with the risk's chance.
VoseInput, VoseOutput | Mark the uncertain inputs for the tornado, and the outputs recorded at every sample.
VoseSimMean, VoseSimPercentile, VoseSimProbability | Statistics of the simulation on the Results sheet.
VoseSimSensitivityMean | The tornado chart: every VoseInput ranked by how far the mean total cost moves across its range.
Further reading
Trial costs | Sertkaya, A. et al. (2016). Key cost drivers of pharmaceutical clinical trials in the United States. Clinical Trials 13(2), 117–126.
Contingency | Vose, D. (2008). Risk Analysis: A Quantitative Guide, 3rd edition. Wiley — project risk analysis.
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Clinical Trial Cost and Duration | [7 empty] | ModelRisk example · Pharmaceuticals and biotech · PH-01
INPUTS · Every assumption the model uses, with its uncertainty and its basis. Change only the yellow cells.
◂ About | [7 empty] | Next: Trial ▸
How to read this sheet: yellow cells are inputs. Orange cells hold ModelRisk distributions and show the current random sample (press F9 to draw again). Low / Most likely / High are the minimum, most likely and maximum for PERT. Mean is the distribution's average (VoseMean); it shows ✗ if a range is out of order.
1 The trial
A Phase II trial at about 30 hospitals in Europe and the US.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Patients who must complete the trial | patients | 180 | Fixed |  |  |  |  | From the sample-size calculation: 90% power for the primary endpoint.
Dropout rate | of patients enrolled | 15% | PERT | 10% | 15% | 25% | 15.83% | Patients who leave before the primary endpoint; 12–20% in similar trials.
Screen-failure rate | of patients screened | 26.52% | PERT | 25% | 35% | 50% | 35.83% | Patients screened who do not meet the entry criteria.
Protocol approved | date | 2027-01-04 | Fixed |  |  |  |  | The clock starts here.
Average days per month | days | 30.4375 | Calculated |  |  |  |  | Turns months into calendar days for the dates.
2 Duration
Back-to-back phases, in months.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Start-up: approvals, contracts, first site open | months | 5.2514 | PERT | 4 | 6 | 10 | 6.3333 | Ethics committees and regulators in six countries.
Enrolment: first to last patient in | months | 11.1756 | PERT | 10 | 12 | 18 | 12.6667 | The clinical team's estimate for 30 sites.
Treatment of the last patient | months | 6 | Fixed |  |  |  |  | 24 weeks, set by the protocol.
Close-out: database lock to top-line results | months | 3.4734 | PERT | 3 | 4 | 6 | 4.1667
3 Costs
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Set-up: protocol, CRO start-up, approvals | US$m | 0.65324 | PERT | 0.6 | 0.8 | 1.2 | 0.83333
Cost per patient screened | US$k | 1.8954 | PERT | 1.5 | 2 | 3 | 2.0833 | Screening visit and tests.
Cost per patient enrolled | US$k | 36.1032 | PERT | 25 | 30 | 40 | 30.8333 | Visits, procedures, imaging, investigator fees.
Drug supply and logistics | US$m | 0.90938 | PERT | 0.8 | 1 | 1.5 | 1.05 | Manufacture, packaging, comparator, distribution.
Running cost per month | US$k / month | 187.4886 | PERT | 150 | 180 | 230 | 183.3333 | CRO management, monitoring, data management: from the first site open to the top-line results.
4 Risks
Each risk delays the trial; its cost is the running cost of the months lost.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Protocol amendment: chance | probability | 40% | Fixed |  |  |  |  | Most Phase II protocols are amended at least once.
Protocol amendment: delay | months | 0 | Risk event · PERT | 1 | 2 | 4 | 0.86667 | Re-approval by ethics committees; sites retrained.
Slow enrolment, new sites needed: chance | probability | 30% | Fixed
Slow enrolment: delay | months | 0 | Risk event · PERT | 2 | 3 | 5 | 0.95 | Time to open new sites.
Clinical hold by a regulator: chance | probability | 5% | Fixed |  |  |  |  | A safety signal stops dosing until it is resolved.
Clinical hold: delay | months | 0 | Risk event · PERT | 3 | 6 | 9 | 0.3

## Trial
Clinical Trial Cost and Duration |  |  |  | ModelRisk example · Pharmaceuticals and biotech · PH-01
TRIAL · Patients, duration and dates, and costs: in this iteration, and in the base estimate.
◂ Inputs |  |  |  | Next: Results ▸
1 Patients
Base: every estimate at its most likely value, and no risks. The base estimate most budgets are built on.
Quantity | Unit | This iteration | Base | How it is calculated
Patients to enrol | patients | 212 | 212 | Enough to keep the evaluable patients after dropouts: evaluable ÷ (1 − dropout rate), rounded up
Patients to screen | patients | 289 | 327 | Enrolled ÷ (1 − screen-failure rate), rounded up
2 Duration and dates
Quantity | Unit | This iteration | Base | How it is calculated
Delay from the risks | months | 0 | 0 | The three risk events on the Inputs sheet: zero when a risk does not happen; none in the base
Expected delay from the risks, calculated exactly | months | 2.1167 |  | The risk events' means on the Inputs sheet (chance × mean delay): a check on the simulation
Months the trial runs | months | 20.649 | 22 | From the first site open to the top-line results
Duration, protocol approval to top-line results | months | 25.9004 | 28 | Start-up + the months the trial runs
First site open | date | 2027-06-12 20:09 | 2027-07-05 15:00 | Protocol approved + start-up
Last patient in | date | 2028-05-17 23:57 | 2028-07-04 21:00 | + enrolment + the risk delays
Last patient's last visit | date | 2028-11-16 14:57 | 2029-01-03 12:00 | + treatment
Top-line results | date | 2029-03-02 08:15 | 2029-05-05 06:00 | + close-out
3 Costs
Quantity | Unit | This iteration | Base | How it is calculated
Set-up | US$m | 0.65324 | 0.8 | From the Inputs sheet
Screening | US$m | 0.54777 | 0.654 | Patients screened × cost per patient screened
Patients | US$m | 7.6539 | 6.36 | Patients enrolled × cost per patient enrolled
Drug supply and logistics | US$m | 0.90938 | 1 | From the Inputs sheet
Running cost | US$m | 3.8715 | 3.96 | Months the trial runs × running cost per month: every month of delay costs this much
Total cost | US$m | 13.6357 | 12.774 | The costs above, added up
4 Value in this iteration
Key outputs, recorded by ModelRisk at every sample (VoseOutput). Their statistics appear on the Results sheet.
Output | Unit | Value |  | Meaning
Total cost | US$m | 13.6357 |  | The total of section 3.
Duration, protocol approval to top-line results | months | 25.9004
Top-line results | date | 2029-03-02 08:15 |  | Recorded as a date.
Delay from the risks | months | 0
5 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
The patients enrolled cover the evaluable patients after dropouts |  | OK
Dropout and screen-failure rates stay below 90% |  | OK
Every date follows the one before |  | OK

## Results
Clinical Trial Cost and Duration | [6 empty] | ModelRisk example · Pharmaceuticals and biotech · PH-01
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Trial
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 The budget | [5 empty] | Total cost — S-curve
P80 = the cost with an 80% chance of not being exceeded.
Measure | Unit | Value
Base estimate (most likely values, no risks) | US$m | 12.774
Mean total cost | US$m | 13.7688
Chance that the base estimate is enough | probability | 13.46%
P80 budget | US$m | 14.5355
Contingency for a P80 budget | US$m | 1.7615
Contingency as a share of the base estimate |  | 13.79%
2 The timeline | [5 empty] | Duration — distribution
From the protocol's approval to the top-line results.
Measure | Unit | Value
Planned duration (most likely values, no risks) | months | 28
Mean duration | months | 31.286
Chance of finishing within the plan | probability | 12.55%
Duration with 80% confidence (P80) | months | 33.6161
Timeline contingency for 80% confidence | months | 5.6161
Top-line results on the plan | date | 2029-05-05 06:00
Top-line results with 50% confidence | date | 2029-08-03 17:42
Top-line results with 80% confidence | date | 2029-10-23 04:34
3 Other confidence levels
Choose the confidence level, then read the budget and the duration.
Measure | Unit | P50 | P80 | P90 | Mean
Total cost | US$m | 13.7071 | 14.5355 | 14.9876 | 13.7688
Duration | months | 30.9729 | 33.6161 | 35.1292 | 31.286
Delay from the risks | months | 1.9365 | 3.5832 | 5.281 | 2.1025
Expected delay from the risks, calculated exactly (check) | months |  |  |  | 2.1167
4 What drives the cost | [5 empty] | What drives the total cost (US$m)
Lowest and highest mean total cost over ten equal groups of each input (VoseSimSensitivityMean): estimate the top ones more carefully.
Input (ranked by influence) | Lowest mean | Highest mean | Rank
Cost per patient enrolled | 12.8703 | 14.8725 | 1
Running cost per month | 13.1446 | 14.4554 | 2
Clinical hold: delay | 13.7143 | 14.7724 | 3
Enrolment period | 13.4078 | 14.2626 | 4
Dropout rate | 13.3979 | 14.2154 | 5
Slow enrolment: delay | 13.6022 | 14.2672 | 6
Protocol amendment: delay | 13.615 | 14.1081 | 7
Drug supply and logistics | 13.6122 | 14.0498 | 8
Set-up cost | 13.5767 | 13.9976 | 9
Close-out period | 13.6272 | 13.9911 | 10
Cost per patient screened | 13.6326 | 13.9881 | 11
Screen-failure rate | 13.6623 | 13.902 | 12
Start-up period | 13.7407 | 13.8205 | 13
5 How to read these results
• The base estimate — every estimate at its most likely value, and no risks — is US$12.8 million and 28 months. It is enough only about one time in seven: most estimates can overrun by more than they can underrun, and the risks only ever add delay.
• A budget of about US$14.5 million has an 80% chance of being enough: a contingency of about US$1.8 million, 14% of the base estimate. The mean, about US$13.8 million, is what such trials cost on average.
• The top-line results are planned for May 2029, but August is as likely as not (50% confidence) and October gives 80% confidence: the timeline needs about 5.6 months of contingency. The three risks add about two months on average — 2.12 months calculated exactly, which checks the simulation — and a clinical hold, rare as it is, stretches the right tail.
• The cost per patient enrolled drives the cost most: negotiate it, or fix it per visit with the sites. Next come the running cost and whatever extends the trial — a clinical hold, a longer enrolment period, slow enrolment — because every month costs about US$180,000.
• Enrolment here is a single three-point estimate. PH-02 builds it from site openings and recruitment rates: the most common cause of delay in clinical trials.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | TotalCost | TrialMonths
1% | 99% | 11.9042 | 25.7962
3% | 97% | 12.198 | 26.5455
5% | 95% | 12.3684 | 26.9912
7% | 93% | 12.4863 | 27.3396
9% | 91% | 12.5945 | 27.6036
11% | 89% | 12.675 | 27.8182
13% | 87% | 12.7579 | 28.052
15% | 85% | 12.829 | 28.2654
17% | 83% | 12.8906 | 28.4681
19% | 81% | 12.9479 | 28.6378
21% | 79% | 13.0081 | 28.8191
23% | 77% | 13.0615 | 28.9988
25% | 75% | 13.1141 | 29.1807
27% | 73% | 13.1699 | 29.3485
29% | 71% | 13.2167 | 29.4995
31% | 69% | 13.267 | 29.6594
33% | 67% | 13.319 | 29.8124
35% | 65% | 13.3766 | 29.9591
37% | 63% | 13.4195 | 30.1028
39% | 61% | 13.4683 | 30.2289
41% | 59% | 13.5153 | 30.3847
43% | 57% | 13.5572 | 30.508
45% | 55% | 13.6006 | 30.64
47% | 53% | 13.6401 | 30.7624
49% | 51% | 13.6837 | 30.8979
51% | 49% | 13.7309 | 31.0489
53% | 47% | 13.7767 | 31.189
55% | 45% | 13.8185 | 31.3369
57% | 43% | 13.8681 | 31.4857
59% | 41% | 13.9187 | 31.6445
61% | 39% | 13.9746 | 31.8121
63% | 37% | 14.0203 | 31.966
65% | 35% | 14.074 | 32.1333
67% | 33% | 14.1237 | 32.3042
69% | 31% | 14.1762 | 32.4825
71% | 29% | 14.2395 | 32.6581
73% | 27% | 14.2989 | 32.8476
75% | 25% | 14.3649 | 33.0544
77% | 23% | 14.4255 | 33.3024
79% | 21% | 14.4965 | 33.5111
81% | 19% | 14.5681 | 33.7293
83% | 17% | 14.6497 | 33.9843
85% | 15% | 14.7254 | 34.2767
87% | 13% | 14.8227 | 34.6246
89% | 11% | 14.9284 | 34.9474
91% | 9% | 15.0487 | 35.3426
93% | 7% | 15.1745 | 35.8404
95% | 5% | 15.3422 | 36.5452
97% | 3% | 15.609 | 37.5702
99% | 1% | 16.0995 | 39.8677
Overall mean of TotalCost |  | 13.7688
Ranked input (chart) |  |  |  | Highest − mean | Lowest − mean
Cost per patient enrolled |  |  |  | 1.1037 | -0.89847
Running cost per month |  |  |  | 0.68657 | -0.62419
Clinical hold: delay |  |  |  | 1.0036 | -0.054493
Enrolment period |  |  |  | 0.49378 | -0.36105
Dropout rate |  |  |  | 0.4466 | -0.3709
Slow enrolment: delay |  |  |  | 0.49844 | -0.16665
Protocol amendment: delay |  |  |  | 0.33929 | -0.15379
Drug supply and logistics |  |  |  | 0.28099 | -0.15657
Set-up cost |  |  |  | 0.22879 | -0.19207
Close-out period |  |  |  | 0.22234 | -0.14163
Cost per patient screened |  |  |  | 0.21934 | -0.13616
Screen-failure rate |  |  |  | 0.13322 | -0.10652
Start-up period |  |  |  | 0.051694 | -0.028086
Percentiles: TrialMonths | Value
0.5% | 25.4701
1% | 25.7962
2% | 26.2089
3% | 26.5455
4% | 26.772
5% | 26.9912
6% | 27.1831
7% | 27.3396
8% | 27.4574
9% | 27.6036
10% | 27.7412
11% | 27.8182
12% | 27.939
13% | 28.052
14% | 28.1546
15% | 28.2654
16% | 28.3691
17% | 28.4681
18% | 28.5647
19% | 28.6378
20% | 28.7474
21% | 28.8191
22% | 28.9033
23% | 28.9988
24% | 29.0941
25% | 29.1807
26% | 29.2637
27% | 29.3485
28% | 29.423
29% | 29.4995
30% | 29.5757
31% | 29.6594
32% | 29.7272
33% | 29.8124
34% | 29.8932
35% | 29.9591
36% | 30.0265
37% | 30.1028
38% | 30.1674
39% | 30.2289
40% | 30.3161
41% | 30.3847
42% | 30.4457
43% | 30.508
44% | 30.5804
45% | 30.64
46% | 30.6952
47% | 30.7624
48% | 30.8279
49% | 30.8979
50% | 30.9729
51% | 31.0489
52% | 31.1212
53% | 31.189
54% | 31.266
55% | 31.3369
56% | 31.4081
57% | 31.4857
58% | 31.5751
59% | 31.6445
60% | 31.7248
61% | 31.8121
62% | 31.8904
63% | 31.966
64% | 32.0452
65% | 32.1333
66% | 32.2114
67% | 32.3042
68% | 32.3915
69% | 32.4825
70% | 32.5759
71% | 32.6581
72% | 32.7676
73% | 32.8476
74% | 32.9453
75% | 33.0544
76% | 33.184
77% | 33.3024
78% | 33.3985
79% | 33.5111
80% | 33.6161
81% | 33.7293
82% | 33.859
83% | 33.9843
84% | 34.1117
85% | 34.2767
86% | 34.4563
87% | 34.6246
88% | 34.7974
89% | 34.9474
90% | 35.1292
91% | 35.3426
92% | 35.5702
93% | 35.8404
94% | 36.2044
95% | 36.5452
96% | 36.9614
97% | 37.5702
98% | 38.4178
99% | 39.8677
99.5% | 41.1255
Histogram: TrialMonths | Edge | Index | Mid-point | Probability | Below edge
0 | 25.4701 | 1 | 25.7963 | 1.29% | 0.5%
1 | 26.1224 | 2 | 26.4486 | 2.222% | 1.79%
2 | 26.7747 | 5 | 27.1009 | 3.73% | 4.013%
3 | 27.427 | 8 | 27.7532 | 5.525% | 7.742%
4 | 28.0793 | 14 | 28.4055 | 6.59% | 13.27%
5 | 28.7317 | 20 | 29.0578 | 7.619% | 19.86%
6 | 29.384 | 28 | 29.7101 | 8.652% | 27.48%
7 | 30.0363 | 37 | 30.3624 | 9.753% | 36.13%
8 | 30.6886 | 46 | 31.0147 | 9.176% | 45.88%
9 | 31.3409 | 56 | 31.667 | 8.287% | 55.06%
10 | 31.9932 | 64 | 32.3193 | 7.503% | 63.34%
11 | 32.6455 | 71 | 32.9717 | 6.114% | 70.85%
12 | 33.2978 | 77 | 33.624 | 5.766% | 76.96%
13 | 33.9501 | 83 | 34.2763 | 4.141% | 82.73%
14 | 34.6024 | 87 | 34.9286 | 3.72% | 86.87%
15 | 35.2547 | 91 | 35.5809 | 2.595% | 90.59%
16 | 35.907 | 94 | 36.2332 | 1.851% | 93.18%
17 | 36.5593 | 96 | 36.8855 | 1.377% | 95.03%
18 | 37.2117 | 97 | 37.5378 | 0.9356% | 96.41%
19 | 37.864 | 98 | 38.1901 | 0.7213% | 97.35%
20 | 38.5163 | 99 | 38.8424 | 0.4499% | 98.07%
21 | 39.1686 | 99 | 39.4947 | 0.4499% | 98.52%
22 | 39.8209 | 99 | 40.147 | 0.273% | 98.97%
23 | 40.4732 | 100 | 40.7993 | 0.2593% | 99.24%
24 | 41.1255 | 101 |  |  | 99.5%

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
93
230
329
359
342
287
195
120
38
7
53
191
271
350
346
316
248
142
68
15
93
250
341
381
345
294
156
104
32
4
144
341
382
374
281
221
143
72
35
7
79
222
323
364
350
287
187
117
55
16
74
239
337
346
360
244
220
109
54
17
81
225
310
343
338
272
187
138
68
38
93
233
357
363
314
268
195
120
45
12
112
288
381
388
326
242
138
98
18
9
55
208
327
353
367
278
209
136
54
13
1182
0
4
70
150
201
189
113
72
19
1408
0
0
0
17
121
181
147
91
35
1899
0
0
0
4
12
30
23
19
13
33
186
377
519
433
250
138
49
9
6
57
274
509
529
359
166
63
26
10
7
57
274
509
529
359
166
63
26
10
7
819
500
359
130
110
35
18
13
12
4