## About
Patient Recruitment and Trial Timelines |  | ModelRisk example · Pharmaceuticals and biotech · PH-02
When will the last patient be enrolled — and how many sites does it take to be confident of the deadline?
Next: Inputs ▸
Model card
Industry | Pharmaceuticals and biotech
Difficulty | ★★★☆☆ Sixty sites, each with its own opening time and recruitment rate; a Poisson–Gamma model of enrolment month by month for three numbers of sites on the same simulated sites.
Business question | A Phase III trial must enrol 300 patients, and the last patient must be in within 18 months for the results to support the filing on time. The plan — 40 sites at half a patient a month each — just makes it. How likely is the plan to finish on time when sites open late, recruit at very different rates and some recruit no one? And how many sites should be opened to be 80% sure of the deadline?
Who it is for | Clinical operations, feasibility and study start-up teams; programme leaders planning a filing date.
Main outputs | The month the last patient is enrolled for 40, 50 and 60 sites: plan, median, P80 and the chance of meeting the deadline · patients enrolled by the deadline · cumulative enrolment month by month against the plan.
ModelRisk techniques | The Poisson–Gamma recruitment model: each site's rate drawn from a Gamma distribution around an uncertain mean (VoseGamma, VosePERT), sites that never recruit (VoseBernoulli), uncertain opening times (VosePERT) · monthly enrolment as a Poisson count of the open sites' rates (VosePoisson) · three numbers of sites compared on the same sites and the same uniform draws (common random numbers through the U argument) · fan chart against the plan.
File | PH-02 Patient recruitment and trial timelines · Version 1.0 · October 2026 · built with ModelRisk 10
The business question
A company is planning a Phase III trial that must enrol 300 patients; the last patient must be in within 18 months of the first site being ready, or the filing slips by a year. The feasibility study counts on 40 sites recruiting half a patient a month each once they open, about three months after the start: 20 patients a month, and 300 patients in 18 months. But in past trials in this indication the average rate per site ranged from 0.3 to 0.7, sites differed widely — some recruited three times the average — about one site in seven never enrolled anyone, and sites opened anywhere from one to eight months after the start. The company can open 50 or 60 sites instead, at a cost. How many should it open?
How the model works
Four sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | The patients to enrol and the deadline; the three numbers of sites to compare; the average recruitment rate per site (uncertain), the spread between sites, the share of sites that never recruit; the earliest, most likely and latest opening of a site.
2 Sites | For each of sixty sites: VoseBernoulli decides whether it ever recruits, VoseGamma its rate relative to the average, VosePERT the month it opens. An option with 40 sites uses the first 40, so all options share the same sites.
3 Enrolment | A grid of sites by months gives each site's expected patients in each month: its rate times the share of the month it is open. Each option adds up the grid over its sites (SUMIF on the site number); the actual number is Poisson with that mean. One uniform draw per month drives all three options. The month the cumulative count crosses the target, interpolated within the month, is the month the last patient is enrolled.
4 Results | For each option: the plan's completion month, the simulated median and the percentile the Inputs ask for, the chance of meeting the deadline and the patients enrolled by then; the fewest sites that meet the deadline that often; the fan of cumulative enrolment against the plan.
How to use it
Step 1 | Enter your target, deadline and the numbers of sites to compare on the Inputs sheet.
Step 2 | Enter recruitment rates from your feasibility work or previous trials: the average, the spread, the sites that never recruit.
Step 3 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set).
Step 4 | Set how sure you need to be of the deadline on the Inputs sheet: the Results sheet highlights the options that meet it that often.
Workbook map
Inputs | Target, deadline, options, recruitment and site openings.
Sites | Sixty sites: recruits or not, rate, opening, options.
Enrolment | Expected patients by site and month; enrolment month by month for each option; outputs and checks.
Results | Options compared, enrolment against the plan.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Time | Months from the start: the first site can open from month 1.
Rates | Patients a site enrols a month once it is open.
Completion | The month the target is reached, interpolated within the month: 17.5 = half way through month 18.
Plan | Every site recruits at the most likely average rate and opens at the most likely month.
Key assumptions and limitations
Recruitment | A Poisson process at each open site: patients arrive independently at the site's rate, which stays constant once the site is open.
Sites | Rates differ between sites (Gamma); the average rate is uncertain and common to all sites; sites open independently.
Options | The extra sites are like the first 40; screening capacity and drug supply never limit enrolment.
Data | The trial and all figures are invented for this example.
ModelRisk functions used
VoseGamma | Each site's rate relative to the average: a mean of 1 and the spread between sites.
VoseBernoulli | Whether a site ever recruits.
VosePERT | The average rate per site, and the month each site opens.
VosePoisson | Patients enrolled in a month, with a shared uniform draw (U argument) across the options.
VoseUniform | The month's uniform draw that drives all three options.
VoseOutput, VoseSimMean, VoseSimPercentile | Outputs and their statistics on the Results sheet.
Further reading
Recruitment model | Anisimov, V. V. & Fedorov, V. V. (2007). Modelling, prediction and adaptive adjustment of recruitment in multicentre trials. Statistics in Medicine 26(27), 4958–4975.
Site performance | Tufts CSDD (2013). 89% of trials meet enrollment, but timelines slip. Impact Report 15(1).
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
Patient Recruitment and Trial Timelines | [7 empty] | ModelRisk example · Pharmaceuticals and biotech · PH-02
INPUTS · Every assumption the model uses, with its uncertainty and its basis. Change only the yellow cells.
◂ About | [7 empty] | Next: Sites ▸
How to read this sheet: yellow cells are inputs. Orange cells hold ModelRisk distributions and show the current random sample (press F9 to draw again). Low / Most likely / High are the minimum, most likely and maximum for PERT. Mean is the distribution's average (VoseMean); it shows ✗ if a range is out of order.
1 The trial
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Patients to enrol | patients | 300 | Fixed |  |  |  |  | From the sample-size calculation.
Last patient in by the end of month | month | 18 | Fixed |  |  |  |  | Later, and the filing slips by a year.
How sure the company wants to be of the deadline | probability | 80% | Fixed |  |  |  |  | The Results sheet highlights the options that meet the deadline this often.
2 Options
Numbers of sites to compare, in increasing order; each option uses the first sites on the Sites sheet.
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Plan | sites | 40 | Fixed |  |  |  |  | The feasibility study's plan.
More sites | sites | 50 | Fixed
Most sites | sites | 60 | Fixed |  |  |  |  | At most 60: the sites listed.
3 Recruitment
Patients a site enrols a month once it is open.
Assumption | Unit | Value in model | Uncertainty | Low | Most likely | High | Mean | Basis / source (illustrative)
Average rate of a recruiting site | patients / month | 0.39453 | PERT | 0.3 | 0.5 | 0.7 | 0.5 | Previous trials in this indication: 0.3 to 0.7. Common to all sites in an iteration.
Spread between sites (CV) | of the average | 60% | Fixed |  |  |  |  | Some sites recruit three times the average, others a fraction of it.
Chance that a site ever recruits | probability | 85% | Fixed |  |  |  |  | About one site in seven never enrols a patient.
4 Site openings
Month in which a site opens, counted from the start: a PERT for each site.
Assumption | Unit | Value in model | Uncertainty |  |  |  |  | Basis / source (illustrative)
Earliest | month | 1 | Fixed
Most likely | month | 3 | Fixed |  |  |  |  | Contracts and ethics approval.
Latest | month | 8 | Fixed

## Sites
Patient Recruitment and Trial Timelines | [5 empty] | ModelRisk example · Pharmaceuticals and biotech · PH-02
SITES · Whether each site recruits, its rate, when it opens, and the options that include it.
◂ Inputs | [5 empty] | Next: Enrolment ▸
1 This iteration's single value
Quantity |  |  |  | Value | How it is calculated
Gamma shape: 1 ÷ spread² |  |  |  | 2.7778 | Site factors: mean 1, spread as on Inputs
2 The options
Each option uses the first sites in the list below: SUMIF over the site numbers up to its number of sites.
Option | Sites | Recruiting | Patients
|  | sites | a month, all open
Plan | 40 | 36 | 12.8538
More sites | 50 | 44 | 15.8651
Most sites | 60 | 51 | 17.6838
3 The sites
VoseBernoulli: does the site ever recruit? VoseGamma: its rate relative to the average. VosePERT: the month it opens.
Site | Recruits | Factor | Rate | Opens
| 1 / 0 | × average | per month | month
1 | 1 | 0.53443 | 0.21085 | 3.4786
2 | 0 | 0.7898 | 0 | 3.7171
3 | 1 | 0.59661 | 0.23538 | 5.7394
4 | 1 | 0.51846 | 0.20455 | 2.1374
5 | 1 | 1.1053 | 0.43606 | 2.6079
6 | 1 | 0.42607 | 0.1681 | 1.3957
7 | 0 | 0.71121 | 0 | 2.5595
8 | 1 | 0.54501 | 0.21502 | 2.7163
9 | 1 | 0.13688 | 0.054001 | 4.1395
10 | 1 | 2.1293 | 0.84009 | 5.2277
11 | 1 | 0.22486 | 0.088713 | 2.3419
12 | 1 | 0.74536 | 0.29406 | 4.1445
13 | 1 | 0.73286 | 0.28913 | 5.1156
14 | 1 | 0.80914 | 0.31923 | 4.8946
15 | 1 | 0.86714 | 0.34211 | 3.8818
16 | 1 | 0.55043 | 0.21716 | 1.7536
17 | 1 | 0.88916 | 0.3508 | 5.7751
18 | 1 | 0.6442 | 0.25415 | 4.5886
19 | 1 | 1.4532 | 0.57333 | 5.527
20 | 1 | 1.4115 | 0.55689 | 2.8113
21 | 1 | 1.5185 | 0.59909 | 3.4631
22 | 1 | 0.97397 | 0.38426 | 1.2923
23 | 1 | 0.60315 | 0.23796 | 5.9072
24 | 1 | 0.97987 | 0.38658 | 3.2806
25 | 0 | 1.7102 | 0 | 4.0972
26 | 1 | 0.70426 | 0.27785 | 4.8994
27 | 0 | 1.1571 | 0 | 5.5085
28 | 1 | 0.79805 | 0.31485 | 2.899
29 | 1 | 0.71189 | 0.28086 | 5.5512
30 | 1 | 0.52989 | 0.20905 | 4.8992
31 | 1 | 0.26616 | 0.10501 | 2.6706
32 | 1 | 2.1425 | 0.84528 | 4.5644
33 | 1 | 1.1403 | 0.4499 | 2.5775
34 | 1 | 0.80537 | 0.31774 | 3.8613
35 | 1 | 2.1101 | 0.8325 | 1.7465
36 | 1 | 0.98682 | 0.38933 | 2.6077
37 | 1 | 1.1463 | 0.45226 | 3.293
38 | 1 | 1.3193 | 0.52051 | 4.1407
39 | 1 | 0.98448 | 0.3884 | 3.5354
40 | 1 | 0.5392 | 0.21273 | 5.2506
41 | 1 | 1.2784 | 0.50437 | 4.3155
42 | 1 | 0.99822 | 0.39382 | 3.0464
43 | 0 | 4.0913 | 0 | 1.675
44 | 0 | 1.0377 | 0 | 2.4091
45 | 1 | 0.68519 | 0.27033 | 3.2076
46 | 1 | 1.5222 | 0.60054 | 1.9393
47 | 1 | 0.35492 | 0.14002 | 2.9835
48 | 1 | 1.4845 | 0.58567 | 5.4035
49 | 1 | 1.0788 | 0.42561 | 4.9364
50 | 1 | 0.23049 | 0.090936 | 3.3752
51 | 1 | 1.5025 | 0.59277 | 6.2421
52 | 1 | 0.33693 | 0.13293 | 3.5542
53 | 1 | 0.29318 | 0.11567 | 3.3972
54 | 0 | 1.9391 | 0 | 1.5402
55 | 1 | 0.28014 | 0.11052 | 1.4808
56 | 0 | 0.47143 | 0 | 3.9092
57 | 1 | 0.97036 | 0.38283 | 1.9875
58 | 1 | 0.47025 | 0.18553 | 4.4993
59 | 1 | 0.75659 | 0.2985 | 3.626
60 | 0 | 2.9339 | 0 | 2.2487

## Enrolment
Patient Recruitment and Trial Timelines | [50 empty] | ModelRisk example · Pharmaceuticals and biotech · PH-02
ENROLMENT · Forty-eight months of enrolment for each option.
◂ Sites | [50 empty] | Next: Results ▸
Month |  | Total |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
1 This iteration's single values
Quantity | Unit | Value |  | 1: How it is calculated
Months simulated | months | 48 |  | 1: The month columns of this sheet
Plan: completion month on the plan | month | 18 |  | 1: Every site open at the most likely month, recruiting at the most likely rate
More sites: completion month on the plan | month | 15
Most sites: completion month on the plan | month | 13
2 Expected patients by site and month
Each site's rate × the share of the month it is open: MAX(0, MIN(1, month − opening)).
1 | patients |  |  | 0 | 0 | 0 | 0.10995 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085 | 0.21085
2 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0.061332 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538 | 0.23538
4 | patients |  |  | 0 | 0 | 0.17645 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455 | 0.20455
5 | patients |  |  | 0 | 0 | 0.17097 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606 | 0.43606
6 | patients |  |  | 0 | 0.10159 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681 | 0.1681
7 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | patients |  |  | 0 | 0 | 0.061004 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502 | 0.21502
9 | patients |  |  | 0 | 0 | 0 | 0 | 0.046468 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001 | 0.054001
10 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0.64879 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009 | 0.84009
11 | patients |  |  | 0 | 0 | 0.058379 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713 | 0.088713
12 | patients |  |  | 0 | 0 | 0 | 0 | 0.25156 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406 | 0.29406
13 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0.25571 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913 | 0.28913
14 | patients |  |  | 0 | 0 | 0 | 0 | 0.033651 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923 | 0.31923
15 | patients |  |  | 0 | 0 | 0 | 0.040437 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211 | 0.34211
16 | patients |  |  | 0 | 0.05351 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716 | 0.21716
17 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0.078879 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508 | 0.3508
18 | patients |  |  | 0 | 0 | 0 | 0 | 0.10456 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415 | 0.25415
19 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0.27118 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333 | 0.57333
20 | patients |  |  | 0 | 0 | 0.1051 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689 | 0.55689
21 | patients |  |  | 0 | 0 | 0 | 0.32167 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909 | 0.59909
22 | patients |  |  | 0 | 0.27196 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426 | 0.38426
23 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0.022088 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796 | 0.23796
24 | patients |  |  | 0 | 0 | 0 | 0.27812 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658 | 0.38658
25 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | patients |  |  | 0 | 0 | 0 | 0 | 0.027949 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785 | 0.27785
27 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | patients |  |  | 0 | 0 | 0.031795 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485 | 0.31485
29 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0.12605 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086 | 0.28086
30 | patients |  |  | 0 | 0 | 0 | 0 | 0.021083 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905 | 0.20905
31 | patients |  |  | 0 | 0 | 0.034585 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501 | 0.10501
32 | patients |  |  | 0 | 0 | 0 | 0 | 0.36817 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528 | 0.84528
33 | patients |  |  | 0 | 0 | 0.19009 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499 | 0.4499
34 | patients |  |  | 0 | 0 | 0 | 0.044072 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774 | 0.31774
35 | patients |  |  | 0 | 0.21104 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325 | 0.8325
36 | patients |  |  | 0 | 0 | 0.15274 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933 | 0.38933
37 | patients |  |  | 0 | 0 | 0 | 0.31974 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226 | 0.45226
38 | patients |  |  | 0 | 0 | 0 | 0 | 0.44727 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051 | 0.52051
39 | patients |  |  | 0 | 0 | 0 | 0.18045 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884 | 0.3884
40 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0.15941 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273 | 0.21273
41 | patients |  |  | 0 | 0 | 0 | 0 | 0.34524 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437 | 0.50437
42 | patients |  |  | 0 | 0 | 0 | 0.37555 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382 | 0.39382
43 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | patients |  |  | 0 | 0 | 0 | 0.2142 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033 | 0.27033
46 | patients |  |  | 0 | 0.036436 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054 | 0.60054
47 | patients |  |  | 0 | 0 | 0.0023132 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002 | 0.14002
48 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0.34937 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567 | 0.58567
49 | patients |  |  | 0 | 0 | 0 | 0 | 0.027067 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561 | 0.42561
50 | patients |  |  | 0 | 0 | 0 | 0.056815 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936 | 0.090936
51 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.44923 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277 | 0.59277
52 | patients |  |  | 0 | 0 | 0 | 0.059261 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293 | 0.13293
53 | patients |  |  | 0 | 0 | 0 | 0.069721 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567 | 0.11567
54 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | patients |  |  | 0 | 0.057386 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052 | 0.11052
56 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | patients |  |  | 0 | 0.0048026 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283 | 0.38283
58 | patients |  |  | 0 | 0 | 0 | 0 | 0.092893 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553 | 0.18553
59 | patients |  |  | 0 | 0 | 0 | 0.11163 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985 | 0.2985
60 | patients |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 The month's uniform draw
VoseUniform: one draw a month, passed as the U argument of all three options' Poisson counts so that they share their luck.
Uniform draw | 0 – 1 |  |  | 0.98878 | 0.77613 | 0.15742 | 0.12831 | 0.17851 | 0.34908 | 0.17278 | 0.44655 | 0.15954 | 0.36518 | 0.74062 | 0.7695 | 0.0086049 | 0.59232 | 0.5685 | 0.69719 | 0.52465 | 0.45319 | 0.43947 | 0.49954 | 0.12576 | 0.97904 | 0.74919 | 0.37922 | 0.81668 | 0.42184 | 0.79941 | 0.090054 | 0.47219 | 0.95793 | 0.2962 | 0.95868 | 0.13298 | 0.15984 | 0.035796 | 0.54653 | 0.2952 | 0.37051 | 0.38602 | 0.25293 | 0.52209 | 0.055696 | 0.12568 | 0.12335 | 0.096313 | 0.34052 | 0.12483 | 0.030125
4 Option 1: plan
Sites: 40. Expected patients: the grid above summed over the option's sites; the count is Poisson.
Expected patients | patients |  |  | 0 | 0.63809 | 2.5831 | 5.6568 | 8.3601 | 11.4569 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538 | 12.8538
Patients coming forward | patients |  |  | 0 | 1 | 1 | 3 | 6 | 10 | 9 | 12 | 9 | 11 | 15 | 15 | 5 | 14 | 13 | 15 | 13 | 12 | 12 | 13 | 9 | 21 | 15 | 12 | 16 | 12 | 16 | 8 | 12 | 19 | 11 | 19 | 9 | 9 | 7 | 13 | 11 | 12 | 12 | 10 | 13 | 7 | 9 | 9 | 8 | 11 | 9 | 7
Enrolled, cumulative (stops at the target) | patients |  | 0 | 0 | 1 | 2 | 5 | 11 | 21 | 30 | 42 | 51 | 62 | 77 | 92 | 97 | 111 | 124 | 139 | 152 | 164 | 176 | 189 | 198 | 219 | 234 | 246 | 262 | 274 | 290 | 298 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300
Target crossed this month: when, within the month | month |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative, plan's sites (output, for the fan chart) | patients |  |  | 0 | 1 | 2 | 5 | 11 | 21 | 30 | 42 | 51 | 62 | 77 | 92 | 97 | 111 | 124 | 139 | 152 | 164 | 176 | 189 | 198 | 219 | 234 | 246 | 262 | 274 | 290 | 298 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300
5 Option 2: more sites
Sites: 50. Expected patients: the grid above summed over the option's sites; the count is Poisson.
Expected patients | patients |  |  | 0 | 0.67453 | 3.186 | 7.0439 | 10.228 | 14.232 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651 | 15.8651
Patients coming forward | patients |  |  | 0 | 1 | 1 | 4 | 7 | 13 | 12 | 15 | 12 | 14 | 18 | 19 | 7 | 17 | 16 | 18 | 16 | 15 | 15 | 16 | 11 | 24 | 18 | 14 | 19 | 15 | 19 | 11 | 15 | 23 | 14 | 23 | 11 | 12 | 9 | 16 | 14 | 14 | 15 | 13 | 16 | 10 | 11 | 11 | 11 | 14 | 11 | 9
Enrolled, cumulative (stops at the target) | patients |  | 0 | 0 | 1 | 2 | 6 | 13 | 26 | 38 | 53 | 65 | 79 | 97 | 116 | 123 | 140 | 156 | 174 | 190 | 205 | 220 | 236 | 247 | 271 | 289 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300
Target crossed this month: when, within the month | month |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.7857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 Option 3: most sites
Sites: 60. Expected patients: the grid above summed over the option's sites; the count is Poisson.
Expected patients | patients |  |  | 0 | 0.73671 | 3.6793 | 7.7779 | 11.3614 | 15.4579 | 17.5403 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838 | 17.6838
Patients coming forward | patients |  |  | 0 | 1 | 2 | 5 | 8 | 14 | 14 | 17 | 14 | 16 | 20 | 21 | 9 | 19 | 18 | 20 | 18 | 17 | 17 | 18 | 13 | 27 | 20 | 16 | 21 | 17 | 21 | 12 | 17 | 25 | 15 | 25 | 13 | 14 | 11 | 18 | 15 | 16 | 16 | 15 | 18 | 11 | 13 | 13 | 12 | 16 | 13 | 10
Enrolled, cumulative (stops at the target) | patients |  | 0 | 0 | 1 | 3 | 8 | 16 | 30 | 44 | 61 | 75 | 91 | 111 | 132 | 141 | 160 | 178 | 198 | 216 | 233 | 250 | 268 | 281 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300
Target crossed this month: when, within the month | month |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.7037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 Value in this iteration
Key outputs, recorded by ModelRisk at every sample (VoseOutput). Their statistics appear on the Results sheet.
Output | Unit | Value |  | 1: Meaning
Plan: last patient enrolled | month | 28.1667 |  | 1: The month the target is crossed; one past the last month if it never is.
More sites: last patient enrolled | month | 23.7857
Most sites: last patient enrolled | month | 21.7037
Plan: patients enrolled by the deadline | patients | 164
More sites: patients enrolled by the deadline | patients | 205
Most sites: patients enrolled by the deadline | patients | 233
Plan: deadline met? (1 = yes) | 1 / 0 | 0
More sites: deadline met? (1 = yes) | 1 / 0 | 0
Most sites: deadline met? (1 = yes) | 1 / 0 | 0
Plan: patients a month with all its sites open | patients | 12.8538 |  | 1: Against the plan's sites × the most likely rate.
8 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
Every range on the Inputs sheet is in order (no ✗ under Mean) |  | OK
Each option uses at most the sites listed |  | OK
The options are in increasing numbers of sites |  | OK
Site openings: earliest ≤ most likely ≤ latest |  | OK
The deadline lies within the months simulated |  | OK

## Results
Patient Recruitment and Trial Timelines | [7 empty] | ModelRisk example · Pharmaceuticals and biotech · PH-02
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Enrolment
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 When will the last patient be enrolled? | [6 empty] | Month of the last patient in — cumulative probability
Month of the last patient in, by number of sites. Highlighted: the options that meet the deadline as often as the Inputs ask.
Option | Plan | Median | P80 | Deadline | By deadline
| month | month | month | chance met | patients, mean
Plan: 40 sites | 18 | 21.3684 | 25 | 15.4% | 241.8521
More sites: 50 sites | 15 | 17.75 | 20.5556 | 53.69% | 279.4064
Most sites: 60 sites | 13 | 15.3462 | 17.625 | 83.27% | 294.6911
Fewest sites that meet the deadline 80% of the time |  | Most sites: 60 sites
Deadline: the end of month 18. Plan: every site open at the most likely month, recruiting at the most likely rate.
2 The plan's sites, month by month | [6 empty] | Cumulative enrolment with the plan's sites
Cumulative enrolment against the plan and the target.
Measure | Unit | Value
Patients a month with all sites open, on the plan | patients | 20
…simulated mean | patients | 16.9878
…chance of falling short of the plan's rate | probability | 81.31%
Sites that never recruit, on average | sites | 6
Patients enrolled by the deadline, mean | patients | 241.8521
…10th percentile | patients | 183
3 How to read these results
• The plan — 40 sites at half a patient a month, open from month 3 — enrols the 300th patient at the end of month 18, just in time. The simulation gives it a 15% chance of meeting the deadline: the median finish is month 21.4, and one trial in five is still enrolling after month 25.
• The plan leaves out three things. About six of the 40 sites never recruit; the others recruit at very different rates, around an average that is itself uncertain; and the sites open over several months. With all sites open, the 40 sites enrol about 17 patients a month on average, not 20, and fall short of the plan's rate in 81% of futures.
• Opening 50 sites gives an even chance of the deadline (54%); 60 sites give 83%, with the P80 finish in month 17.6. The plan's arithmetic says 60 sites would finish five months early, in month 13: averages hide how often enrolment runs slow. Sixty is the fewest of the three that meets the deadline 80% of the time; change the confidence on the Inputs sheet and the line under the table follows.
• By the deadline the 40 sites have enrolled about 242 patients on average, and fewer than 183 one time in ten. Tracking actual enrolment against the fan chart shows early whether rescue sites are needed.
• Recruitment rates are the weakest assumption. Update them as the sites report: a Gamma prior on each site's rate and its Poisson counts give a Gamma posterior, and the forecast sharpens within a few months (PH-08 shows Bayesian updating).
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | Months_1 | Months_2 | Months_3
1% | 99% | 15.0606 | 12.8182 | 11.3871
3% | 97% | 15.9444 | 13.5909 | 12
5% | 95% | 16.48 | 14 | 12.3125
7% | 93% | 16.8519 | 14.3214 | 12.5714
9% | 91% | 17.1667 | 14.5556 | 12.8
11% | 89% | 17.4828 | 14.7778 | 12.9615
13% | 87% | 17.7308 | 15 | 13.125
15% | 85% | 17.9643 | 15.1875 | 13.2759
17% | 83% | 18.2 | 15.35 | 13.4091
19% | 81% | 18.4211 | 15.5 | 13.5417
21% | 79% | 18.625 | 15.6522 | 13.6667
23% | 77% | 18.8261 | 15.8148 | 13.7778
25% | 75% | 19 | 15.9615 | 13.9032
27% | 73% | 19.1818 | 16.1053 | 14.0323
29% | 71% | 19.375 | 16.25 | 14.1562
31% | 69% | 19.5625 | 16.3913 | 14.2647
33% | 67% | 19.7619 | 16.5238 | 14.3846
35% | 65% | 19.95 | 16.6667 | 14.5
37% | 63% | 20.1364 | 16.8125 | 14.6071
39% | 61% | 20.3158 | 16.9524 | 14.7097
41% | 59% | 20.5 | 17.0952 | 14.8261
43% | 57% | 20.7059 | 17.2174 | 14.9375
45% | 55% | 20.875 | 17.3667 | 15.0476
47% | 53% | 21.0769 | 17.5263 | 15.1667
49% | 51% | 21.2778 | 17.6667 | 15.2941
51% | 49% | 21.4706 | 17.8333 | 15.4062
53% | 47% | 21.6818 | 18 | 15.5294
55% | 45% | 21.8824 | 18.1304 | 15.6552
57% | 43% | 22.0833 | 18.28 | 15.8182
59% | 41% | 22.2778 | 18.4545 | 15.9412
61% | 39% | 22.5 | 18.6364 | 16.0625
63% | 37% | 22.7143 | 18.8 | 16.2
65% | 35% | 22.9231 | 18.9524 | 16.3636
67% | 33% | 23.1429 | 19.1429 | 16.5
69% | 31% | 23.3889 | 19.3243 | 16.6667
71% | 29% | 23.625 | 19.5263 | 16.8095
73% | 27% | 23.9167 | 19.7333 | 16.9545
75% | 25% | 24.2 | 19.95 | 17.1176
77% | 23% | 24.5 | 20.1667 | 17.3
79% | 21% | 24.8421 | 20.4091 | 17.5
81% | 19% | 25.2 | 20.6923 | 17.7619
83% | 17% | 25.5263 | 21 | 18
85% | 15% | 25.9375 | 21.3 | 18.2353
87% | 13% | 26.4375 | 21.6154 | 18.52
89% | 11% | 26.9333 | 22 | 18.8421
91% | 9% | 27.5 | 22.5263 | 19.2308
93% | 7% | 28.1765 | 23.0625 | 19.72
95% | 5% | 29.1765 | 23.8462 | 20.2857
97% | 3% | 30.6471 | 24.9091 | 21.1667
99% | 1% | 33.3846 | 27 | 22.6471
Period | 10th percentile | Median | 90th percentile | Mean | Target | Plan
1 | 0 | 0 | 0 | 0 | 300 | 0
2 | 0 | 0 | 2 | 0.68033 | 300 | 0
3 | 2 | 5 | 9 | 4.903 | 300 | 0
4 | 7 | 13 | 21 | 13.9244 | 300 | 20
5 | 17 | 26 | 38 | 27.0625 | 300 | 40
6 | 29 | 42 | 58 | 42.7961 | 300 | 60
7 | 42 | 59 | 79 | 59.5691 | 300 | 80
8 | 54 | 75 | 101 | 76.5072 | 300 | 100
9 | 67 | 92 | 122 | 93.4816 | 300 | 120
10 | 80 | 109 | 143 | 110.3934 | 300 | 140
11 | 93 | 126 | 165 | 127.3968 | 300 | 160
12 | 105 | 143 | 186 | 144.3587 | 300 | 180
13 | 118 | 159 | 207 | 161.385 | 300 | 200
14 | 131 | 176 | 229 | 178.4115 | 300 | 220
15 | 144 | 193 | 250 | 195.2463 | 300 | 240
16 | 157 | 210 | 271 | 211.7893 | 300 | 260
17 | 169 | 227 | 293 | 227.5149 | 300 | 280
18 | 183 | 243 | 300 | 241.852 | 300 | 300
19 | 195 | 260 | 300 | 254.4693 | 300 | 300
20 | 208 | 277 | 300 | 265.1698 | 300 | 300
21 | 221 | 294 | 300 | 273.8772 | 300 | 300
22 | 233 | 300 | 300 | 280.8462 | 300 | 300
23 | 246 | 300 | 300 | 286.1739 | 300 | 300
24 | 259 | 300 | 300 | 290.171 | 300 | 300
25 | 272 | 300 | 300 | 293.149 | 300 | 300
26 | 285 | 300 | 300 | 295.2769 | 300 | 300
27 | 297 | 300 | 300 | 296.7869 | 300 | 300
28 | 300 | 300 | 300 | 297.8237 | 300 | 300
29 | 300 | 300 | 300 | 298.5441 | 300 | 300
30 | 300 | 300 | 300 | 299.024 | 300 | 300
31 | 300 | 300 | 300 | 299.3529 | 300 | 300
32 | 300 | 300 | 300 | 299.5747 | 300 | 300
33 | 300 | 300 | 300 | 299.7108 | 300 | 300
34 | 300 | 300 | 300 | 299.8022 | 300 | 300
35 | 300 | 300 | 300 | 299.8645 | 300 | 300
36 | 300 | 300 | 300 | 299.9054 | 300 | 300
37 | 300 | 300 | 300 | 299.933 | 300 | 300
38 | 300 | 300 | 300 | 299.9541 | 300 | 300
39 | 300 | 300 | 300 | 299.9722 | 300 | 300
40 | 300 | 300 | 300 | 299.9832 | 300 | 300
41 | 300 | 300 | 300 | 299.99 | 300 | 300
42 | 300 | 300 | 300 | 299.9937 | 300 | 300
43 | 300 | 300 | 300 | 299.9975 | 300 | 300
44 | 300 | 300 | 300 | 299.9985 | 300 | 300
45 | 300 | 300 | 300 | 299.9997 | 300 | 300
46 | 300 | 300 | 300 | 300 | 300 | 300
47 | 300 | 300 | 300 | 300 | 300 | 300
48 | 300 | 300 | 300 | 300 | 300 | 300

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
0
0
0
0
0
2000
0
0
0
0
1134
530
0
224
76
0
26
0
8
2
195
520
546
249
272
136
23
40
16
3
53
255
587
520
350
147
60
23
3
2
15
166
361
581
472
215
114
52
21
3
10
112
364
647
448
262
108
43
5
1
20
139
362
535
473
276
133
47
13
2
9
61
324
478
552
341
148
70
14
3
7
69
274
529
520
367
155
66
11
2
7
57
266
513
518
371
177
72
16
3
6
65
302
549
542
339
145
42
9
1
7
68
350
527
561
302
145
33
6
1
5
62
285
499
537
361
182
56
11
2
3
36
190
369
498
438
267
137
49
13
2
24
102
284
394
442
368
210
111
63
2
15
77
186
316
397
391
278
184
154
2
8
38
133
238
333
371
323
246
308
2
8
31
93
179
260
320
318
285
504
2
8
25
76
131
212
262
275
306
703
2
6
19
47
108
144
231
245
256
942
2
4
11
34
78
104
176
208
234
1149
2
7
6
28
58
85
132
165
194
1323
2
6
6
17
38
71
100
131
146
1483
2
4
6
10
28
57
66
97
129
1601
2
3
4
6
22
29
61
63
100
1710
2
3
4
4
11
19
51
50
68
1788
2
1
3
4
11
11
20
55
42
1851
2
0
4
3
7
10
13
32
48
1881
2
0
1
3
6
7
7
15
37
1922
2
0
0
4
3
5
7
7
23
1949
2
0
0
3
3
3
5
6
8
1970
2
0
0
3
2
2
3
4
7
1977
2
0
1
2
3
0
3
1
4
1984
2
0
0
1
2
2
3
0
2
1988
2
0
0
0
2
2
1
2
2
1989
2
0
0
0
1
1
2
1
1
1992
2
0
0
0
0
1
2
1
1
1993
2
0
0
0
0
0
1
1
1
1995
1
1
0
0
0
0
0
1
0
1997
1
1
0
0
0
0
0
0
0
1998
1
0
0
1
0
0
0
0
0
1998
1
0
0
0
1
0
0
0
0
1998
1
0
0
0
0
1
0
0
0
1998
1
0
0
0
0
0
0
0
0
1999
1
0
0
0
0
0
0
0
0
1999
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
56
465
679
468
215
85
21
7
2
2
52
441
676
471
230
88
30
8
3
1
59
413
608
480
262
118
40
10
7
3
2
8
31
93
179
260
320
318
285
504
1
1
8
26
51
88
135
190
204
1296
1
1
4
9
13
27
32
61
82
1770
1699
0
0
0
0
0
0
0
0
301
930
0
0
0
0
0
0
0
0
1070
346
0
0
0
0
0
0
0
0
1654
11
118
332
528
481
307
161
50
10
2
35
136
233
291
373
320
284
195
109
24