## About
R&D Portfolio: Which Projects to Fund |  | ModelRisk example · Pharmaceuticals and biotech · PH-04
Eight projects, one budget: which to fund for value, for a steady pipeline, and within the money we have?
Next: Inputs ▸
Model card
Industry | Pharmaceuticals and biotech
Difficulty | ★★★★★ Eight projects at different stages, each with phase-by-phase attrition and spending year by year; shared mechanisms that correlate their Phase II results; four portfolios compared on value, launches and the budget.
Business question | A mid-sized pharma company has eight development projects, from preclinical to Phase III, and an R&D budget of US$170 million a year. Funding them all would break the budget. Three pairs of projects share a biological mechanism, so if the mechanism fails in one, it probably fails in the other. Which projects should it fund to create the most value, keep a launch coming, and stay within the budget?
Who it is for | R&D portfolio committees, heads of development and strategy, finance teams in pharma and biotech.
Main outputs | For four candidate portfolios: NPV (mean and 1 in 10), expected launches, the chance of no launch, and the chance of breaking the budget · for each project: chance of launch, mean NPV, R&D cost and value per dollar · the effect of shared mechanisms · spending by year against the budget.
ModelRisk techniques | Phase-by-phase attrition for eight projects (VoseBernoulli) · shared-mechanism correlation of Phase II results through bivariate Normal copulas (VoseCopulaBiNormal, passed to VoseBernoulli's U argument) · value at launch as a Lognormal from P10 and P90 (VoseLognormalAlt) · spending year by year that stops when a project fails · four portfolios on the same simulated outcomes · fan chart of spending against the budget.
File | PH-04 R&D portfolio which projects to fund · Version 1.0 · October 2026 · built with ModelRisk 10
The business question
A mid-sized pharma company has eight projects in development: a solid-tumour drug in Phase III, three projects in Phase II, two in Phase I and two in preclinical work. Three pairs share a mechanism — two oncology projects act on the same apoptosis pathway, two immunology projects on the same interleukin, and two neurology projects on amyloid — so their Phase II results tend to agree. Each phase costs money, takes time and may fail; a project that fails stops spending. The R&D budget is US$170 million a year for the next five years, and funding everything would need more in the early years. The portfolio committee is weighing four options: fund everything, fund one project per mechanism, fund only the late-stage projects, or fund a set that stays within the budget.
How the model works
Five sheets after this one, read from left to right. Each one feeds the next.
1 Inputs | The annual R&D budget, the correlation between the Phase II results of projects that share a mechanism, the discount rate and the portfolio to chart.
2 Projects | The duration and yearly cost of each phase; each project's current stage, chance of success in each phase and value at launch (P10 and P90); which projects each portfolio funds.
3 Pipeline | Three bivariate Normal copulas draw correlated uniforms for the Phase II results of each pair. VoseBernoulli decides every remaining phase. The last phase each project works on (its first failure, or the review), the year each phase would end and the launch year follow; the value at launch is discounted to today.
4 Spend | The phase each project works on in each year — a Gantt chart of the iteration — gives its spending: the yearly cost of that phase. Each portfolio adds up the projects it funds; its NPV, its launches, and whether it spends more than the budget in a year of the budget horizon.
5 Results | The portfolios side by side; the projects ranked by value per dollar; how shared mechanisms make successes and failures come in pairs; spending against the budget.
How to use it
Step 1 | Enter your projects on the Projects sheet: stage, success rates by phase, value at launch.
Step 2 | Mark which projects each candidate portfolio funds, and set the budget on the Inputs sheet.
Step 3 | Run a simulation from the ModelRisk ribbon (10,000 samples with a fixed seed are set).
Step 4 | Compare the portfolios on value, launches and budget risk; try other combinations.
Workbook map
Inputs | Budget, correlation, discount rate, chart choice.
Projects | Phases, projects, portfolios.
Pipeline | Correlated Phase II results, phase results, schedule, project values.
Spend | The phase under way (a Gantt chart), spending by year, the budget; outputs and checks.
Results | Portfolios, projects, shared mechanisms, spending.
Colour key
Input | An assumption you may change. Only these cells are inputs.
Uncertain variable | A ModelRisk distribution: a new random value is drawn at every recalculation (F9) and every simulation sample.
Calculation | A formula. Do not overwrite.
Key output | Marked with VoseOutput; its full distribution is recorded when you simulate.
Simulation result | A VoseSim… function: a statistic of the last simulation, filled in automatically.
Units and conventions
Money | US$ million (US$m); costs discounted from the middle of each year, values from the launch year.
Time | Years from now; year 1 is the coming year.
Value at launch | The NPV, at launch, of the product's sales after all commercial costs.
Over budget | A portfolio's spending exceeds the budget in at least one year of the budget horizon (five years as shipped).
Key assumptions and limitations
Phases | Whole years, back to back; a project stops spending when a phase fails.
Correlation | Only through the Phase II results of projects sharing a mechanism; all other results are independent.
Unfunded projects | Shelved: no cost and no value. Partnering them out could recover some value.
Data | The company, the projects and all figures are invented for this example.
ModelRisk functions used
VoseCopulaBiNormal | Correlated uniforms for the Phase II results of two projects sharing a mechanism (array).
VoseBernoulli | Whether each phase succeeds; the U argument takes the copula's uniform for Phase II.
VoseLognormalAlt | Each project's value at launch from its P10 and P90.
VoseOutput, VoseSimMean, VoseSimPercentile | Outputs and their statistics on the Results sheet.
Further reading
R&D productivity | Paul, S. M. et al. (2010). How to improve R&D productivity: the pharmaceutical industry's grand challenge. Nature Reviews Drug Discovery 9, 203–214.
Portfolio decisions | Vose, D. (2008). Risk Analysis: A Quantitative Guide, 3rd edition. Wiley.
© 2026 Vose Software · www.vosesoftware.com · An illustrative example: the figures are invented for teaching and do not describe a real company, project or asset.

## Inputs
R&D Portfolio: Which Projects to Fund |  |  |  | ModelRisk example · Pharmaceuticals and biotech · PH-04
INPUTS · The budget, the correlation and the discount rate. The phases, the projects and the portfolios are on the Projects sheet. Change only the yellow cells.
◂ About |  |  |  | Next: Projects ▸
How to read this sheet: yellow cells are inputs.
1 Budget and finance
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
R&D budget | US$m a year | 170 | Fixed | For each year of the budget horizon below.
Budget horizon | years | 5 | Fixed | The years the budget is set for.
Correlation of Phase II results within a mechanism | copula ρ | 0.8 | Fixed | On the Normal scale: if the mechanism fails in one project, it probably fails in the other.
Discount rate | per year | 10% | Fixed
2 Chart
Assumption | Unit | Value in model | Uncertainty | Basis / source (illustrative)
Portfolio shown in the spending chart | 1 – 4 | 2 | Fixed | 1 Everything · 2 One per mechanism · 3 Late stage · 4 Within budget.

## Projects
R&D Portfolio: Which Projects to Fund | [8 empty] | ModelRisk example · Pharmaceuticals and biotech · PH-04
PROJECTS · Phases, projects and the portfolios to compare. Change only the yellow cells.
◂ Inputs | [8 empty] | Next: Pipeline ▸
1 Development phases
Duration and yearly cost of each phase, the same for every project.
|  |  | Preclinical | Phase I | Phase II | Phase III | Review
Duration | years |  | 1 | 1 | 2 | 3 | 1
Cost per year | US$m |  | 8 | 15 | 25 | 60 | 5
2 Projects
Stage now, chance of success in each remaining phase, and value at launch (the NPV of its sales at launch).
Project | Mechanism | Stage now | Preclinical | Phase I | Phase II | Phase III | Review | Value P10 | Value P90
|  |  | chance of success |  |  |  |  | US$m at launch
A ONC-301 solid tumours | Kinase inhibitor (own) | Phase III | 65% | 65% | 35% | 60% | 90% | 800 | 2500
B ONC-210 leukaemia | Mechanism 1: apoptosis | Phase II | 65% | 65% | 35% | 60% | 90% | 600 | 2000
C IMM-220 psoriasis | Mechanism 2: IL pathway | Phase II | 65% | 65% | 35% | 60% | 90% | 500 | 1800
D IMM-110 Crohn's disease | Mechanism 2: IL pathway | Phase I | 65% | 65% | 35% | 60% | 90% | 500 | 1800
E NEU-120 Alzheimer's disease | Mechanism 3: amyloid | Phase I | 65% | 65% | 25% | 55% | 90% | 900 | 3500
F NEU-010 Parkinson's disease | Mechanism 3: amyloid | Preclinical | 65% | 65% | 25% | 55% | 90% | 900 | 3500
G RARE-230 enzyme deficiency | Enzyme replacement (own) | Phase II | 65% | 65% | 50% | 70% | 95% | 500 | 1200
H ONC-020 lymphoma | Mechanism 1: apoptosis | Preclinical | 65% | 65% | 35% | 60% | 90% | 600 | 2000
Phases before the current stage are already passed: their chances are not used. Pairs sharing a mechanism: B and H, C and D, E and F.
3 Portfolios
1 = the portfolio funds the project; 0 = shelved.
Project |  |  | Everything | One per mechanism | Late stage | Within budget
A ONC-301 solid tumours |  |  | 1 | 1 | 1 | 1
B ONC-210 leukaemia |  |  | 1 | 1 | 1 | 0
C IMM-220 psoriasis |  |  | 1 | 1 | 1 | 0
D IMM-110 Crohn's disease |  |  | 1 | 0 | 0 | 0
E NEU-120 Alzheimer's disease |  |  | 1 | 1 | 0 | 1
F NEU-010 Parkinson's disease |  |  | 1 | 0 | 0 | 1
G RARE-230 enzyme deficiency |  |  | 1 | 1 | 1 | 1
H ONC-020 lymphoma |  |  | 1 | 0 | 0 | 0
Projects funded |  |  | 8 | 5 | 4 | 4

## Pipeline
R&D Portfolio: Which Projects to Fund | [8 empty] | ModelRisk example · Pharmaceuticals and biotech · PH-04
PIPELINE · This iteration's results phase by phase, the schedule, and each project's value (US$m).
◂ Projects | [8 empty] | Next: Spend ▸
1 Shared mechanisms: correlated Phase II results
VoseCopulaBiNormal: two uniforms whose Normal scores have the correlation on the Inputs sheet, one pair per mechanism.
Project |  | Uniform |  | Pair
B ONC-210 leukaemia |  | 0.33542 |  | B and H share a mechanism
H ONC-020 lymphoma |  | 0.37894
C IMM-220 psoriasis |  | 0.62673 |  | C and D share a mechanism
D IMM-110 Crohn's disease |  | 0.93288
E NEU-120 Alzheimer's disease |  | 0.71145 |  | E and F share a mechanism
F NEU-010 Parkinson's disease |  | 0.52634
2 Phase results
1 = the phase succeeds. Phases already passed show 1; VoseBernoulli decides the others (Phase II of a paired project takes its copula uniform). The project works until the first phase that fails.
Project | Stage now | Preclinical | Phase I | Phase II | Phase III | Review | Last phase | Launched
phase number |  | 1 | 2 | 3 | 4 | 5
A ONC-301 solid tumours | 4 | 1 | 1 | 1 | 0 | 1 | 4 | 0
B ONC-210 leukaemia | 3 | 1 | 1 | 0 | 1 | 1 | 3 | 0
C IMM-220 psoriasis | 3 | 1 | 1 | 0 | 1 | 0 | 3 | 0
D IMM-110 Crohn's disease | 2 | 1 | 1 | 1 | 0 | 1 | 4 | 0
E NEU-120 Alzheimer's disease | 2 | 1 | 1 | 0 | 0 | 1 | 3 | 0
F NEU-010 Parkinson's disease | 1 | 1 | 1 | 0 | 1 | 1 | 3 | 0
G RARE-230 enzyme deficiency | 3 | 1 | 1 | 0 | 1 | 1 | 3 | 0
H ONC-020 lymphoma | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0
Stage now and last phase are phase numbers: 1 Preclinical, 2 Phase I, 3 Phase II, 4 Phase III, 5 Review. Last phase: the first one that fails, or 5. Launched: the last phase succeeded.
3 Schedule
The year each remaining phase would end if everything succeeds: the previous end plus the phase's duration. Phases already passed show –.
Project | Now | Preclinical | Phase I | Phase II | Phase III | Review | Stops after | Launch
phase number |  | 1 | 2 | 3 | 4 | 5
A ONC-301 solid tumours | 0 | -99 | -99 | -99 | 3 | 4 | 3 | 4
B ONC-210 leukaemia | 0 | -99 | -99 | 2 | 5 | 6 | 2 | 6
C IMM-220 psoriasis | 0 | -99 | -99 | 2 | 5 | 6 | 2 | 6
D IMM-110 Crohn's disease | 0 | -99 | 1 | 3 | 6 | 7 | 6 | 7
E NEU-120 Alzheimer's disease | 0 | -99 | 1 | 3 | 6 | 7 | 3 | 7
F NEU-010 Parkinson's disease | 0 | 1 | 2 | 4 | 7 | 8 | 4 | 8
G RARE-230 enzyme deficiency | 0 | -99 | -99 | 2 | 5 | 6 | 2 | 6
H ONC-020 lymphoma | 0 | 1 | 2 | 4 | 7 | 8 | 1 | 8
Stops after: the end of the last phase it works on. Launch: the end of the review.
4 Value of each project
VoseLognormalAlt: value at launch from the P10 and the P90, discounted from the launch year; less the R&D spending, discounted.
Project |  | Launched | Value at | PV of | PV of | NPV
|  | 1 / 0 | launch | value | R&D cost
A ONC-301 solid tumours |  | 0 | 1770.4587 | 0 | 156.4939 | -156.4939
B ONC-210 leukaemia |  | 0 | 700.0604 | 0 | 45.5062 | -45.5062
C IMM-220 psoriasis |  | 0 | 866.0205 | 0 | 45.5062 | -45.5062
D IMM-110 Crohn's disease |  | 0 | 901.0513 | 0 | 173.2474 | -173.2474
E NEU-120 Alzheimer's disease |  | 0 | 2260.7177 | 0 | 55.6712 | -55.6712
F NEU-010 Parkinson's disease |  | 0 | 742.3679 | 0 | 58.2379 | -58.2379
G RARE-230 enzyme deficiency |  | 0 | 410.8004 | 0 | 45.5062 | -45.5062
H ONC-020 lymphoma |  | 0 | 1420.0289 | 0 | 7.6277 | -7.6277

## Spend
R&D Portfolio: Which Projects to Fund | [11 empty] | ModelRisk example · Pharmaceuticals and biotech · PH-04
SPEND · R&D spending by project and by portfolio, year by year; each portfolio's results (US$m).
◂ Pipeline | [11 empty] | Next: Results ▸
Year |  | Total | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Discount factor (mid-year) |  |  | 0.95346 | 0.86678 | 0.78799 | 0.71635 | 0.65123 | 0.59203 | 0.5382 | 0.48928 | 0.4448 | 0.40436
1 Phase under way
The phase each project works on in the year, if it is still going: one more than the phases that ended before the year (COUNTIF over its schedule). A Gantt chart of this iteration.
A ONC-301 solid tumours | phase |  | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B ONC-210 leukaemia | phase |  | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C IMM-220 psoriasis | phase |  | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D IMM-110 Crohn's disease | phase |  | 2 | 3 | 3 | 4 | 4 | 4 | 0 | 0 | 0 | 0
E NEU-120 Alzheimer's disease | phase |  | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F NEU-010 Parkinson's disease | phase |  | 1 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
G RARE-230 enzyme deficiency | phase |  | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H ONC-020 lymphoma | phase |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phases: Pre = preclinical, Ph I – Ph III, Review. Empty: stopped, launched or not yet started.
2 Spending by project
The yearly cost of the phase under way.
A ONC-301 solid tumours | US$m | 180 | 60 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B ONC-210 leukaemia | US$m | 50 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C IMM-220 psoriasis | US$m | 50 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D IMM-110 Crohn's disease | US$m | 245 | 15 | 25 | 25 | 60 | 60 | 60 | 0 | 0 | 0 | 0
E NEU-120 Alzheimer's disease | US$m | 65 | 15 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F NEU-010 Parkinson's disease | US$m | 73 | 8 | 15 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0
G RARE-230 enzyme deficiency | US$m | 50 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H ONC-020 lymphoma | US$m | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 Spending by portfolio
The projects each portfolio funds, added up.
Everything | US$m | 721 | 181 | 200 | 135 | 85 | 60 | 60 | 0 | 0 | 0 | 0
One per mechanism | US$m | 395 | 150 | 160 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Late stage | US$m | 330 | 135 | 135 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Within budget | US$m | 368 | 108 | 125 | 110 | 25 | 0 | 0 | 0 | 0 | 0 | 0
Portfolio in the chart (output) | US$m |  | 150 | 160 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget | US$m |  | 170 | 170 | 170 | 170 | 170 | 0 | 0 | 0 | 0 | 0
4 Over budget
1 = the portfolio spends more than the budget in the year, within the budget horizon.
Everything | 1 / 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
One per mechanism | 1 / 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Late stage | 1 / 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Within budget | 1 / 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 Value in this iteration
Key outputs, recorded by ModelRisk at every sample (VoseOutput). Their statistics appear on the Results sheet.
Output | Unit | Value | 1: Meaning
Everything: NPV | US$m | -587.7966 | 1: The funded projects' NPVs added up.
One per mechanism: NPV | US$m | -348.6836
Late stage: NPV | US$m | -293.0124
Within budget: NPV | US$m | -315.9092
Everything: launches | products | 0
One per mechanism: launches | products | 0
Late stage: launches | products | 0
Within budget: launches | products | 0
Everything: no launch? (1 = yes) | 1 / 0 | 1
One per mechanism: no launch? (1 = yes) | 1 / 0 | 1
Late stage: no launch? (1 = yes) | 1 / 0 | 1
Within budget: no launch? (1 = yes) | 1 / 0 | 1
Everything: over budget? (1 = yes) | 1 / 0 | 1 | 1: In at least one year of the horizon.
One per mechanism: over budget? (1 = yes) | 1 / 0 | 0
Late stage: over budget? (1 = yes) | 1 / 0 | 0
Within budget: over budget? (1 = yes) | 1 / 0 | 0
Project A: NPV | US$m | -156.4939 | 1: If funded.
Project B: NPV | US$m | -45.5062
Project C: NPV | US$m | -45.5062
Project D: NPV | US$m | -173.2474
Project E: NPV | US$m | -55.6712
Project F: NPV | US$m | -58.2379
Project G: NPV | US$m | -45.5062
Project H: NPV | US$m | -7.6277
Project A: launched? (1 = yes) | 1 / 0 | 0
Project B: launched? (1 = yes) | 1 / 0 | 0
Project C: launched? (1 = yes) | 1 / 0 | 0
Project D: launched? (1 = yes) | 1 / 0 | 0
Project E: launched? (1 = yes) | 1 / 0 | 0
Project F: launched? (1 = yes) | 1 / 0 | 0
Project G: launched? (1 = yes) | 1 / 0 | 0
Project H: launched? (1 = yes) | 1 / 0 | 0
Project A: PV of R&D cost | US$m | 156.4939
Project B: PV of R&D cost | US$m | 45.5062
Project C: PV of R&D cost | US$m | 45.5062
Project D: PV of R&D cost | US$m | 173.2474
Project E: PV of R&D cost | US$m | 55.6712
Project F: PV of R&D cost | US$m | 58.2379
Project G: PV of R&D cost | US$m | 45.5062
Project H: PV of R&D cost | US$m | 7.6277
Projects B and H both launched? (1 = yes) | 1 / 0 | 0
Projects C and D both launched? (1 = yes) | 1 / 0 | 0
Projects E and F both launched? (1 = yes) | 1 / 0 | 0
6 Model checks
Should all read OK. A CHECK means an input has been set outside the range the model is built for.
Every stage is one of the four on the list |  | OK
Phase durations are whole years |  | OK
Every launch falls within the years modelled |  | OK
The portfolio in the chart is 1 to 4 |  | OK

## Results
R&D Portfolio: Which Projects to Fund | [6 empty] | ModelRisk example · Pharmaceuticals and biotech · PH-04
RESULTS · Filled in automatically from the last simulation. Run a simulation after changing any input.
◂ Spend
✔ Showing results of the last simulation run in this Excel session. Re-run the simulation after changing any input.
✔ All model checks read OK.
1 Which portfolio? | [5 empty] | Portfolio NPV — cumulative probability
Value (NPV, US$m), launches and budget risk of each candidate portfolio.
Portfolio | Mean NPV | NPV | Launches | No launch | Over budget
|  | 1 in 10 (P10) | expected | chance | chance
Everything (8 projects) | 540.3762 | -483.2221 | 1.587 | 15.01% | 100%
One per mechanism (5 projects) | 538.1978 | -436.6482 | 1.328 | 18.36% | 35.15%
Late stage (4 projects) | 512.6502 | -422.3463 | 1.2464 | 19.97% | 35.15%
Within budget (4 projects) | 481.7328 | -316.4167 | 1.0025 | 27.69% | 2.18%
Over budget: spending above US$170 million in at least one of the next 5 years.
2 The projects | [5 empty] | Spending of the charted portfolio against the budget
Each project as if funded: chance of launch, value and R&D cost (US$m).
Project | Stage | Launch | Mean NPV | R&D cost | Value per
|  | chance |  | PV, mean | US$ of R&D
A ONC-301 solid tumours | Phase III | 53.21% | 408.7961 | 158.605 | 3.5774
B ONC-210 leukaemia | Phase II | 18.81% | 37.5682 | 91.3046 | 1.4115
C IMM-220 psoriasis | Phase II | 18.8% | 21.7561 | 91.2941 | 1.2383
D IMM-110 Crohn's disease | Phase I | 13.08% | 3.3074 | 68.3767 | 1.0484
E NEU-120 Alzheimer's disease | Phase I | 8.16% | 25.5476 | 60.0827 | 1.4252
F NEU-010 Parkinson's disease | Preclinical | 5.06% | 2.8592 | 43.2936 | 1.066
G RARE-230 enzyme deficiency | Phase II | 33.82% | 44.5298 | 111.9482 | 1.3978
H ONC-020 lymphoma | Preclinical | 7.76% | -3.9882 | 48.6988 | 0.9181
Value per US$ of R&D: the expected present value of the launch ÷ the expected R&D cost. Below 1, the project destroys value.
3 Shared mechanisms
Projects that share a mechanism succeed — and fail — together.
Pair | Both launch | Both launch | Ratio
| simulated | if independent
B and H | 2.97% | 1.46% | 2.0347
C and D | 4.97% | 2.459% | 2.0211
E and F | 1.21% | 0.4129% | 2.9305
4 How to read these results
• Funding everything gives the most value on average, about US$540 million, but it needs more than the US$170 million budget in the early years in every future: the Phase III drug and three Phase II projects all spend at once.
• Funding one project per mechanism keeps almost all of that value, about US$538 million. The three projects it drops — D, F and H — are early and worth little on average: about a dollar of value per dollar of R&D. It still breaks the budget about one time in three, when several Phase II trials succeed and their Phase III trials start together.
• The portfolio that stays within the budget (A, E, F and G) gives up about US$56 million of value, and its chance of no launch rises from 18% to 28%, because it leaves out two Phase II projects. The choice is between value and a steady flow of launches on one side and the budget on the other — unless more money is found, for example by partnering a Phase III.
• Projects that share a mechanism succeed and fail together: each pair launches together two to three times as often as if they were independent. Funding both projects of a pair concentrates the risk, which is why funding everything has the worst 1-in-10 value of the four portfolios.
• The Phase III drug, project A, carries every portfolio: most of the value and the reason the four NPV curves look alike. The portfolios differ in what happens if A fails — and in what they spend while waiting to find out.
Chart data
Statistics of the last simulation behind the charts and the ranking above. Grouped: click + in the left margin to show them.
Cumulative probability | Exceedance | PNPV_1 | PNPV_2 | PNPV_3 | PNPV_4
1% | 99% | -757.0519 | -607.3513 | -551.6801 | -510.7612
3% | 97% | -653.3148 | -484.0922 | -425.928 | -411.2163
5% | 95% | -590.1096 | -478.0175 | -422.3463 | -398.2146
7% | 93% | -550.1882 | -466.2598 | -422.3463 | -382.8752
9% | 91% | -507.5748 | -436.6482 | -422.3463 | -353.2636
11% | 89% | -470.2204 | -360.7416 | -313.4654 | -315.9092
13% | 87% | -432.612 | -348.6836 | -293.0124 | -315.9092
15% | 85% | -404.2445 | -348.6836 | -293.0124 | -278.3008
17% | 83% | -378.241 | -307.3144 | -293.0124 | -274.5399
19% | 81% | -322.8651 | -307.3144 | -293.0124 | -268.8807
21% | 79% | -261.726 | -231.1005 | -268.6385 | -265.299
23% | 77% | -214.4687 | -171.9719 | -173.9875 | -240.5133
25% | 75% | -163.6479 | -123.546 | -122.9528 | -227.5115
27% | 73% | -113.8708 | -75.895 | -76.7892 | -223.9298
29% | 71% | -66.099 | -35.4334 | -32.8299 | -159.6984
31% | 69% | -20.1257 | 3.2915 | 8.3436 | -93.1648
33% | 67% | 24.107 | 45.4958 | 45.4725 | -42.0086
35% | 65% | 73.5588 | 88.5985 | 85.4864 | 2.8829
37% | 63% | 123.8538 | 128.4047 | 127.6694 | 50.2506
39% | 61% | 170.4823 | 177.6164 | 172.2109 | 96.5177
41% | 59% | 215.0724 | 227.6854 | 213.7718 | 143.8214
43% | 57% | 254.4817 | 273.2313 | 263.2797 | 195.7485
45% | 55% | 301.4568 | 320.6966 | 304.6214 | 247.575
47% | 53% | 349.6449 | 365.2998 | 348.6523 | 301.0573
49% | 51% | 391.9824 | 402.8847 | 391.5137 | 350.1915
51% | 49% | 438.1704 | 442.8464 | 433.7938 | 395.4083
53% | 47% | 490.2942 | 488.956 | 475.7451 | 436.4066
55% | 45% | 537.3401 | 539.0211 | 519.2591 | 481.4613
57% | 43% | 578.9401 | 586.6209 | 570.1702 | 527.6188
59% | 41% | 631.0467 | 633.3831 | 616.989 | 575.4507
61% | 39% | 675.6971 | 682.9171 | 660.1922 | 621.7714
63% | 37% | 722.0607 | 723.7495 | 711.7757 | 664.0287
65% | 35% | 776.2729 | 767.4231 | 754.3037 | 706.1032
67% | 33% | 837.0899 | 813.988 | 797.8129 | 746.9369
69% | 31% | 888.6605 | 865.9945 | 840.8425 | 796.4494
71% | 29% | 942.1523 | 916.461 | 888.6023 | 838.9823
73% | 27% | 998.5226 | 968.7121 | 938.9433 | 885.4496
75% | 25% | 1059.4839 | 1028.7416 | 984.9685 | 933.5379
77% | 23% | 1135.3304 | 1089.3655 | 1044.949 | 984.9474
79% | 21% | 1199.141 | 1150.822 | 1103.7649 | 1047.751
81% | 19% | 1274.7314 | 1219.0591 | 1166.9874 | 1112.2292
83% | 17% | 1355.9483 | 1297.4024 | 1233.361 | 1182.0355
85% | 15% | 1451.1737 | 1375.2824 | 1302.0626 | 1257.388
87% | 13% | 1559.4365 | 1471.9883 | 1393.1434 | 1341.2022
89% | 11% | 1668.5716 | 1567.6167 | 1487.413 | 1448.2376
91% | 9% | 1798.8293 | 1693.4104 | 1594.4269 | 1557.9455
93% | 7% | 1964.2949 | 1838.697 | 1721.4689 | 1736.8858
95% | 5% | 2171.0066 | 2028.5514 | 1896.8574 | 1942.3435
97% | 3% | 2511.4333 | 2324.4063 | 2166.184 | 2198.8726
99% | 1% | 3153.6613 | 2994.0942 | 2693.3318 | 2818.0048
Period | 10th percentile | Median | 90th percentile | Mean | Budget
1 | 150 | 150 | 150 | 150 | 170
2 | 135 | 160 | 160 | 151.1796 | 170
3 | 85 | 145 | 205 | 148.4292 | 170
4 | 5 | 65 | 180 | 84.773 | 170
5 | 0 | 60 | 180 | 81.8261 | 170
6 | 0 | 5 | 60 | 13.4352 | #N/A
7 | 0 | 0 | 0 | 0.44852 | #N/A
8 | 0 | 0 | 0 | 0 | #N/A
9 | 0 | 0 | 0 | 0 | #N/A
10 | 0 | 0 | 0 | 0 | #N/A

## ModelRiskDSN (hidden)
DSN Files Count: | 0

## ModelRiskCharts (hidden)
0
0
0
0
0
2000
0
0
0
0
669
0
0
0
0
0
0
0
0
1331
145
301
289
0
568
201
0
385
34
77
374
0
803
0
253
352
0
205
0
13
374
0
803
0
605
0
0
205
0
13
1423
259
0
0
0
0
0
131
144
43
1832
0
0
0
0
0
0
0
0
168
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
0
0
0
0
0
2000
0
0
0
0
380
479
490
317
186
86
41
18
1
2
441
495
472
304
171
69
33
11
2
2
439
386
402
344
214
124
55
27
3
6
606
447
500
254
119
52
11
8
2
1
311
708
648
0
235
80
0
15
2
1
378
859
0
574
0
164
0
24
0
1
407
0
909
0
530
0
0
139
0
15
565
0
938
0
453
0
0
37
0
7
1689
0
0
0
0
0
0
0
0
311
1622
0
0
0
0
0
0
0
0
378
1593
0
0
0
0
0
0
0
0
407
1435
0
0
0
0
0
0
0
0
565
0
0
0
0
0
2000
0
0
0
0
1303
0
0
0
0
0
0
0
0
697
1303
0
0
0
0
0
0
0
0
697
1959
0
0
0
0
0
0
0
0
41
973
315
371
186
92
39
16
5
1
2
1638
48
100
84
49
32
20
17
6
6
1655
114
122
58
28
16
4
0
1
2
1742
85
84
41
25
12
5
4
1
1
1856
46
47
30
9
8
2
0
1
1
1891
24
31
21
18
4
5
3
2
1
332
1042
184
209
130
58
24
12
2
7
1857
29
33
46
16
3
8
4
3
1
951
0
0
0
0
0
0
0
0
1049
1635
0
0
0
0
0
0
0
0
365
1639
0
0
0
0
0
0
0
0
361
1732
0
0
0
0
0
0
0
0
268
1846
0
0
0
0
0
0
0
0
154
1891
0
0
0
0
0
0
0
0
109
1329
0
0
0
0
0
0
0
0
671
1854
0
0
0
0
0
0
0
0
146
836
0
0
0
0
0
0
0
0
1164
1329
0
0
0
0
0
0
0
0
671
1312
0
0
0
0
0
0
0
0
688
714
0
817
0
0
0
0
0
0
469
669
0
1013
0
0
0
0
0
0
318
1171
0
0
617
0
0
0
0
0
212
997
0
0
0
0
0
0
0
0
1003
1147
0
0
560
0
0
0
0
0
293
1949
0
0
0
0
0
0
0
0
51
1898
0
0
0
0
0
0
0
0
102
1972
0
0
0
0
0
0
0
0
28