## _MC_Store (hidden)
{"_v":2,"trees":{"MC_Tree_1":"{\r\n \"RootId\": \"D_root\",\r\n \"Nodes\": {\r\n \"D_root\": {\r\n \"type\": \"decision\",\r\n \"id\": \"D_root\",\r\n \"name\": \"Energy Project Selection\",\r\n \"options\": [\r\n {\r\n \"name\": \"Solar Farm (50 MW)\",\r\n \"childId\": \"C_solar_permit\",\r\n \"value\": -45000000\r\n },\r\n {\r\n \"name\": \"Wind Farm (30 MW)\",\r\n \"childId\": \"C_wind_permit\",\r\n \"value\": -52000000\r\n },\r\n {\r\n \"name\": \"Hybrid Solar+Storage\",\r\n \"childId\": \"C_hybrid_permit\",\r\n \"value\": -62000000\r\n },\r\n {\r\n \"name\": \"No Project\",\r\n \"childId\": \"T_none\"\r\n }\r\n ]\r\n },\r\n \"C_solar_permit\": {\r\n \"type\": \"chance\",\r\n \"id\": \"C_solar_permit\",\r\n \"name\": \"Permitting \u0026 Grid Connect\",\r\n \"branches\": [\r\n {\r\n \"name\": \"On Schedule\",\r\n \"probability\": 0.55,\r\n \"childId\": \"C_solar_policy\"\r\n },\r\n {\r\n \"name\": \"Delayed 12 Months\",\r\n \"probability\": 0.3,\r\n \"childId\": \"C_solar_policy_delay\",\r\n \"value\": -3000000\r\n },\r\n {\r\n \"name\": \"Permit Blocked\",\r\n \"probability\": 0.15,\r\n \"childId\": \"T_solar_blocked\",\r\n \"value\": 5000000\r\n }\r\n ]\r\n },\r\n \"C_solar_policy\": {\r\n \"type\": \"chance\",\r\n \"id\": \"C_solar_policy\",\r\n \"name\": \"Policy \u0026 Subsidy Environment\",\r\n \"branches\": [\r\n {\r\n \"name\": \"Favorable (ITC Extended)\",\r\n \"probability\": 0.4,\r\n \"childId\": \"C_solar_gen_fav\"\r\n },\r\n {\r\n \"name\": \"Neutral\",\r\n \"probability\": 0.4,\r\n \"childId\": \"C_solar_gen_neut\"\r\n },\r\n {\r\n \"name\": \"Unfavorable (Subsidy Cut)\",\r\n \"probability\": 0.2,\r\n \"childId\": \"C_solar_gen_unfav\"\r\n }\r\n ]\r\n },\r\n \"C_solar_gen_fav\": {\r\n \"type\": \"chance\",\r\n \"id\": \"C_solar_gen_fav\",\r\n \"name\": \"Solar Generation (Favorable)\",\r\n \"branches\": [\r\n {\r\n \"name\": \"Above Average Sun\",\r\n \"probability\": 0.35,\r\n \"childId\": \"T_solar_fav_high\",\r\n \"value\": 85000000\r\n },\r\n {\r\n \"name\": \"Average Sun\",\r\n \"probability\": 0.5,\r\n \"childId\": \"T_solar_fav_avg\",\r\n \"value\": 68000000\r\n },\r\n {\r\n \"name\": \"Below Average\",\r\n \"probability\": 0.15,\r\n \"childId\": \"T_solar_fav_low\",\r\n \"value\": 52000000\r\n }\r\n ]\r\n },\r\n \"T_solar_fav_high\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_solar_fav_high\",\r\n \"name\": \"Solar+Favorable+High\",\r\n \"value\": 0\r\n },\r\n \"T_solar_fav_avg\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_solar_fav_avg\",\r\n \"name\": \"Solar+Favorable+Avg\",\r\n \"value\": 0\r\n },\r\n \"T_solar_fav_low\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_solar_fav_low\",\r\n \"name\": \"Solar+Favorable+Low\",\r\n \"value\": 0\r\n },\r\n \"C_solar_gen_neut\": {\r\n \"type\": \"chance\",\r\n \"id\": \"C_solar_gen_neut\",\r\n \"name\": \"Solar Generation (Neutral)\",\r\n \"branches\": [\r\n {\r\n \"name\": \"Above Average Sun\",\r\n \"probability\": 0.3,\r\n \"childId\": \"T_solar_neut_high\",\r\n \"value\": 72000000\r\n },\r\n {\r\n \"name\": \"Average Sun\",\r\n \"probability\": 0.5,\r\n \"childId\": \"T_solar_neut_avg\",\r\n \"value\": 58000000\r\n },\r\n {\r\n \"name\": \"Below Average\",\r\n \"probability\": 0.2,\r\n \"childId\": \"T_solar_neut_low\",\r\n \"value\": 42000000\r\n }\r\n ]\r\n },\r\n \"T_solar_neut_high\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_solar_neut_high\",\r\n \"name\": \"Solar+Neutral+High\",\r\n \"value\": 0\r\n },\r\n \"T_solar_neut_avg\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_solar_neut_avg\",\r\n \"name\": \"Solar+Neutral+Avg\",\r\n \"value\": 0\r\n },\r\n \"T_solar_neut_low\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_solar_neut_low\",\r\n \"name\": \"Solar+Neutral+Low\",\r\n \"value\": 0\r\n },\r\n \"C_solar_gen_unfav\": {\r\n \"type\": \"chance\",\r\n \"id\": \"C_solar_gen_unfav\",\r\n \"name\": \"Solar Generation (Unfavorable)\",\r\n \"branches\": [\r\n {\r\n \"name\": \"Above Average Sun\",\r\n \"probability\": 0.3,\r\n \"childId\": \"T_solar_unfav_high\",\r\n \"value\": 55000000\r\n },\r\n {\r\n \"name\": \"Average Sun\",\r\n \"probability\": 0.5,\r\n \"childId\": \"T_solar_unfav_avg\",\r\n \"value\": 40000000\r\n },\r\n {\r\n \"name\": \"Below Average\",\r\n \"probability\": 0.2,\r\n \"childId\": \"T_solar_unfav_low\",\r\n \"value\": 28000000\r\n }\r\n ]\r\n },\r\n \"T_solar_unfav_high\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_solar_unfav_high\",\r\n \"name\": \"Solar+Unfav+High\",\r\n \"value\": 0\r\n },\r\n \"T_solar_unfav_avg\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_solar_unfav_avg\",\r\n \"name\": \"Solar+Unfav+Avg\",\r\n \"value\": 0\r\n },\r\n \"T_solar_unfav_low\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_solar_unfav_low\",\r\n \"name\": \"Solar+Unfav+Low\",\r\n \"value\": 0\r\n },\r\n \"C_solar_policy_delay\": {\r\n \"type\": \"chance\",\r\n \"id\": \"C_solar_policy_delay\",\r\n \"name\": \"Policy (Delayed Project)\",\r\n \"branches\": [\r\n {\r\n \"name\": \"Favorable\",\r\n \"probability\": 0.35,\r\n \"childId\": \"T_solar_delay_fav\",\r\n \"value\": 65000000\r\n },\r\n {\r\n \"name\": \"Neutral\",\r\n \"probability\": 0.4,\r\n \"childId\": \"T_solar_delay_neut\",\r\n \"value\": 50000000\r\n },\r\n {\r\n \"name\": \"Unfavorable\",\r\n \"probability\": 0.25,\r\n \"childId\": \"T_solar_delay_unfav\",\r\n \"value\": 35000000\r\n }\r\n ]\r\n },\r\n \"T_solar_delay_fav\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_solar_delay_fav\",\r\n \"name\": \"Delayed+Favorable\",\r\n \"value\": 0\r\n },\r\n \"T_solar_delay_neut\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_solar_delay_neut\",\r\n \"name\": \"Delayed+Neutral\",\r\n \"value\": 0\r\n },\r\n \"T_solar_delay_unfav\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_solar_delay_unfav\",\r\n \"name\": \"Delayed+Unfavorable\",\r\n \"value\": 0\r\n },\r\n \"T_solar_blocked\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_solar_blocked\",\r\n \"name\": \"Solar Permit Blocked\",\r\n \"value\": 0\r\n },\r\n \"C_wind_permit\": {\r\n \"type\": \"chance\",\r\n \"id\": \"C_wind_permit\",\r\n \"name\": \"Permitting \u0026 Environmental\",\r\n \"branches\": [\r\n {\r\n \"name\": \"Approved\",\r\n \"probability\": 0.45,\r\n \"childId\": \"C_wind_resource\"\r\n },\r\n {\r\n \"name\": \"Delayed (Environmental)\",\r\n \"probability\": 0.35,\r\n \"childId\": \"C_wind_resource_delay\",\r\n \"value\": -5000000\r\n },\r\n {\r\n \"name\": \"Blocked\",\r\n \"probability\": 0.2,\r\n \"childId\": \"T_wind_blocked\",\r\n \"value\": 4000000\r\n }\r\n ]\r\n },\r\n \"C_wind_resource\": {\r\n \"type\": \"chance\",\r\n \"id\": \"C_wind_resource\",\r\n \"name\": \"Wind Resource Quality\",\r\n \"branches\": [\r\n {\r\n \"name\": \"Excellent Wind\",\r\n \"probability\": 0.25,\r\n \"childId\": \"T_wind_excellent\",\r\n \"value\": 95000000\r\n },\r\n {\r\n \"name\": \"Good Wind\",\r\n \"probability\": 0.5,\r\n \"childId\": \"T_wind_good\",\r\n \"value\": 70000000\r\n },\r\n {\r\n \"name\": \"Below Average Wind\",\r\n \"probability\": 0.25,\r\n \"childId\": \"T_wind_poor\",\r\n \"value\": 45000000\r\n }\r\n ]\r\n },\r\n \"T_wind_excellent\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_wind_excellent\",\r\n \"name\": \"Wind: Excellent\",\r\n \"value\": 0\r\n },\r\n \"T_wind_good\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_wind_good\",\r\n \"name\": \"Wind: Good\",\r\n \"value\": 0\r\n },\r\n \"T_wind_poor\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_wind_poor\",\r\n \"name\": \"Wind: Below Average\",\r\n \"value\": 0\r\n },\r\n \"C_wind_resource_delay\": {\r\n \"type\": \"chance\",\r\n \"id\": \"C_wind_resource_delay\",\r\n \"name\": \"Wind Resource (Delayed)\",\r\n \"branches\": [\r\n {\r\n \"name\": \"Excellent Wind\",\r\n \"probability\": 0.25,\r\n \"childId\": \"T_wind_delay_exc\",\r\n \"value\": 88000000\r\n },\r\n {\r\n \"name\": \"Good Wind\",\r\n \"probability\": 0.5,\r\n \"childId\": \"T_wind_delay_good\",\r\n \"value\": 63000000\r\n },\r\n {\r\n \"name\": \"Below Average\",\r\n \"probability\": 0.25,\r\n \"childId\": \"T_wind_delay_poor\",\r\n \"value\": 38000000\r\n }\r\n ]\r\n },\r\n \"T_wind_delay_exc\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_wind_delay_exc\",\r\n \"name\": \"Delayed Wind: Excellent\",\r\n \"value\": 0\r\n },\r\n \"T_wind_delay_good\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_wind_delay_good\",\r\n \"name\": \"Delayed Wind: Good\",\r\n \"value\": 0\r\n },\r\n \"T_wind_delay_poor\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_wind_delay_poor\",\r\n \"name\": \"Delayed Wind: Poor\",\r\n \"value\": 0\r\n },\r\n \"T_wind_blocked\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_wind_blocked\",\r\n \"name\": \"Wind Permit Blocked\",\r\n \"value\": 0\r\n },\r\n \"C_hybrid_permit\": {\r\n \"type\": \"chance\",\r\n \"id\": \"C_hybrid_permit\",\r\n \"name\": \"Permitting (Hybrid)\",\r\n \"branches\": [\r\n {\r\n \"name\": \"Approved\",\r\n \"probability\": 0.5,\r\n \"childId\": \"C_hybrid_market\"\r\n },\r\n {\r\n \"name\": \"Delayed\",\r\n \"probability\": 0.35,\r\n \"childId\": \"C_hybrid_market_delay\",\r\n \"value\": -4000000\r\n },\r\n {\r\n \"name\": \"Blocked\",\r\n \"probability\": 0.15,\r\n \"childId\": \"T_hybrid_blocked\",\r\n \"value\": 6000000\r\n }\r\n ]\r\n },\r\n \"C_hybrid_market\": {\r\n \"type\": \"chance\",\r\n \"id\": \"C_hybrid_market\",\r\n \"name\": \"Energy Market \u0026 Storage Value\",\r\n \"branches\": [\r\n {\r\n \"name\": \"High Storage Premium\",\r\n \"probability\": 0.3,\r\n \"childId\": \"T_hybrid_high\",\r\n \"value\": 110000000\r\n },\r\n {\r\n \"name\": \"Moderate Premium\",\r\n \"probability\": 0.45,\r\n \"childId\": \"T_hybrid_mod\",\r\n \"value\": 80000000\r\n },\r\n {\r\n \"name\": \"Low Premium\",\r\n \"probability\": 0.25,\r\n \"childId\": \"T_hybrid_low\",\r\n \"value\": 55000000\r\n }\r\n ]\r\n },\r\n \"T_hybrid_high\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_hybrid_high\",\r\n \"name\": \"Hybrid: High Premium\",\r\n \"value\": 0\r\n },\r\n \"T_hybrid_mod\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_hybrid_mod\",\r\n \"name\": \"Hybrid: Moderate\",\r\n \"value\": 0\r\n },\r\n \"T_hybrid_low\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_hybrid_low\",\r\n \"name\": \"Hybrid: Low Premium\",\r\n \"value\": 0\r\n },\r\n \"C_hybrid_market_delay\": {\r\n \"type\": \"chance\",\r\n \"id\": \"C_hybrid_market_delay\",\r\n \"name\": \"Energy Market (Delayed)\",\r\n \"branches\": [\r\n {\r\n \"name\": \"High Premium\",\r\n \"probability\": 0.3,\r\n \"childId\": \"T_hybrid_delay_high\",\r\n \"value\": 100000000\r\n },\r\n {\r\n \"name\": \"Moderate Premium\",\r\n \"probability\": 0.45,\r\n \"childId\": \"T_hybrid_delay_mod\",\r\n \"value\": 72000000\r\n },\r\n {\r\n \"name\": \"Low Premium\",\r\n \"probability\": 0.25,\r\n \"childId\": \"T_hybrid_delay_low\",\r\n \"value\": 48000000\r\n }\r\n ]\r\n },\r\n \"T_hybrid_delay_high\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_hybrid_delay_high\",\r\n \"name\": \"Delayed Hybrid: High\",\r\n \"value\": 0\r\n },\r\n \"T_hybrid_delay_mod\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_hybrid_delay_mod\",\r\n \"name\": \"Delayed Hybrid: Moderate\",\r\n \"value\": 0\r\n },\r\n \"T_hybrid_delay_low\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_hybrid_delay_low\",\r\n \"name\": \"Delayed Hybrid: Low\",\r\n \"value\": 0\r\n },\r\n \"T_hybrid_blocked\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_hybrid_blocked\",\r\n \"name\": \"Hybrid Permit Blocked\",\r\n \"value\": 0\r\n },\r\n \"T_none\": {\r\n \"type\": \"terminal\",\r\n \"id\": \"T_none\",\r\n \"name\": \"No Project\",\r\n \"value\": 0\r\n }\r\n },\r\n \"Settings\": {\r\n \"ModelName\": \"Renewable Energy Project\",\r\n \"CalculationMethod\": 0,\r\n \"Maximize\": true,\r\n \"UtilityConfig\": null,\r\n \"Display\": {\r\n \"DecimalPlaces\": 0,\r\n \"ShowExpectedValues\": true,\r\n \"ShowOptimalLabels\": true,\r\n \"ShowRollbackValues\": true,\r\n \"CalculatedValueFormat\": \"\\\"$\\\"#,##0\",\r\n \"CalculatedProbabilityFormat\": \"0.0%\",\r\n \"InputValueFormat\": \"\\\"$\\\"#,##0\",\r\n \"InputProbabilityFormat\": \"0.0%\",\r\n \"CalculatedValuesLabel\": \"\",\r\n \"TreeStartRow\": 20\r\n },\r\n \"ChanceProbabilities\": 1,\r\n \"ProbabilityTolerance\": 0.001,\r\n \"Simulation\": {\r\n \"CalculationMode\": 0,\r\n \"DecisionMode\": 0\r\n }\r\n },\r\n \"NodeMetadata\": {},\r\n \"UserFormulas\": {\r\n \"MC_BV_D_root_C_solar_permit\": \"=-SolarFarm50MwCost\",\r\n \"MC_BV_D_root_C_wind_permit\": \"=-WindFarm30MwCost\",\r\n \"MC_BV_D_root_C_hybrid_permit\": \"=-HybridSolarstorageCost\"\r\n }\r\n}"}}

## _MC_Calc (hidden)
0.3 | 110000000 | 0.45 | 80000000 | 0.25 | 55000000 | 0.3 | 100000000 | 0.45 | 72000000 | 0.25 | 48000000 | 0.5 | 0 | 0.35 | -4000000 | 0.15 | 6000000 | 0.35 | 85000000 | 0.5 | 68000000 | 0.15 | 52000000 | 0.3 | 72000000 | 0.5 | 58000000 | 0.2 | 42000000 | 0.3 | 55000000 | 0.5 | 40000000 | 0.2 | 28000000 | 0.55 | 0 | 0.3 | -3000000 | 0.15 | 5000000 | 0.4 | 0 | 0.4 | 0 | 0.2 | 0 | 0.35 | 65000000 | 0.4 | 50000000 | 0.25 | 35000000 | 0.45 | 0 | 0.35 | -5000000 | 0.2 | 4000000 | 0.25 | 95000000 | 0.5 | 70000000 | 0.25 | 45000000 | 0.25 | 88000000 | 0.5 | 63000000 | 0.25 | 38000000 | -45000000 | -52000000 | -62000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Problem
Renewable Energy Project Selection
ModelChoice Example Model
Background
An independent power producer (IPP) is evaluating three renewable energy
projects for a site with both good solar irradiance and wind resources.
Each technology carries different permitting risks, resource uncertainties,
and sensitivity to government policy changes.
Option 1: Solar Farm - 50 MW ($45M)
Proven technology, fastest permitting, but revenue depends on solar irradiance
and government tax credit (ITC) extension.
Option 2: Wind Farm - 30 MW ($52M)
Higher capacity factor potential but more permitting risk (environmental
reviews, bird/bat studies). Revenue highly dependent on wind quality.
Option 3: Hybrid Solar + Battery Storage ($62M)
Highest cost but earns a storage premium for dispatchable power.
Battery storage value depends on grid congestion and peak demand pricing.
Decision Objective
Maximize expected 20-year NPV. This model shows how technology choice
interacts with regulatory, resource, and market risk in energy investments.
Key Assumptions
Parameter | Value | Notes
Solar Farm Cost | 45000000 | 50 MW, $900/kW installed
Wind Farm Cost | 52000000 | 30 MW, $1,733/kW installed
Hybrid Cost | 62000000 | Solar + 4-hour battery storage
Project Life | 20 years | NPV of all revenue streams
Solar Permit Approval | 55% | On schedule; 30% delayed, 15% blocked
Wind Permit Approval | 45% | Lower due to environmental concerns
Permit Delay Cost | $3-5M | Carrying costs, redesign
Storage Premium Potential | High: $110M NPV | Peak shaving + ancillary services
Wind Revenue Range | $45-95M NPV | Widest range due to resource variability
Suggested Analyses
▶ Strategy Table - Compare solar, wind, and hybrid with risk-return frontier
▶ Sensitivity Analysis - How do permit odds and energy prices affect project value?
▶ Risk Profile - Which technology has the best risk-adjusted return?

## MC_Tree_1
Renewable Energy Project — Control Panel
Adjust parameters below to update the decision tree instantly
Parameter | Value | Units | Notes
Solar Farm (50 MW) | 45000000 | $ | Investment for Permitting & Grid Connect path
Wind Farm (30 MW) | 52000000 | $ | Investment for Permitting & Environmental path
Hybrid Solar+Storage | 62000000 | $ | Investment for Permitting (Hybrid) path
|  |  |  | 35% | 7.7%
|  |  |  | 85000000 | 40000000
|  |  | 40% | Solar Generation (Favorable)
|  |  | 0 | 26550000
|  |  |  | 50% | 11%
|  |  |  | 68000000 | 23000000
|  |  |  | 15% | 3.3%
|  |  |  | 52000000 | 7000000
|  | 55% | Policy & Subsidy Environment
|  | 0 | 15640000
|  |  |  | 30% | 6.6%
|  |  |  | 72000000 | 27000000
|  |  | 40% | Solar Generation (Neutral)
|  |  | 0 | 14000000
|  |  |  | 50% | 11%
|  |  |  | 58000000 | 13000000
|  |  |  | 20% | 4.4%
|  |  |  | 42000000 | -3000000
|  |  |  | 30% | 3.3%
|  |  |  | 55000000 | 10000000
|  |  | 20% | Solar Generation (Unfavorable)
|  |  | 0 | -2900000
|  |  |  | 50% | 5.5%
|  |  |  | 40000000 | -5000000
|  |  |  | 20% | 2.2%
|  |  |  | 28000000 | -17000000
Permitting & Grid Connect
| -45000000 | 3652000
|  |  | 35% | 10.5%
|  |  | 65000000 | 17000000
|  | 30% | Policy (Delayed Project)
|  | -3000000 | 3500000
|  |  | 40% | 12%
|  |  | 50000000 | 2000000
|  |  | 25% | 7.5%
|  |  | 35000000 | -13000000
|  | 15% | 15%
|  | 5000000 | -40000000
Energy Project Selection
4915000
|  |  | 25% | 11.25%
|  |  | 95000000 | 43000000
|  | 45% | Wind Resource Quality
|  | 0 | 18000000
|  |  | 50% | 22.5%
|  |  | 70000000 | 18000000
|  |  | 25% | 11.25%
|  |  | 45000000 | -7000000
Permitting & Environmental
| -52000000 | 600000
|  |  | 25% | 8.75%
|  |  | 88000000 | 31000000
|  | 35% | Wind Resource (Delayed)
|  | -5000000 | 6000000
|  |  | 50% | 17.5%
|  |  | 63000000 | 6000000
|  |  | 25% | 8.75%
|  |  | 38000000 | -19000000
|  | 20% | 20%
|  | 4000000 | -48000000
|  |  | 30% | 15%
|  |  | 110000000 | 48000000
|  | 50% | Energy Market & Storage Value
|  | 0 | 20750000
|  |  | 45% | 22.5%
|  |  | 80000000 | 18000000
|  |  | 25% | 12.5%
|  |  | 55000000 | -7000000
| optimal | Permitting (Hybrid)
| -62000000 | 4915000
|  |  | 30% | 10.5%
|  |  | 100000000 | 34000000
|  | 35% | Energy Market (Delayed)
|  | -4000000 | 8400000
|  |  | 45% | 15.75%
|  |  | 72000000 | 6000000
|  |  | 25% | 8.75%
|  |  | 48000000 | -18000000
|  | 15% | 15%
|  | 6000000 | -56000000
100%
| 0 | 0
Renewable Energy Project
Solar Farm (50 MW)
Wind Farm (30 MW)
Hybrid Solar+Storage
No Project
On Schedule
Delayed 12 Months
Permit Blocked
Favorable (ITC Extended)
Neutral
Unfavorable (Subsidy Cut)
Above Average Sun
Average Sun
Below Average
Above Average Sun
Average Sun
Below Average
Above Average Sun
Average Sun
Below Average
Favorable
Neutral
Unfavorable
Approved
Delayed (Environmental)
Blocked
Excellent Wind
Good Wind
Below Average Wind
Excellent Wind
Good Wind
Below Average
Approved
Delayed
Blocked
High Storage Premium
Moderate Premium
Low Premium
High Premium
Moderate Premium
Low Premium