## Read me
Four Risk Managers and a Mustard Factory
A Vose Software workbook · runs in Excel with ModelRisk · a plain-Excel version is included for readers without it
What this is
One project, five risk managers, identical luck. A family condiment firm builds a new €10m mustard filling line: 12 months, planned finish 30 September, and it must be commissioned by 31 October to catch the Christmas season. The same risks hit the same project in five parallel universes. The only thing that differs is how each risk manager works:
Brian keeps a heat-map register and manages the top ten. Sandra adds 10% and six weeks and calls it contingency. Quentin models the risks quantitatively and spends where the model says it pays: an early acceptance test at the supplier's works, re-sequenced commissioning, fire-only insurance and a P80 budget. Petra transfers risk: a full insurance package with delay-in-start-up cover. Trevor keeps no register at all.
Every universe reads the same random draw in every iteration (common random numbers), so any difference in outcome is caused by method, never by luck.
How to run it (ModelRisk)
1. Check that 'Replay the story year' on the Inputs sheet is 0. 2. In the ModelRisk ribbon, open Simulation Settings: Samples 10,000, Simulations 1. 3. Click Start. The 'Simulation results' table on the Dashboard fills in: mean, P50, P80 and P95 cost for each risk manager, the chance each one misses the Christmas season, and how often Brian ends up cheaper than Quentin. 4. Open the Results Viewer on the five totals to see the whole distributions side by side. The story is in the tails.
Tip: pressing F9 without a simulation shows one random year. Set 'Replay the story year' to 1 to see the year told in the article, where the filler fails acceptance.
The sheets
Inputs: every assumption, in blue. Change any of them and re-run.
Dashboard: this year's five totals, the simulation results, and the reference values from Vose's Python model.
Model: the risk register (39 small 'green' snags, 12 months of scope creep, the filler, the fire) with a live draw and the story-year value for every item, then the five universes calculated side by side.
Without ModelRisk: the same model in plain Excel (RAND). Press F9 for one random year at a time. ModelRisk runs ten thousand and gives you the distributions.
The three behavioural assumptions
Sandra's budget carries a +5% 'Parkinson' factor: money that is available tends to get spent. Trevor, with nobody asking whether each change is worth it, gets twice the scope creep, and problems found late cost him 30% more to fix. Everything else in the model is a physical or contractual mechanism. All three are on the Inputs sheet. Set Sandra's Parkinson factor to 0 and she becomes Brian with €1m of false comfort. Set both of Trevor's multipliers to 1 and he becomes Brian without the paperwork.
Don't have ModelRisk? Free 15-day trial: https://www.vosesoftware.com/Risk-In-Excel/Download-ModelRisk-trial.php

## Dashboard
Four Risk Managers and a Mustard Factory: Dashboard
Light-blue cells are ModelRisk results: run 1 simulation × 10,000 samples (see Read me). Blue numbers in the reference table are the Python reference model's.
This year (changes with every F9; set the story switch to 1 for the article's year)
| Brian | Sandra | Quentin | Petra | Trevor
Total cost
Over (+) or under (−) budget
Delay (months)
Christmas season missed (1 = yes)
Story switch is currently
Simulation results (after one run of 10,000 samples)
| Brian | Sandra | Quentin | Petra | Trevor
Mean cost
P50 cost
P80 cost
P95 cost
Chance of missing the Christmas season
How often Brian ends up cheaper than Quentin
Value of Quentin's acceptance test (expected saving, before its price)
What you should see (Vose Python reference model, 10,000 replays, seed 20260921)
| Brian | Sandra | Quentin | Petra | Trevor
Mean cost | 11.1967 | 11.6967 | 10.8163 | 11.8063 | 11.4747
P50 cost | 10.5433 | 11.0433 | 10.7525 | 11.2417 | 10.7376
P80 cost | 10.7664 | 11.2664 | 10.9108 | 11.4285 | 11.0509
P95 cost | 14.23 | 14.73 | 11.3126 | 14.8509 | 14.9276
Chance of missing the Christmas season | 18.45% | 18.45% | 0.22% | 18.45% | 18.45%
How often Brian ends up cheaper than Quentin | 80.8%
Value of Quentin's acceptance test | 0.4621 | 3.85
The story year (iteration 734): total cost | 14.0573 | 14.5573 | 11.3102 | 14.7573 | 14.6922
Reading it: in the quiet majority of years Quentin's tests and premiums buy nothing you can see, and Brian is cheaper. Quentin wins on the average and decisively in the bad years (P95). That is why Brian still has a job, and why he shouldn't.
No ModelRisk? The 'Without ModelRisk' sheet runs one random year per F9. Free 15-day trial: https://www.vosesoftware.com/Risk-In-Excel/Download-ModelRisk-trial.php

## Inputs
Inputs
Blue cells are assumptions. Money in € millions, time in months.
Replay the story year (1 = yes, 0 = random years) | 0 | 1 replaces every draw with iteration 734 of the reference model: the filler fails, snags come in around P80, no fire.
Base budget | 10
Planned finish (month of the year, 9 = end September) | 9
Season gate (month, 10 = commissioned by end October) | 10 | Miss it and the Christmas season is lost.
Cost of each month of delay | 0.12 | Prelims, standing army.
Lost Christmas contribution if the gate is missed | 1.5
R1 snag swarm: chance each of the 39 small 'green' snags bites | 50% | Register rows 23–61, each individually trivial.
R1: mean cost of a snag | 0.015 | Lognormal
R1: standard deviation of a snag's cost | 0.012
R1: schedule friction if an average number of snags bite (months, mean) | 0.4 | Lognormal, scaled by how many snags actually bite
R1: schedule friction, standard deviation (months) | 0.25
R2: chance the bespoke filler fails acceptance | 15%
R2: rectification cost if it fails on site, mean | 1.5 | Lognormal
R2: rectification cost on site, standard deviation | 0.4
R2: rectification delay on site, mean (months) | 4 | Lognormal
R2: rectification delay on site, standard deviation (months) | 1
R2: cost of the fix if found at the supplier's works (share of the site cost) | 30% | Quentin's early acceptance test
R2: delay if found at the supplier's works (months) | 0.5
R4: chance of a fire during hot works | 1%
R4: fire loss, mean | 8 | Lognormal
R4: fire loss, standard deviation | 2
R5: chance of a scope-creep nibble in each of the 12 months | 50% | 'One nozzle at a time'
R5: smallest nibble | 0.01 | Uniform
R5: largest nibble | 0.05
Quentin: early acceptance test at the supplier's works | 0.12
Quentin: fire-only insurance premium | 0.09 | Pays fire loss above the deductible
Quentin: fire-only deductible | 0.25
Petra: full insurance package premium (incl. delay in start-up) | 0.7 | Delay from a failed acceptance test is excluded: clause 14.3(b), 'a quality matter'
How each risk manager works
Setting | Brian | Sandra | Quentin | Petra | Trevor | Quentin without the test
Early acceptance test at the supplier's works (1 = yes) | 0 | 0 | 1 | 0 | 0 | 0
Re-sequenced commissioning: one more month before the season gate (1 = yes) | 0 | 0 | 1 | 0 | 0 | 1
Insurance (none / tail / full) | none | none | tail | full | none | tail
Budget inflation from available money (Parkinson factor) | 0% | 5% | 0% | 0% | 0% | 0%
Scope-creep multiplier (no register means nobody says no) | 1 | 1 | 1 | 1 | 2 | 1
Firefighting multiplier on costs of risks found late | 1 | 1 | 1 | 1 | 1.3 | 1
The Sandra column reads her 10% + 6 weeks as budget padding only: it changes what she reports, not what happens. What does change the cost is the Parkinson factor.

## Model
The model: one risk register, five risk managers
Every universe below reads the same draws (columns C–D, or the story-year values in E–F when the story switch is on). Totals are ModelRisk outputs; run the simulation from the ModelRisk ribbon.
Part 1: the risk register (one draw per item)
Item | Happens? (draw) | Size if it happens (draw) | Story year: happens | Story year: size | Used: happens | Used: size | Contribution
R1 snag, register row 23 (green) |  |  | 1 | 0.018174
R1 snag, register row 24 (green) |  |  | 1 | 0.007181
R1 snag, register row 25 (green) |  |  | 0 | 0.07428
R1 snag, register row 26 (green) |  |  | 1 | 0.017778
R1 snag, register row 27 (green) |  |  | 1 | 0.009614
R1 snag, register row 28 (green) |  |  | 1 | 0.006544
R1 snag, register row 29 (green) |  |  | 0 | 0.006497
R1 snag, register row 30 (green) |  |  | 0 | 0.005674
R1 snag, register row 31 (green) |  |  | 1 | 0.026591
R1 snag, register row 32 (green) |  |  | 1 | 0.008902
R1 snag, register row 33 (green) |  |  | 0 | 0.015114
R1 snag, register row 34 (green) |  |  | 1 | 0.008112
R1 snag, register row 35 (green) |  |  | 1 | 0.020987
R1 snag, register row 36 (green) |  |  | 0 | 0.00923
R1 snag, register row 37 (green) |  |  | 1 | 0.005402
R1 snag, register row 38 (green) |  |  | 1 | 0.004729
R1 snag, register row 39 (green) |  |  | 0 | 0.032766
R1 snag, register row 40 (green) |  |  | 1 | 0.0066
R1 snag, register row 41 (green) |  |  | 0 | 0.025054
R1 snag, register row 42 (green) |  |  | 0 | 0.013641
R1 snag, register row 43 (green) |  |  | 0 | 0.012043
R1 snag, register row 44 (green) |  |  | 1 | 0.00698
R1 snag, register row 45 (green) |  |  | 0 | 0.00645
R1 snag, register row 46 (green) |  |  | 0 | 0.014184
R1 snag, register row 47 (green) |  |  | 1 | 0.043433
R1 snag, register row 48 (green) |  |  | 1 | 0.014773
R1 snag, register row 49 (green) |  |  | 1 | 0.003974
R1 snag, register row 50 (green) |  |  | 1 | 0.02965
R1 snag, register row 51 (green) |  |  | 0 | 0.003413
R1 snag, register row 52 (green) |  |  | 1 | 0.005157
R1 snag, register row 53 (green) |  |  | 1 | 0.02178
R1 snag, register row 54 (green) |  |  | 1 | 0.015309
R1 snag, register row 55 (green) |  |  | 0 | 0.009582
R1 snag, register row 56 (green) |  |  | 1 | 0.011541
R1 snag, register row 57 (green) |  |  | 1 | 0.003144
R1 snag, register row 58 (green) |  |  | 0 | 0.008896
R1 snag, register row 59 (green) |  |  | 1 | 0.006895
R1 snag, register row 60 (green) |  |  | 1 | 0.028677
R1 snag, register row 61 (green) |  |  | 1 | 0.017187
R5 scope creep, month 1 |  |  | 1 | 0.040505
R5 scope creep, month 2 |  |  | 1 | 0.027322
R5 scope creep, month 3 |  |  | 1 | 0.01426
R5 scope creep, month 4 |  |  | 0 | 0.010699
R5 scope creep, month 5 |  |  | 0 | 0.043851
R5 scope creep, month 6 |  |  | 0 | 0.020654
R5 scope creep, month 7 |  |  | 1 | 0.034703
R5 scope creep, month 8 |  |  | 0 | 0.021658
R5 scope creep, month 9 |  |  | 1 | 0.030833
R5 scope creep, month 10 |  |  | 1 | 0.012557
R5 scope creep, month 11 |  |  | 1 | 0.029683
R5 scope creep, month 12 |  |  | 0 | 0.015886
R1 schedule friction (months at an average snag count) | 1 |  | 1 | 0.36528
R2 filler fails acceptance: site rectification cost |  |  | 1 | 1.4835
R2 filler: site rectification delay (months; same failure as the row above) |  |  |  | 3.9885
R4 fire during hot works: loss |  |  | 0 | 10.7029
Register summary for this year
Snag swarm cost
Snags that bit
Snag schedule friction (months)
Scope creep cost
Filler failed acceptance (1 = yes)
Filler rectification cost if found on site
Filler rectification delay if found on site (months)
Fire (1 = yes)
Fire loss if it happens
Part 2: five universes, same year
| Brian | Sandra | Quentin | Petra | Trevor | Quentin without the test
Base budget as spent (incl. Parkinson factor)
Snag swarm
Scope creep
Filler rectification
Delay (months)
Cost of delay
Finish (month of the year)
Season gate (month)
Christmas season missed (1 = yes)
Lost Christmas contribution
Insurance premium
Early acceptance test
Fire loss
Insurance recovery
TOTAL COST
Over (+) or under (−) the €10m budget
Brian ends up cheaper than Quentin this year (1 = yes)
'Quentin without the test' is not a sixth risk manager: it exists only to value Quentin's €120k acceptance test (see the Dashboard).

## Without ModelRisk
No ModelRisk? The same model in plain Excel
Press F9 for one random year. One year per keypress; ModelRisk runs 10,000 and gives you the distributions. Free trial: https://www.vosesoftware.com/Risk-In-Excel/Download-ModelRisk-trial.php
Part 1: the risk register (one draw per item)
Item | Happens? (draw) | Size if it happens (draw) | Story year: happens | Story year: size | Used: happens | Used: size | Contribution
R1 snag, register row 23 (green) |  |  | 1 | 0.018174
R1 snag, register row 24 (green) |  |  | 1 | 0.007181
R1 snag, register row 25 (green) |  |  | 0 | 0.07428
R1 snag, register row 26 (green) |  |  | 1 | 0.017778
R1 snag, register row 27 (green) |  |  | 1 | 0.009614
R1 snag, register row 28 (green) |  |  | 1 | 0.006544
R1 snag, register row 29 (green) |  |  | 0 | 0.006497
R1 snag, register row 30 (green) |  |  | 0 | 0.005674
R1 snag, register row 31 (green) |  |  | 1 | 0.026591
R1 snag, register row 32 (green) |  |  | 1 | 0.008902
R1 snag, register row 33 (green) |  |  | 0 | 0.015114
R1 snag, register row 34 (green) |  |  | 1 | 0.008112
R1 snag, register row 35 (green) |  |  | 1 | 0.020987
R1 snag, register row 36 (green) |  |  | 0 | 0.00923
R1 snag, register row 37 (green) |  |  | 1 | 0.005402
R1 snag, register row 38 (green) |  |  | 1 | 0.004729
R1 snag, register row 39 (green) |  |  | 0 | 0.032766
R1 snag, register row 40 (green) |  |  | 1 | 0.0066
R1 snag, register row 41 (green) |  |  | 0 | 0.025054
R1 snag, register row 42 (green) |  |  | 0 | 0.013641
R1 snag, register row 43 (green) |  |  | 0 | 0.012043
R1 snag, register row 44 (green) |  |  | 1 | 0.00698
R1 snag, register row 45 (green) |  |  | 0 | 0.00645
R1 snag, register row 46 (green) |  |  | 0 | 0.014184
R1 snag, register row 47 (green) |  |  | 1 | 0.043433
R1 snag, register row 48 (green) |  |  | 1 | 0.014773
R1 snag, register row 49 (green) |  |  | 1 | 0.003974
R1 snag, register row 50 (green) |  |  | 1 | 0.02965
R1 snag, register row 51 (green) |  |  | 0 | 0.003413
R1 snag, register row 52 (green) |  |  | 1 | 0.005157
R1 snag, register row 53 (green) |  |  | 1 | 0.02178
R1 snag, register row 54 (green) |  |  | 1 | 0.015309
R1 snag, register row 55 (green) |  |  | 0 | 0.009582
R1 snag, register row 56 (green) |  |  | 1 | 0.011541
R1 snag, register row 57 (green) |  |  | 1 | 0.003144
R1 snag, register row 58 (green) |  |  | 0 | 0.008896
R1 snag, register row 59 (green) |  |  | 1 | 0.006895
R1 snag, register row 60 (green) |  |  | 1 | 0.028677
R1 snag, register row 61 (green) |  |  | 1 | 0.017187
R5 scope creep, month 1 |  |  | 1 | 0.040505
R5 scope creep, month 2 |  |  | 1 | 0.027322
R5 scope creep, month 3 |  |  | 1 | 0.01426
R5 scope creep, month 4 |  |  | 0 | 0.010699
R5 scope creep, month 5 |  |  | 0 | 0.043851
R5 scope creep, month 6 |  |  | 0 | 0.020654
R5 scope creep, month 7 |  |  | 1 | 0.034703
R5 scope creep, month 8 |  |  | 0 | 0.021658
R5 scope creep, month 9 |  |  | 1 | 0.030833
R5 scope creep, month 10 |  |  | 1 | 0.012557
R5 scope creep, month 11 |  |  | 1 | 0.029683
R5 scope creep, month 12 |  |  | 0 | 0.015886
R1 schedule friction (months at an average snag count) | 1 |  | 1 | 0.36528
R2 filler fails acceptance: site rectification cost |  |  | 1 | 1.4835
R2 filler: site rectification delay (months; same failure as the row above) |  |  |  | 3.9885
R4 fire during hot works: loss |  |  | 0 | 10.7029
Register summary for this year
Snag swarm cost
Snags that bit
Snag schedule friction (months)
Scope creep cost
Filler failed acceptance (1 = yes)
Filler rectification cost if found on site
Filler rectification delay if found on site (months)
Fire (1 = yes)
Fire loss if it happens
Part 2: five universes, same year
| Brian | Sandra | Quentin | Petra | Trevor | Quentin without the test
Base budget as spent (incl. Parkinson factor)
Snag swarm
Scope creep
Filler rectification
Delay (months)
Cost of delay
Finish (month of the year)
Season gate (month)
Christmas season missed (1 = yes)
Lost Christmas contribution
Insurance premium
Early acceptance test
Fire loss
Insurance recovery
TOTAL COST
Over (+) or under (−) the €10m budget
Brian ends up cheaper than Quentin this year (1 = yes)
'Quentin without the test' is not a sixth risk manager: it exists only to value Quentin's €120k acceptance test (see the Dashboard).